| 1Para | Commitment | Specific Action | Date [unless stated Departments to identify dates for achievement of specific actions] | Achieved Yes – Y No - N Not applicable yet – N/A | Specific Progress/New Specifications | If not yet achieved or did not meet commitment date please provide further details |
| --- | --- | --- | --- | --- | --- | --- |
|  | Common Commitments |  |  |  |  |  |
|  | Customer Service |  |  |  |  |  |
| 1 (ref. 20.13) 1a (ref. 22.4) | All public service organisations over the course of this Agreement will be required to commit publicly to service standards for their customers. Performance will be evaluated against these standards and the results published in annual reports or another appropriate format. Improvements in customer service will be a particular focus of the partnership structures going forward. All Departments and Offices will publish a charter of service standards and report on performance against these standards in their annual report. | The Office’s Client Service Guide 2002 – 2004 will be reviewed at end 2004 with a view to publication of a Guide for 2005 – 2007. The Office will publish its first Customer Charter which will include reference to client service standards in relation to internal and external clients. All staff will comply with the obligations set out in the Charter. The Office will through its website and Office facilities improve access for all clients by way of improving services to people with disabilities and provision of Irish language version. The Office will undertake a safety audit of its premises. The Office will prepare a scheme to implement the provisions of the Official Languages Act. The Office will convene meetings of its Client Panel at least once a year. The Office will undertake a further survey of clients. The Law Reform Commission will continue its work under the Second Programme for Law Reform 2000-2007. The Law Reform Commission will, as part of its consultation process and in order to ensure as wide a debate as possible, continue its series of seminars on the publication of Consultation Papers to seek views on its original provisional recommendations before proceeding to Report stage. The Law Reform Commission will review its Health and Safety at Work statement. Ongoing staff training will be provided. The Law Reform Commission will adhere to its service standards as outlined in its Strategy and Business Plan 2003 – 2005 which was issued in January, 2003. The preparation of a new Business Plan will commence in 2005. The Office and the Law Reform Commission will report on performance achieved against the standards in their respective Annual Reports from 2004 onwards. | End-October 2005 December, 2004 December, 2004 onwards Late 2006 End 2004 In line with direction of Minister for Community, Rural and Gaeltacht Affairs. November, 2004 onwards November, 2005 November, 2004 onwards June, 2006 November, 2004 onwards Early 2005 Late 2005 Annual Reports to be published in 2004 to 2006. Early October, 2005. | Y Y Y Y Y Y Y Y Y Y N/A Y N Y N/A N/A Y Y Y Y Y Y Y Y Y Y Y N/A | The Client Service Guide 2005-2007 was finalised in December, 2005, and published with the CSSO Customer Action Plan 2005-2007 on the Office website. The documents have been translated into Irish prior to printing in English and Irish. Proofs currently being checked and it is expected that finalised electronic copies in both languages will be available by end-March, 2006, with finalised paper format available in both languages by end-April, 2006. The Charters for the Advisory and Administration sides of the Office and the Office of the Chief Parliamentary Counsel along with the Charter for the CSSO were put on the Office website in mid-March, 2005. They were printed in English and Irish in booklet form and circulated to clients in mid-May, 2005. All staff are required to adhere to Service Standards set out in the Charters. Client Service continues as a core competency for all staff in the Office under PMDS. Induction course for entrants to the Office includes client service. The second session of the Programme of Education in European Criminal Law put in place by the Office in co-operation with the Office of the Director of Public Prosecutions and the Department of Justice, Equality and Law Reform was hosted by the Office on 23 January, 2006. Approximately 100 attended including staff from the Office, the Office of the Chief State Solicitor, Office of the Director of Public Prosecutions, Department of Justice, Equality and Law Reform, Law Reform Commission, Houses of the Oireachtas, Office of the Revenue Commissioners, etc. The Office in February, 2006, made available to Government Departments/Offices basic guidelines on three key legal topics. These guidelines, which were produced in the Office, are intended to assist generally well informed Civil Servants to bear key legal issues in mind in the formulation of policy among other matters, to formulate legal queries, to understand legal concepts in any such advice, to assist in the drafting of legislation. It is intended to forward further chapters during the next year. In December, 2005, the Office advertised a competition for the recruitment of Advisory Counsel for training prior to secondment to a number of Government Departments as Legal Advisers. Interviews held on 27/28 February and 1 March, 2006. The Public Appointments Service are preparing formal offers of appointment in respect of 4 positions. It is anticipated that at least 1 further position will also become available. The Irish version of the Office’s website went live in December, 2005. The site had earlier been developed in accordance with Public Sector guidelines on accessibility. The site was audited to validate the accessibility and usability measures taken. The Office is currently reviewing tenders for the design and implementation of accessibility and usability measures for the Irish Statute Book element of the website. Procedures for the purpose of ensuring compliance with the Prosecutions of Offences Act 1974 have been established in relation to briefing of Counsel, and a formal consultation process put in place with the Office of the Director of Public Prosecutions which will involve an annual review each Summer. The Office prepared draft website design concepts and briefing on the IT support requirements for the Law Reform Commission. A key feature of the Commission’s website development will be access capability for people with disabilities. Health and Safety Consultants, Nifast, undertook a safety audit of the Office premises at end-January, 2005. Nifast made suggestions for the revision of the Office’s Health and Safety Statement in early-March, 2005. Following further meetings with the consultants, the Statement was submitted in the Office’s Partnership Committee which approved it on 2 December, 2005. The Statement was submitted to the Office MAC for consideration on 22 February, 2006, when the Action Points of the Statement were approved. The full Statement will be considered at the next MAC meeting on 29 March, 2006. A Committee has been set up to help promote the use of Irish in the Office, to promote Irish language training and to raise awareness of Irish among staff. The Committee, known as An Coiste Gaeilge, comprises staff from both the administrative and legal sides of the Office. It meets fortnightly in an informal lunchtime session to discuss an agreed topic. All members of staff are welcome to participate, and attendances are increasing. The first Meeting of the Panel was held in November, 2005. An Action Plan arising from the Report on the meeting will be put in place. The survey has been deferred to end November 2006 but review meetings with clients continue. The Law Reform Commission published a Report on the Court Poor Box; Probation of Offenders and a Report on Multi-Party Litigation in September, 2005, a Report on Corporate Killing in October, 2005, and a Report on the Establishment of a DNA Database in November, 2005 and a Consultation Paper on Legal Structures of Charities in December, 2005. The Law Reform Commission plans to publish a Report on Process Model for eConveyancing, a Consultation Paper on Homicide; the Plea of Duress and Necessity. In December, 2005, the Law Reform Commission was asked to prepare a Government Bill on Land and Conveyancing Law. The Law Reform Commission has received two References from the Attorney General, the first in December 2005 on ‘Adoption’ and the second in January 2006 ‘Good Samaritan’. Work will commence on ‘Adoption’ reference in March 2006 and work on the second reference will not commence until the second half of 2006. In December, 2005, the Law Reform Commission held a Conference on Vulnerable Adults and the Law (over 230 attended including a high number of interest groups and a number of health professionals). The international speakers were from England (Baroness Hale, House of Lords and Master Denzil Lush, Master of the Court of Protection) and Canada (Jay Chalke, the Public Guardian of British Columbia). In January, 2006, the Law Reform Commission held a forum with its Working Group on Cohabitees: Rights and Duties. A consultative seminar was also held. Attendees included those who made submissions and representatives of interested groups. Meetings have been held by the Law Reform Commission with the Medical Council on the issue of new draft ethical guidelines for the medical profession. First meeting of the Law Reform Commission Working Group on Guardianship structure was held in February, 2006. Members of the Law Reform Commission continue to be involved in making presentations to seminars and conferences with a view to furthering debate in relation to ongoing projects. The Law Reform Commission will continue to liaise with relevant Government Departments in relation to its work. The Law Reform Commission carried out its Health and Safety review following an audit by Nifast. Staff training was provided. A new Health and Safety Statement has been approved by the Commission. Further training and staff briefing will be arranged. The Law Reform Commission is preparing its Strategy and Business Plan for 2006-2008. Following a tender completion a consultant was engaged to assist in the process. A review of the Commission’s management structures and processes has taken place. The next stage is the finalisation of the Strategy Statement and Business Plan and subject to ratification by the Commission should be completed by end of April, 2006. Law Reform Commission Annual Report for 2003 published in December, 2004. The Commission’s Annual Report for 2004 was published in English and Irish in August, 2005. Work on preparation of the 2005 Annual Report has commenced and it will include a report on the developments of service standards for its stakeholders. Office Annual Report for 2003 presented to Government in December, 2004. It has been published in English on Office website, translated into Irish and is being printed in both English and Irish and the proofs have been checked. It is expected that the finalised electronic version in both languages will be available by end-March, 2006, and the finalised printed version in both languages by end-April, 2006. A limited number of copies of the English version in Braille have been prepared. Office Annual Report for Office for 2004 presented to Government in November, 2005, has been published in English on Office website. It has been translated into Irish for printing in both English and Irish and the proofs are currently being checked. It is expected that the finalised electronic version in both languages will be available by end-March, 2006, and the finalised printed version in both languages by end-April, 2006. The Report incorporates progress achieved against service standards. Office Annual Report for 2005 is in the process of preparation with a view to publication by end-June, 2006. | A direction from Minister for Community, Rural and Gaeltacht Affairs is expected before end-March, 2006. It was decided that the Client and Customer Panel be given time to bed in. |
|  | Efficient Use of Resources |  |  |  |  |  |
| 2 (ref. 20.11) | The parties to this Agreement will co-operate fully with the modernisation and change required to ensure that maximum value is achieved from all public expenditure in terms of defined outputs and outcomes. | The Office will continue to adopt a Project Management approach for all big projects as a means of enhancing value for money. The Office will complete its Expenditure Reviews in respect of the Law Reform Commission and the Attorney General’s Scheme (jointly with the CSSO) and reviews on Training and Development and the Electronic Statute Book and any necessary action arising will be taken. The Office will review the position in relation to implementation of recommendations of the Audit Committee Reports. Some aspects may have to await rollout of MIF and compilation of new procedures arising therefrom. The Office will roll out the MIF initiative which will be aimed at enhancing VFM. The new FMS will facilitate both cash and accrual accounting, therefore providing enhanced financial management information. The Office, in conjunction with the CSSO, will develop an appropriate interface with the New Case and Records Management System to meet with MIF Requirements. Payment by EFT as part of the development of the FMS will be rolled out. MIF training will be rolled out to appropriate staff. The Office in conjunction with the CSSO, will identify appropriate performance indicators and put in place arrangements for their monitoring and development. The Office is pursuing an Implementation Plan arising from the Report on the Accountability of Secretaries General and Accounting Officers. This has included a review of internal financial procedures both in the Office and the Law Reform Commission, an enhanced internal audit function, installation of a Financial Management System including an asset tracker module, initiation of implementation of MIF and identification of potential risks. Risk Management Strategies will be put in place. A new Case and Records Management System, which covers all Office records, both legal and non-legal, will be installed in the Office in conjunction with the CSSO. It will enhance the quantity and quality of management information and facilitate the introduction of a comprehensive costing package. The Law Reform Commission will review all of its tendering procedures and prepare protocols for same. | From November, 2004 onwards March, 2005 March, 2006 From November, 2004 onwards Mid-2005 November, 2004 end-October, 2005 end-April, 2006 Early-mid 2005 March, 2005 January, 2005 June, 2006 End 2004 End 2005 New system to be piloted in December, 2004, and be rolled out in April, 2005, and new costing facilities to be developed in 2005. End January, 2005 | Y Y Y N/A Y Y Y Y Y Y Y Y Y Y Y Y Y Y Y Y N/A Y Y N/A Y Y Y | Current IT, Electronic Irish Statute Book Project and Expenditure Review Projects being pursued via Project Management approach. Two further staff members received training in project management in January, 2006. Expenditure Reviews on Administration of the Attorney General’s Scheme (completion expected end-March, 2006) and on Law Reform Commission (completion expected end-April, 2006) being progressed. Office wrote to Department of Finance in March, 2005, about Expenditure Reviews to be undertaken in 2006 and 2007 – the Office proposes to undertake an Expenditure Review of the Library and Know-How Unit in late 2006/early 2007, as well as the Reviews on Training and Development and the Electronic Irish Statute Book Project. Draft terms of reference and proposed membership of the Steering Group on the Electronic Irish Statute Book Project were approved by the Electronic Irish Statute Book Group on 14 March, 2006. Steering Group will hold its first meeting on 22 March, 2006 – some members commenced Expenditure Review training on 7 March, 2006. Further Report on implementation in the Office and in the Law Reform Commission of recommendations of the Audit Committee Reports submitted to the Office MAC and to the Audit Committee in December, 2005. Practically all of the recommendations have been implemented. The Audit Committee will review the position again at end-2006. The non-ACME (new Case and Records Management System) dependent functionality has been embedded since end – 2004. The integration between it and that the ACME dependent functionality continues to be tested taking account of financial control procedures. Management and Costing Reports are made available from FMS to Office MAC, the joint AGO/CSSO MAC and senior management. The MIF Project Board, representative of the Office and the CSSO, was restructured and now includes Partnership Committee representatives from both Offices. The new Board and a Sub-Group review the Offices’ MIF Project Plan, which has been displayed on the Office Intranet. The MIF Project Manager provides updates on implementation of the Plan to each Office MAC, Partnership Committee, IT Steering Committee, MIF Project Board meeting to a fortnightly meeting of the MIF Sub-Group and to MIF Central Unit on a regular basis. Integration with the Case and Records Management System (ACME) will continue in line with progress of the ACME Project. Interface developed, subject to implementing some financial control procedures. The functionality to enable EFT payments are in place. Testing of the technical structures has been undertaken and an initial payment completed. It is planned to have the system in fully place by end-March, 2006, with a view to operation from April, 2006, onwards. The Law Reform Commission has put in place all of the requirements for EFT. Training has been provided and appropriate protocols and procedures agreed. The Law Reform Commission has decided to make all tax payments through ROS and has developed a protocol in respect of same. MIF Training Course Sessions held for MAC members and Business Unit heads and staff representatives from the Law Reform Commission on 6/7 October, 2004, 23/24 February, 17/18 May and 10/11 October, 2005. Two other AG0 MAC members had attended an earlier pilot session. Briefing/information notes on MIF are available on the Office Intranet and briefing sessions on ACME/MIF awareness will be made available to relevant AGO and CSSO staff from April, 2006. The Office and the CSSO commissioned assistance to facilitate work on identification of performance indicators by July, 2005, taking account of performance indicators included in the Offices’ Statement of Strategy and Business Plans. The consultants having met senior management held a series of workshops in April and May, 2005 to identify performance indicators. The resultant Report was finalised in June, 2005, placed on the Office Intranet. It is being considered by MAC and Partnership in the context of the Office’s Statement of Strategy 2006-2008 currently being finalised with an envisaged completion date of end-April, 2006. New Business Plans will be developed taking account of the new Statement of Strategy. The Office has addressed all of the recommendations arising from the Mullarkey Report. The reviews on internal financial procedures in the Office and in the Law Reform Commission were concluded and recommendations approved by the Audit Committee are being progressed. The procedures were reviewed again in December, 2005, and a Report was submitted to, and approved by, the Audit Committee at its meeting on 23 February, 2006. The Report will be considered by the Office MAC on 29 March, 2006. The asset tracker software was installed in the FMS in January, 2005, and a workshop for users was held on 15 February, 2005. The Office has submitted draft load sheets of 2004 and 2005 assets to the system vendor for testing and these will be put on live on 31 March, 2006. Assets for 2002 and 2003 have been verified and bar-coded and transferred to a load sheet for testing. The Law Reform Commission has carried out a full audit of its IT assets and maintenance and has put in place an ongoing updating process to track faults within the system. The Office, in conjunction with CSSO, proposes to install Invoice Manager with a view to its operation from 1 July, 2006. A Project Plan has been agreed setting out relevant project milestones. The Audit Committee on 23 February, 2006, approved its Annual Report for 2005 and Schedule of Audits for 2006. These were accepted by the Joint AGO/CSSO MAC on 2 March, 2006 and placed on the Office Intranet. The Law Reform Commission has decided to establish an Audit Committee in accordance with the Code of Practice of State Bodies. The LRC Audit Committee will liaise with the Office Audit Committee in order to avoid duplication of effort. Risk Management Strategies were initially adopted in the Office in the context of Group/Unit Business Plans. Disaster and Recovery Plans were put in place in the Library and Know-how Unit and Registry. Subsequently, the Office, in conjunction with the CSSO, commissioned assistance in devising whole-of-Office Risk Management Strategies. These took account of the work already done by the Offices via the business planning process which involved specific tailoring of the Department of Finance Guidelines on Risk Management. Following a Special MAC meeting on Risk Management, a series of workshops took place during the last week of June, 2005, to assist with the identification of risks. Follow-up interviews with workshop participants took place. Draft Risk Registers in respect of the legal and administrative sides of the Office have been supplied to the Office and are being reviewed by a Sub-Group of the joint AGO/CSSO MAC (Risk Management Committee) and will be submitted to MAC at end-March, 2006 and to the Audit Committee, Partnership Committee and to the Joint AGO/CSSO MAC. Nifast, Health and Safety Consultants, undertook a safety audit of risks and made suggestions for the revision of the Office’s Health and Safety Statement. These were considered by the Office and the Statement revised. The document was then submitted to the Office’s Partnership Committee and approved by it on 2 December, 2005. It has also been submitted to MAC for consideration. At its meeting on 22 February, 2006, the MAC approved the Action Points of the Statement and will consider the full Statement at its meeting on 29 March, 2006. The Office, in conjunction with the CSSO, will commission assistance to undertake a risk analysis with a view to updating IT Disaster Recovery arrangements on an Office-wide basis. An Invitation to Tender for Business Continuity and Management Consulting services across both the Office and the CSSO has been prepared. The Law Reform Commission carried out a preliminary risk analysis of its IT and Library operations, Financial administration and Health and Safety procedures in 2005. Further detailed risk assessment analysis to be carried out by Commission by June, 2006. A detailed operating IT plan is now in place. The piloting of the new Case and Records Management System (ACME) commenced in the Asylum and Registry areas in both the Office and the CSSO on 11 April, 2005. Technical and functional issues arising from the pilot continue to be addressed. Specifications have been agreed in respect of all areas in both the Office and the CSSO, workflows have been reviewed between both Offices with a view to streamlining the progress of State litigation, ensuring that reminder notifications to keep track of both internal and external correspondence are provided for, and Records Management Policies have been developed. Phase 1 of the roll out of the system to State Property and Advisory and Parliamentary Counsel drafting areas was commenced in December, 2005. System testing for phases 2 and 3 was completed at the end of 2005. Initial UAT for these phases has been completed with further development and retesting ongoing. Testing of the management information reporting functionality continues. Further development of management information reports is underway. Specific Training for those involved in the pilot took place in early to mid-April, 2005, and a programme of refresher training was put in place. All staff are being trained on the new system before it is rolled out to their areas. The final phases of the roll out to all remaining areas in both Offices is expected by end-June, 2006. The Law Reform Commission reviewed its tendering procedures and drew up appropriate tender documentation. | Final draft of Review on AG’s Scheme has been revised to take account of comments of External Evaluator and is with the Chief State Solicitor for sign off. The published version will take into account recent developments arising from the agreement with the Department of Justice, Equality and Law Reform on the transfer of the administration of the Scheme to that Department along with progress made in clearing outstanding arrears of payments. Draft of LRC Review discussed with External Evaluator who submitted observations. Law Reform Commission also provided comments which have been considered. The Evaluator’s Report will be considered by the Expenditure Review Steering Committee on 29 March, 2006. |
|  | Better Regulation |  |  |  |  |  |
| 3 (Ref. 20.16) 4 (Ref. 20.17) | The Government is committed to publishing a National Policy Statement on Better Regulation in 2003. A model of Regulatory Impact Analysis (RIA) will be introduced on a pilot basis in a number of Government Departments during 2003. In the light of the pilot phase, a model of RIA appropriate to the Irish context will be introduced. | The White Paper on Better Regulation which was published in January, 2004, included proposals in respect of improving the accessibility and coherence of Irish Statute law. These proposals have a substantial impact on the work of the Office. |  | Y | As a matter of policy the Law Reform Commission continues to include draft legislation in its final Reports where relevant. |  |
| 5 (Ref. 20.18) | Well-drafted, easily understood and accessible regulation can reduce the difficulties and costs of compliance for both businesses and citizens. Building on progress in recent years and utilising the provisions of the Statute Law (Restatement) Act, a structured programme targeted on areas where the benefits to business and the citizen are likely to be greatest will be pursued to achieve these improvements in regulations. | There has been an increase in work related to the policy of Restatement following the enactment of the Statute Law (Restatement) Act 2002. The Office is involved in advising Departments on the strategy to be adopted to improve access to legislation through a policy of restatement, advising Departments on technical aspects of Restatements and, certification of Restatements by the Attorney General as is required by law. The Office commissioned consultants to prepare a Business Case and Draft Request for Tender in relation to Restatements. Proposals will be made to the Attorney General. Arising from an audit of pre-1922 legislation undertaken by the SLRU in 2003 a Statute Law Revision Bill repealing obsolete legislation is being prepared for publication. Advice is being prepared for Government as to what should be done in relation to pre-1922 legislation still in force and needed. The Office of the Parliamentary Counsel will participate in any further consultation process that may take place in relation to changes in layout and presentation of Bills that may be made by the Houses of the Oireachtas. The Office will pending the establishment of an appropriate national website, continue to make available the Chronological Tables, Statutes and Statutory Instruments on its website. In line with the greater awareness of the need to improve the accessibility and coherence of legislation, following the publication of Reducing Red Tape an Action Plan for Regulatory Reform in Ireland (1999), Regulatory Reform in Ireland (OECD, 2001) and Towards Better Regulation (2002) and the Law Reform Commission’s Report on Statutory Drafting and Interpretation: Plain Language and the Law, it is anticipated that the Office will experience an increase in consolidation and revision/reform work. Moreover, work involving both drafting and legal advice expertise is currently underway in the areas of company law, the codification of all substantive criminal law and all law relating to the sale of alcohol and consumer law. The Law Reform Commission in its Second Programme for Law Reform 2000-2007 and under the heading, Access to Justice, will undertake a comprehensive review of the Courts Acts. This will involve a review of relevant pre-1922 Statutes. In the context of its Trust Law project the Law Reform Commission will also consider what pre-1922 Statutes needs replacement and reform. The Law Reform Commission, in the context of e-Government commenced in 2003 an e-conveyancing project which will have a major input on conveyancing when implemented. The Commission’s Consultation Paper on the substantive law element of this project was launched in October 2004. This includes a review of over 150 pre-1922 Statutes. Following a Conference on modernising land law in November, 2004, the final phase of the substantive law element is the preparation of a Report by the Commission. This will include draft legislation. | From November, 2004 onwards End 2004 End 2004 Mid/Late 2006 June, 2006 Mid-2006 November, 2004 onwards September, 2006 November, 2004 onwards Commencing 2005 Commencing 2005 Late 2005 End-June, 2006 | Y Y Y N/A Y N/A Y Y Y Y N/A N/A Y N/A | Work on Restatements suspended, pending completion of review of consultant’s Report (see next item). A revised draft of the consultant’s Report on Restatements Policy is under consideration in consultation with the Law Reform Commission. The Commission is at the preliminary stage of considering the strategic issues that would arise if it were to agree to undertake the Restatement project. The Statute Law Revision (Pre-1922) Bill 2004 was enacted at end 2005. It removed over 200 redundant Acts from the Statute Book. In early 2005 the Office commenced a comprehensive audit of all Pre-1922 legislation. Arising from this a Statute Law Revision (Pre-Union) Bill 2006 is being prepared. The Bill will retain less than 300 of the 2,600 pre-1801 Acts still in force. A process of consultation is currently in progress. Comments on the proposed repeals have been requested by 30 April, 2006. At a later stage it is proposed to bring forward a Bill dealing with Acts during the period 1801 to 1922. The Office also continues preparation of an electronic database which will list the Acts which remain in force since the pre-1922 period and the Law Reform Commission has also assessed relevant legislation from that period in relation to its Court Acts project having completed its work on Land Law. This database will provide a template for future Statute Law revision and it is planned that a version of the database listing the Acts will be electronically accessible. The Law Reform Commission dealt with over 157 pre-1922 Statutes as part of its work on the Reform and Modernisation of Land Law and Conveyancing Law to include the publication of draft legislation. The Commission has also been asked by Government to prepare the draft Bill. The Office of the Parliamentary Counsel continues to be in consultation with the Houses of the Oireachtas on the Bill-drafting needs of the Office. Work continuing on updating data for the Electronic Irish Statute Book – Chronological Tables for 2004 and Acts to end 2005 and Statutory Instruments up to no. 350 of 2005. Office website and CD ROM expected to be updated by end-April, 2006. The Office liaised in July, 2005, with the high-level Better Regulation Group to establish a group (Interdepartmental Working Group on Electronic Statutory Instruments) to examine the possibility of standardising the procedures for the drafting and publication of statutory instruments. The Interdepartmental Working Group has had regular meetings since then. It is anticipated that a project to modernise the electronic publication of Statutory Instruments will be introduced on a pilot basis by Autumn 2006. The Office has set up a post-independence database containing all of the Acts of the Oireachtas enacted since 5 December, 1922. A project to track the commencement status of these Acts and any repeals commenced on 8 March, 2006. Social Welfare Consolidation Bill 2005 enacted. It consolidates 19 Acts enacted since 1993 up to the Social Welfare and Pensions Act 2005. The Law Reform Commission convened the Working Group on the Courts Acts Codification and Reform in December, 2005. The Commission is incorporating a consolidated Courts Bill of post-1922 legislation into its legislative template which will take account of subsequent amendments to that legislation. When this ‘template’ work has been completed, (having already identified relevant pre-1922 legislation to include amendments and repeals), it will allow for manipulation of text. As this exercise is being done areas in need of reform are also being examined. The Law Reform Commission published a Consultation Paper on Trust Law in February, 2005, and as part of its work on the Trust Report is reviewing pre-1922 legislation in this context. The Law Reform Commission published its Report on Modernisation of Land Law and Conveyancing which included draft legislation in July, 2005. The Law Reform Commission will publish a Report on eConveyancing by end of June, 2006. It will have appended to it the management consultants Report on “Modelling of the Irish Conveyancing System”. |  |
|  | Stable Industrial Relations |  |  |  |  |  |
| 6 (Ref. 19.3, 19.6 and 20.5) | The parties are committed to maintaining a well-managed industrial relations environment to minimise disputes affecting the level of service to the public. In this regard the agreement provides that: (i)No cost increasing claims for improvements in pay or conditions of employment will be made or processed during the course of the Agreement. (ii)Precludes strikes or other forms of industrial action on any matter covered by the Agreement. | The Office and the Law Reform Commission will monitor the position to ensure that no issue leads to industrial action. In the Office biannual meetings between management and Union representatives will continue. The partnership approach will be used in the Office and in the Law Reform Commission to foster good industrial relations. The Law Reform Commission will prepare a book of administrative protocols for best practice in consultation with staff. | November, 2004 onwards November, 2004 onwards Early 2005 | Y Y Y Y N Y | Second 2004 Office Management/Union meeting held on 28 September, 2004. The first meeting of 2005 arranged for 5 April, 2005, was deferred. In the meantime relevant issues have been successfully dealt with by the Partnership Committee or by more informal management/ union consultation and neither management or unions felt that additional meetings were necessary. The facility to have such meetings as necessary remains. The Law Reform Commission management and staff continue to foster good industrial relations. A strong consultative approach was taken with Law Reform Commission staff in the preparation of the Commission’s Statement of Strategy and Business Plan. The Office Partnership Committee and Sub-Committees continue to consider important issues. For instance, the Office’s HR Strategy, Sick Leave Procedures, Probation Procedures and Health and Safety Statement all had significant Partnership Committee input and more recently the Committee agreed Interview Guidelines for all future competitions in the Office. The Law Reform Commission has to hand a book of administrative and procedural protocols for use by management and staff. These will also be accessible on the Commission’s Intranet which is currently being developed. |  |
|  | Performance Management Systems |  |  |  |  |  |
| 7 (Ref. 20.7) | Where these are not already in place, the parties agree that appropriate performance management systems will be introduced so that developed performance management systems will be fully operating in each sector of the public service by 1st January, 2005 | The PMDS has been in place in the Office since 2001. The Office will introduce the centrally produced implementation plan for upward feedback, subject to any necessary adaptations, by integration into the Office’s existing PMDS systems in respect of the 2005 cycle. The Office’s PMDS Implementation Working Group, a Sub-Committee of the Partnership Committee, with cross-Office representation, will consider issues, monitor the implementation of the Action Plan agreed by MAC and Partnership arising from the attitudinal/climate survey of PMDS, assess the implementation of existing core competencies so as to ensure that they continue to lead to organisational development in the chosen direction of the Office, and in relation to its core functions. Each year the Office and the Law Reform Commission will choose appropriate core competencies and implement plans for their development. Priority will continue to be given to PMDS training. A Sub-Committee of the Partnership Committee have been examining the issue of communications within the Office. Arising from their recommendations which are currently being considered by Partnership a communication strategy will be developed and put in place. Information about expenditure on training identified through PMDS will be provided in Progress Reports. The Law Reform Commission commenced implementation of the PMDS in early 2002 and has consulted with its staff. As a result, the Commission has agreed a core competency profile for each member of staff. From the information obtained a detailed Training Plan will be put in place. This Plan will be reviewed on a quarterly basis in light of the core functions of the Commission. | January, 2005 November, 2004 onwards End 2004 April, 2005 onwards end December 2004 | Y Y Y Y Y Y Y | Upward Feedback operated in 2005 PMDS cycle. The Action Plan has been monitored with most of its objectives achieved. In particular “open” meetings are now a regular feature of each Unit’s work. Bullying and Harassment workshops were held in September, 2004. The undertaking to give training to management on interpersonal skills/communications is to be incorporated in a Management Training Programme. Proposals in relation to such a programme are being considered by MAC. A follow-up survey will follow later in 2006. New staff trained in PMDS with courses held on 20/21 October, 2004, 2/3 March, 22/23 November 2005 and 22/23 February 2006. The PMDS Working Group met on 15 March, 2006 in relation to implementation of the next developments with PMDS, in particular, the rollout of formal linking of PMDS to increments, probation and promotion. Necessary training will be provided to all staff. Sub-Committee of Partnership submitted a Communications Action Plan for consideration by Partnership at its meeting on 6 May, 2005, and this was approved on 3 June, 2005. The Action Plan is now being implemented – Office Intranet has been developed and Grapevine, an Office newsletter, produced jointly with the CSSO, is used as a mechanism for disseminating Office information/ developments. Each Partnership Committee meeting is briefed on developments in the Office. Expenditure of €115,954 was incurred by the Office in PMDS related training in 2004 and €21,150 in 2005. The Law Reform Commission incurred €11,500 in training in PMDS in 2004, €7,000 in 2005 and €1,000 to date in 2006. The Law Reform Commission has completed a review of its PMDS core competencies and an appropriate PMDS Training Plan has been put in place. Training has been received by two members of Law Reform Commission staff on the IPA course: “Moving into Management in the Public Service”. Three members of staff have received training in EFTS. Further relevant staff training to be organised. |  |
|  | Modernisation and Flexibility |  |  |  |  |  |
| 8 (Ref. 20.6) | The parties are committed to increased flexibility to ensure that public services are delivered in a manner which more closely reflects the needs of its customers. In accordance with this: | Significant flexibility already exists in the Office and in the Law Reform Commission in that staff co-operate to ensure that projects are completed on time and also fill in for absent colleagues on leave etc. Where appropriate, this flexibility will be enhanced. Training will continue to be provided for relevant staff. In the context of the effects that decentralisation will have on staffing in the administrative side of the Office, existing staff will document practices, procedures and precedents and training will be given to other staff to enable them to effect the duties involved. Staff will be moved in order to ensure that any impact due to decentralisation is spread throughout the Office. | From November 2004 onwards | Y Y Y | Significant flexibility continues to be demonstrated in areas such as implementation of IT projects in the Office. A notable example is the involvement of a significant number of staff in data migration, review of fileplan, workflows and screenshots, user acceptance testing and writing scripts for the Case and Records Management (ACME) project. The Law Reform Commission staff continue to provide flexibility to ensure that work projects are completed on schedule. An Office Action Plan in respect of the impact of Decentralisation has been formulated. Each Group/Unit in the Office has documented practices, procedures and precedents for each position. Staff members interested in decentralising have been identified and an evaluation of the risk based on those likely to transfer to ‘Early Mover’ Departments/Offices has been made. In order to assess the likely timescales, contact has been made with all Departments to which staff wish to move in order to assess likely timescales. Additionally, the Office has been in contact with the Central Decentralisation Unit to clarify the procedures to be applied to any staff moves. The Office has prepared itself as far as practical. However, the actual movement of staff to and from the decentralising Departments/Offices has been considerably slower than anticipated. |  |
|  | Team working, cross-functional and cross-departmental working |  |  |  |  |  |
| 9 (Ref. 21.5) | All of the parties will co-operate fully with initiatives in these areas and it remains open to management to implement such initiatives in accordance with the provisions of this Agreement. | The Office commits itself to the continuation of team working which is an Office competency under PMDS, and cross-functional working initiatives such as the introduction of new IT systems and policies. The Law Reform Commission separately commits itself likewise. The Office will continue to participate in cross-Departmental initiatives. The Office will continue to promote the use of project management. In line with the Office’s Knowledge Management Strategy, group and other meetings in the Office will continue to be developed to enhance the culture of knowledge sharing. This will assist in promoting team-working, circulation of information on technical business unit issues and on wider Office issues. It will also be a factor in facilitating flexibility and mobility of staff. The new Human Resources Strategy to be agreed by Partnership will focus on issues such as mobility within the Office. The Strategy will be implemented progressively. The Law Reform Commission will prepare a Human Resources Policy document. | November, 2004 onwards November, 2004 onwards November, 2004 onwards November, 2004 onwards End 2004 From January, 2005. Mid 2005 | Y Y Y Y Y Y Y Y Y | Teamworking course held on 27 January, 2005, attended by 6 AGO staff, 4 CSSO staff and 1 Law Reform Commission staff member. A course held on 6 July, 2005 was attended by 6 AGO staff. Two further courses on 19 and 20 July and 22 November, 2005, were each attended by 1 staff member. After a full review of the Law Reform Commission’s IT systems and policies to enable more efficient work practices to be put in place, the Commission has developed a resilient IT system with dedicated backup. The Commission will continue to ensure constant updating of the system. This participation continues. The Office initiated a Serials Management Project to co-ordinate the purchase and supply of journals to the AGO, CSSO and Office of Director of Public Prosecutions libraries in both print and electronic formats for the period January, 2006- December, 2007. The Office also initiated a Monograph Supply Project to co-ordinate the approach to the purchase of monographs to the AGO and CSSO Libraries for the period January, 2006 – December 2006. Contracts and Service Level Agreements have been agreed and signed for both of these projects. This process continues. Legal Issues meetings were held on 27th September 2005, 7th December 2005 and 1st March 2006 and were well attended. The Legal Issues Meetings are advertised in the CSSO and vice versa. A webpage has been developed for Legal Issues Meetings. The webpage contains information on the meetings and links to electronic copies of papers presented. Meetings of administrative staff with management took place on 4 April, 23 May, 2005. On 3 August 2005 the HR Manager met with Administrative staff to update them on Decentralisation and to respond to questions thereon. Another meeting is being arranged for April 2006. Partnership Committee on 15 March, 2005, approved the new Human Resources Strategy. Many facets of the Strategy are already being implemented. Aspects of the Strategy such as Decentralisation and Interview Guidelines were prioritised. Work will now commence on formulating a formal Action Plan to implement any aspects of the Strategy not already in place. The Law Reform Commission has prepared a draft Human Resources Policy document to be agreed by staff and the Commission. The finalisation of the document is awaiting the findings of the Commission’s Strategy Statement and Business Plan to be published by the end of April, 2006. |  |
|  | New Technology and eGovernment |  |  |  |  |  |
| 10 (Ref. 21.6 and 21.7) | It is accepted that the use of new technology may necessitate significant change in work processes in order that the benefits of technology will be maximised. There will be full co-operation with the design and implementation of eGovernment projects. | Some major IT based initiatives are underway at present in the Office, in conjunction with the CSSO, on foot of its current IT Plan. These include the implementation of a new Case and Records Management System, a new Financial Management System, an e-Legislation system, a Human Resources Management System and a Legal Know-how Application. Also, the Office has prepared a Knowledge Management Strategy 2003 – 2005 in conjunction with the CSSO. The implementation of this strategy will ensure that both Offices capture, organise and share knowledge, experience and expertise. All of these systems offer opportunities for process review and improvement and these opportunities are being, and will continue to be, availed of where appropriate. All staff commit themselves to adopting the new procedures arising from the implementation of new IT systems within the Office, in particular, full compliance with training obligations and other aspects which fall out of the implementation of the Plan in relation to the Case and Records Management System, Management Information Framework, e-Legislation, e-Cabinet etc., full compliance with the changeover from Lotus Notes to Microsoft Outlook and training as to Microsoft Outlook and full co-operation with IT training to ensure levels of IT proficiency. The development of an interface between the new Case Records Management System and the Financial Management System will enhance the quantity and quality of management information and facilitate the introduction of a comprehensive costing package thus ensuring that the Office meets its MIF requirements. The Law Reform Commission will continue to develop the IT efficiencies of its Library administration. This will enable access from all desktops using the Sirsi and Unicorn networks which are hosted by the Office. The Office is committed to fully supporting and facilitating the e-Government agenda, particularly e-Cabinet and e-Legislation. The Office is a key driving force behind e-Legislation and will maintain close contact with other stakeholders including the Office of the Houses of the Oireachtas and Government Departments. The Office will continue to co-operate with the Courts Service in the development of its IT strategy. Members of the Office’s legal and IT staff are members of and participate in the work of the Supreme Court Group on Computerisation. The Office is committed to improving access to legislation through: work underway to add the 2003 Chronological Tables on the Office web page. The 2004 Statutes will be added to the web page by the third quarter of 2005. advising Government on a policy to be adopted as regards pre-1922 legislation | End 2005 Commence implementation of Case and Records Management System in December 2004 on a pilot basis and fully from April, 2005. Implement Legal Know-how Application from End 2005. Implement Knowledge Management Strategy by end 2005. Implementation of training in new systems to continue to Mid 2006. Implementation of Financial Management System and roll out of Management Information Framework to Mid 2005. Implementation of Human Resources Management System from Mid 2006. Mid 2005 Mid 2006 November, 2004 onwards. End November, 2004. September, 2005 End-February, 2006 | Y Y Y Y Y N/A Y Y Y N/A Y Y N/A Y N Y Y | Piloting of ACME commenced on 11 April, 2005. Specific training for all those engaged in ACME pilot project took place in early to mid-April, 2005 and a programme of refresher training is being put in place. Specifications have been agreed in respect of all areas in both the Office and the CSSO, workflows have been reviewed between both Offices with a view to streamlining the progress of State litigation, ensuring that reminder notifications to keep track of both internal and external correspondence are provided for, and Records Management Policies have been developed. Phase 1 of the roll out of the system was commenced in December, 2005, to the Advisory, Parliamentary Counsel drafting and State Property areas System testing for phases 2 and 3 was completed at end-2005. Initial UAT for those phases has been completed with further development and retesting on-going. Testing of the management information reporting functionality has commenced. Further development of management information reports is underway. Full training has been provided for pilot users and those involved in phase 1 of the roll out. General system training has commenced for users in phase 2. Following this, workflow training will be delivered prior to commencing roll out of phase 2 by end-March/early April. Training has commenced for super users for both phases 2 and 3. Currently over half of the staff in both the Office and CSSO have access to the system. Knowledge Management Strategy largely implemented. Training on ACME and FMS continues. FMS being implemented - went live on 1 July 2004. Core models in full use. MIF being rolled out in accordance with Office Project Plan. Following a consultant’s evaluation CMOD substantially revised the roll-out of a Civil Service HRMS. Although this has resulted in delays generally it is anticipated that the Office will still meets its previously advised target of September 2006. Two double issues of the Legal Bulletin and ECHR Bulletin were prepared by the Office/CSSO during August-December, 2005. The first series of seven Legal Reference Guides has been substantially completed and made available to legal staff in print and electronic formats. Copies of AGO Legal Reference Guides are in the CSSO Library and Know-how Unit and vice versa. 5 AGO and 2 CSSO Staff trained on Microsoft Outlook during 2005. All relevant staff trained and operate new eCabinet system. Office manual made available to relevant staff and placed on Office Intranet. The interface between ACME and FMS continues to be developed and tested. Some financial control procedures remain to be implemented before full roll out. The Law Reform Commission, with the assistance of the Office, has access to the Unicorn Collection Management System. The Office continues to work with the Law Reform Commission to further develop Unicorn in the Commission, for example, by providing advice and training on the implementation of the circulation acquisitions and serials control modules of Unicorn, and by providing any other training as required. The Law Reform Commission following a review of the efficiencies of its IT desktop publishing templates has put new templates in place and training has been provided to all staff. The Commission has implemented a protocol on the completion of publications. It has also adopted a legislation template in addition to augmenting the publications template to include an index of cases and statutes to be included in publications from January, 2006. The Commission has also compiled a database in respect of submissions made by interested parties on Consultation Papers published by the Commission. As indicated the relevant Office staff have been trained and operate the eCabinet system. An Office manual has been made available to them and it is also displayed on the Office Intranet. The Supreme Court Computerisation Working Group is in abeyance pending further development and preparation for the implementation of a new system. Work continues on preparation of 2004 Chronological Tables and 2005 Acts and Statutory Instruments up to Number 350 of 2005 for placing on Office website and CD ROM by end-April, 2006. Statute Law Revision (Pre 1922) Bill 2004 enacted in November, 2005. Work commenced on preparation of another Revision Bill which is expected to be published in mid-2006. | Once the new ACME system is in place, the matter of a Legal Know-how Application will be reviewed. This review will be carried out against criteria, including those outlined in the KM Strategy. OPC to update. The Office of the Parliamentary Counsel is engaged in the ACME project. When that project is implemented the status and direction of eLegislation project will be considered. (see progress under paragraph 5 above). |
|  | Atypical Working Arrangements |  |  |  |  |  |
| 11 (Ref. 21.8) | The work pattern may be such in specific areas that specific work processes can be performed most effectively by part time staff. | Job-sharing is a feature in the Office and staff also avail of parental leave and term time. The Office is also piloting teleworking from end November, 2004. The Law Reform Commission is aware of the potential for assisting the work of its part-time Commissioners and legal experts by introducing external network access. | End November, 2004 2005 | Y Y N/A | Telecom/IT infrastructure put in place and health and safety inspections of the home locations took place in mid-May, 2005. Since then 4 of the 5 eworking applicants have worked from their home locations. One e-worker transferred in early January, 2006, to a Government Department. A review of the pilot will be undertaken in May, 2006. Currently 18 staff members (or 15% of all permanent staff) avail of atypical working arrangements such as work sharing, parental leave, e-working or special leave. A further 7 have applied to avail of term-time arrangements during Summer 2006. The Law Reform Commission has recently introduced external network access IT for members of the Commission and the Director of Research. A protocol has been put in place to ensure restricted use to comply with security arrangements. |  |
| 12 (Ref. 21.9) | Situations may arise where the need to respond to temporary pressures may require the employment of temporary staff or outsourcing of work. Unions will be notified in advance of initiatives of this kind. | Following consultation with the unions contract workers are employed in the Office and some work is outsourced. This consultation will continue. |  | Y | This process continues. IMPACT consulted re engagement of Consultant Drafters and Pre-1922 legislation Research Assistants. Relevant staff are kept informed of arrangements in respect of contract workers, e.g. Registry and Finance Unit. |  |
|  | Attendance Patterns |  |  |  |  |  |
| 13 (Ref. 21.10) | In order to provide a satisfactory level of service to the public, there is a need in certain areas for changes to the standard working day in order to provide services outside the traditional “9 to 5” pattern. The parties are committed to discussions to establish how this can best be achieved, where required. | The Office does not have many direct dealings with members of the public and this is, therefore, not a significant issue. In the past, developments with a potential impact on attendance patterns such as changes to the operation of the flexible working hours system have been discussed with staff in advance. This approach will be continued in the future and any proposed change in attendance patterns will be reviewed through Partnership. The Office and the Law Reform Commission operate systems whereby certain staff are available where necessary out of core hours. |  | Y Y | This process continues. The Office and the Law Reform Commission continue to maintain staff flexibility on working out of core hours. Subject to its needs, the Commission has introduced on a trial basis an electronic flexitime system to enable staff to record working hours and to also monitor any additional hours worked. |  |
|  | Redeployment of Staff |  |  |  |  |  |
| 14 (Ref. 21.11) | Redeployment of staff may be necessary on occasion to respond to urgent work demands. | The Office and the Law Reform Commission have and will continue to reorganise themselves to respond to urgent work demands. | November, 2004 onwards | Y | The Office and the Law Reform Commission continue to reorganise work schedules in order to respond to urgent work demands. Recent examples include reassignment of staff to assist in the introduction of new work practices in Registry. |  |
|  | Management of the Introduction of Change and New Development |  |  |  |  |  |
| 15 (Ref. 21.12) | In accordance with the partnership approach, unions will be informed in advance of all new significant workplace related initiatives, the reasons for them and the proposed implementation date. Notification will be given in advance and in sufficient time to allow discussions with the union(s) concerned to take place. Such discussions will cover the nature of the changes involved, the reasons for them and any impact on staff. The discussions will be approached in a partnership manner and will be concluded in time to allow the changes to be introduced by the date specified. Subject to this, it is accepted that management have the right to implement changes in accordance with the provisions of the Agreement. | Changes and developments in the Office and the Law Reform Commission are discussed as appropriate with unions and staff and also in the case of the Office through the Partnership Committee. Extensive use is made of the Intranet and e-mail systems for keeping all staff in the Office informed of developments. | November, 2004 onwards | Y Y Y | These processes continue insofar as the Office is concerned. There is continued engagement by all staff in the Office in the rollout of ACME and MIF. The Law Reform Commission holds regular meetings to brief all staff of developments in work practices and has introduced “Current Work” communication updates. The regular publication of the Commission’s rolling work programme schedules and prioritises work demands. |  |
|  | e-Government |  |  |  |  |  |
| 16 (Ref. 20.19) 16 a (Ref. 22.24) | The parties are committed to the further development of eGovernment on the following basis: F( i) facilitating better citizen access and interaction with the public service by realising the potential of information and communication technologies (ICTs);  (ii) building collaborative knowledge-based structures focused on serving both citizens and the public service; and (iii) facilitating continuous adaptation and improvement in service delivery by fully utilising ICTs to deliver public services seamlessly and across traditional boundaries. The parties commit to full co-operation with the further development and implementation of eGovernment policy as outlined in ‘New Connections’, the Government’s Action Plan to realise the potential of the Information Society. | See paras 21.6 and 21.7 The Office and the Law Reform Commission will continue to regularly review their websites to ensure that the information contained therein is kept up to date. The Office’s website will be redeveloped by end November, 2004, while the Commission’s was redeveloped earlier. The Office and the Law Reform Commission will continue to develop the Intranet as an important channel of internal communication. See paras 21.6 and 21.7 | November, 2004 onwards. November, 2004 onwards. March, 2006 | Y Y Y | See comments on section 20.13 on Office and Law Reform Commission websites. The new Office Intranet site went live on 4 July, 2005. The Intranet includes the following new features; - design standards that will enhance accessibility - an index to allow for searching across the entire site - Telephone Directory and Who’s Who database direct from a web browser - Minutes and Agendas for MAC and Partnership meetings including links to briefing papers. The Intranet is continually updated. The Law Reform Commission has agreed the design and concept of its new Intranet development. While assisting in day to day office communications it will also have a comprehensive administrative support and research resources available to hand. See comments above at sections 21.6 and 21.7 on eCabinet and eLegislation. |  |
|  | Verification of Change Mechanisms etc. |  |  |  |  |  |
| 17 (Ref. 20.25) | The parties agree to the establishment of a mechanism to verify that all sectors, organisations and grades in the public service deliver outputs in line with the provisions of this Agreement. This mechanism will be established in accordance with Section 26. | The Office will adhere to the procedures set out in Section 26 of ‘Sustaining Progress’. Progress will be monitored by a Sub-Group of the Partnership Committee. | November, 2004 onwards. | Y | The Partnership Sub-Group met on 22 February, 2006 and on 8 March, 2006 to review this Progress Report. Progress in implementing the Action Plan was also reviewed by the Office Partnership Committee, MAC and the joint AGO/CSSO MAC. |  |
| 18 (Ref. 22.10) | Open recruitment will be introduced for appointments above existing entry levels and one-year contracts will be extended to all new recruits to the Civil Service starting on 1 January, 2004. | On receipt of the promised Department of Finance guidelines the Office will, in consultation with Partnership, implement guidelines on one-year contracts on open recruitment. |  | N/A |  | Guidelines not yet received from Department of Finance. |
| 19 (Ref. 22.11) | In order to deal with certain skills and expertise shortages the following specific measures have been agreed: (i)Beginning with IT, HR and financial management areas, open recruitment will be introduced (ii)Any need for open recruitment will be identified and communicated to the relevant union/unions with a view to reaching agreement on the matter speedily. (iii)The trade unions are committed to co-operating with such open recruitment in circumstances where there is a need for it. (iv)In the event that the parties have difficulties on such issues, a third party adjudication mechanism will be established immediately after ratification of this Agreement. This mechanism will make a final decision on any matter referred to it within a two month period. (v)There will be a review of these arrangements within 12 months to ensure that significant progress is made. | In advance of any competitions the Office will have regard to the skills and competencies identified in its skills audit. In conjunction with the CSSO the Office is recruiting a Records Management Officer. | November, 2004 onwards. End 2004 | Y Y Y | Discussions have taken place with staff representatives and agreement reached that open recruitment can take place. Any such recruitment will be in accordance with the agreed procedures. Professional Accountant recruited in conjunction with CSSO by way of PAS competition and took up duty in October, 2005. Records Management Officer has been recruited and took up duty on 1 February, 2005. |  |
| 20 (Ref. 22.11) | (vi) The Civil Service may recruit in any year a number of staff at the level of Higher Executive Officer, Assistant Principal and Principal Officer (and equivalent grades) equal to the number of staff in those grades who had resigned from the Civil Service in the previous year to take up positions in the private sector or elsewhere in the public sector. (vii) Where posts, which are normally filled by promotion, are filled under the terms of the above arrangements by open competition, they will be regarded as fulfilling the requirements to fill posts by interdepartmental competitions and will also count towards the fulfillment of quotas of posts to be filled by open recruitment at lower levels where appropriate. | The Office will continue to conduct exit interviews to capture information (where necessary) The Office will identify members resigning from the Civil Service in 2004 and 2005, at the level of HEO, AP and PO (and equivalent grades). | November, 2004 onwards. February, 2005 and 2006 | Y Y | The exit interview procedure is in place and information obtained is used to improve or enhance service. For instance the induction day and printed information given to new entrants has been revised as a result. Appropriate return made to the Department of Finance. |  |
| 21 (Ref. 22.14, and 22.15) | Discussions will take place so that greater use of competitive, merit-based promotions within Departments will be introduced and progressed over the life of the Agreement. Progress in this regard must be based on competitive selection methods used in Departments demonstrating best practice in this area. Specific measurable progress is to be made within individual Departments on a progressive basis over the life of the Agreement. | Competitive merit-based promotions apply to all grades in the Office. | November, 2004 onwards | Y | The necessary procedures for competitive merit-based promotions are in place and are being applied. The most recent internal competition for CO to SO positions used a competitive competency based system to evaluate candidates. Additionally, the upcoming EO to HEO competition will also use this method. |  |
| 22 (Ref. 22.16) | In the case of grades that are covered by the Executive Officer dual promotion structure, the following arrangements will apply: (i) Discussions will take place with a view to concluding an agreement on extending the proportion of competitive merit-based promotions within Departments by mid-2004 and their introduction at the first opportunity thereafter; (ii) Where competitive promotion systems do not apply in Departments they will be introduced and progressed over the life of the Agreement. | As above |  | Y | Competitive merit-based promotion system agreed for Executive Officers in AGO. |  |
| 23 (Ref. 22.17) | (ii) The proportion of posts filled under mobility provisions of interdepartmental promotion competitions will be increased from 33.3% to 40% from the beginning of the next competitions to be held under the existing arrangements for interdepartmental promotion schemes. This proportion will be increased to 50% from the date equating to the commencement of the next subsequent competition for promotion to Principal level. In this context, provision, will be made where feasible for a scheme of regional interdepartmental competitions outside the Dublin area to be in place as early as possible; | The Office will ensure that vacancies fillable from interdepartmental competition will be filled from that panel so as to ensure that 40% of vacancies are filled by interdepartmental panel and in due course increased to 50%. | November, 2004 onwards. | N/A |  | No relevant APO/PO vacancies have yet arisen in the Office. |
| 24 (Ref. 22.17) | In the event that problems arise in direct discussions in relation to the manner in which any of the above provisions are to be implemented, the issues involved will be processed with the aid of a facilitator, and if necessary, referred to a third party adjudication in order to assist the parties meet the objectives identified above. | The Office will if necessary through the Partnership Committee refer any issues to a facilitator or to a third party for adjudication and provide relevant information. | November, 2004 onwards. | N/A |  | The issue has not arisen. |
|  | Training |  |  |  |  |  |
| 25 (Ref. 20.20) 25 a (Ref. 22.20) | The parties are committed to continued training and development for all staff The target spend on training and development in the Civil Service will be 4% of payroll by 2003. | The Office’s Statement of Strategy 2003 – 2005 and the Law Reform Commission’s Strategy and Business Plan 2003 – 2005 place particular focus on the need for a knowledge-based organisation. The importance of ensuring that staff have access to continued training and development opportunities is emphasised. The Office has set aside 4% of payroll as a target for the training and development of all staff. The training programme is also made available to the staff of the Law Reform Commission. An Office Training and Development Strategy taking account of the Civil Service Strategy will form part of the Office’s Human Resources Strategy currently being prepared. Partnership will be consulted. The Strategy will be implemented from January, 2005. Special attention will be directed at training needs arising from decentralisation of Office staff. A breakdown of the overall expenditure on training e.g. travel and subsistence will be provided in Progress Reports. A training programme will be put in place for senior managers. | November, 2004 onwards. November, 2004 onwards. End 2004 January, 2005 January, 2005 April, 2005 onwards early 2005 | Y Y Y Y Y Y N | All staff in the Office and Law Reform Commission are notified of training opportunities. On a reciprocal basis CSSO are offered places if the Office and Commission have insufficient numbers. Priority is given to needs identified in PMDS Role Profile Forms, user training on the new ACME system and FMS. €270,000 has been made specifically available in 2006 for Training and Development. However, this figure does not take into account provision made under the Travel and Subsistence Subhead for ancillary costs. It is expected that the Office will, in total, spend 4% of its Salaries allocation, i.e. €348,000 on Training and Development in 2006. An Office Training and Development Plan for 2006 is being finalised and copies will be made available to all staff and placed on the Office Intranet where Training and Development information is displayed. The Office Legal Information Skills Programme for May – November, 2005, was substantially completed and individual training sessions have been provided December 2005 – March 2006. The HR Strategy is in place. This forms part of the Action Plan on Decentralisation. In 2005, the Office incurred expenditure of €318,545 in total on Training and Development. This figure is slightly in excess of the recommended 4% of Salaries allocation. Seminars, Conferences and Training Course Fees accounted for €153,000, Fees Refunds to staff accounted for €12,000. Expenditure related to the implementation of the new IT systems accounted for €79,000 and Travel and Subsistence accounted for €73,000. Consultation Paper on Management Development Training submitted by Partnership Sub-Group on Training and Development to MAC who are considering it prior to submission to Partnership Committee. |  |
|  | Partnership |  |  |  |  |  |
| 26 (Ref. 22.23) 27 (Ref. 20.9) | The recommendations of the Review of Partnership in the Civil Service will be considered by a Sub- Group of General Council which will present proposals for the development of partnership to General Council. The parties are committed to building upon the structures that have been established, and to further embedding and refining the process across the public service, in order to deliver real improvements in performance at organizational level, involve staff in the change and modernization process and improve the working environment. | The Office Partnership Committee is currently examining how it might be further embedded and it will take account of any agreement reached at General Council. The Committee is also considering whether to make any recommendations to the unions and management (who agreed its composition) about representation on the Committee. A Sub-Group of Partnership continues to review progress in implementation of this Action Plan. This and other Partnership Sub-Committees provide an opportunity for those who are not members of the Partnership Committee to be involved. | November, 2004 onwards. | Y Y Y Y | Partnership Committee representatives participate on the restructured MIF Project Board. Partnership Committee made a very big contribution to the adoption of the Office’s Client and Customer Charters and Client Service Guide 2005-2007, to the development of PMDS Upward Feedback criteria, the Office’s Probation Procedures, Sick Leave Procedures, Human Resources Strategy, Interview Guidelines and Health and Safety Strategy. The Partnership Sub-Group to monitor the implementation of the Action Plan met on 22 February and 8 March, 2006. This and other Sub-Groups on Training and Development Client Service, PMDS, Probation and Communications and other Office Groups provide an opportunity for staff who are not on the Partnership Committee to be involved. |  |
|  | Equality |  |  |  |  |  |
| 28 (Ref. 22.25) | The parties agree to continue to work to promote equality of opportunity for all Civil Service staff in accordance with these policies. | The Office and the Law Reform Commission will implement policies / targets on equality and diversity. The Office is aware of its obligations in relation to the employment of persons with disabilities and keeps the situation under review. The Office will progressively implement recommendations of an OPW Audit on accessibility to its premises and will continue in respect of future recruitment competitions to make specific reference to the facilities available. The Office has already achieved the Government target of 33% of AP posts filled by women. The Office will seek to ensure that the target level is maintained. The Office and the Law Reform Commission will report on the above issues in their respective Annual Reports. | November, 2004 onwards. November, 2004 onwards. November, 2004 onwards. 2004, 2005 and 2006 | Y Y Y Y Y | The Office already meets its targets with respect to gender equality and will seek to meet any targets set by the Government in relation to diversity. The Law Reform Commission is currently meeting its obligations for the employment of people with disabilities – being 1.54% above the 3% target. The Office has progressed much of the recommendations of the OPW Audit on accessibility to the premises. In November, 2004, a Loop system for persons with hearing disabilities was installed in the Reception Area, Conference and Training Rooms. Light and other fittings lowered and evacuation chairs placed on all floors of the building. People with disabilities have commented very favourably on the improvements. The Office has reviewed Guidelines from the National Disabilities Agency (NDA) in relation to obligations arising from the Disability Act 2005. So far, the Office has met all its obligations but where practicable will improve even further, particularly in the context of refurbishment works. The Office currently exceeds the Government’s target with respect to gender equality. Currently 42% of AP level staff are female and 43% of staff at or above AP level are female. The relevant information in respect of the Office has been included in the 2004 Annual Report. |  |
| 28 a (Ref. 22.27) 28 b (Ref. 20.21) | The Department of Finance is currently drawing up proposals with a view to developing action plans to ensure that the Government’s policy, of a 3% employment target for people with a disability, is implemented as effectively as possible. Particular consideration will be given to improving monitoring arrangements. The public service will continue to build on the significant progress which has been made in regard to policies on equality and diversity in order to promote equal opportunity in all aspects of civil and public service employment. | Currently the Office is 0.5% above the 3% employment target for people with disabilities. The Office will when recruiting new employees seek to meet the target by way of drawing special attention to its facilities to employ and accommodate persons with disabilities. The Public Appointments Service (PAS) has been informed and all future competitions will include reference to the facilities. The HR Strategy being prepared, in consultation with the Partnership Committee, will review issues relating to equality and diversity. The Strategy will be implemented from January, 2005. | November, 2004 onwards. End 2004 January 2005 | Y Y | The Office is currently 0.42% above the 3% target. The Office will again draw the attention of the Public Appointments Service (PAS) to the facilities in the Office when next recruiting. The competitions for Researchers for the pre-1922 legislation project as well as the recent PC and AC competitions made specific reference to the facilities for people with disabilities. The Office will regularly monitor how it can continue to meet and possibly exceed the 3% target. The HR Strategy which was underpinned by the undertaking to treat individuals with equality, dignity and respect and included an entire section on Equality was approved by the Partnership Committee on 15 March, 2005. As requested by the Public Appointments Service the Office has for all recent and will for all future competitions retain statistical information in relation to equality and diversity. |  |

{pos060306a}