|  | Commitment | Specific Action | Date | Achieved Yes – Y No – N Not applicable yet – N/A | Specific Progress New Specific Actions | If not yet achieved or did not meet commitment date please provide further details |
| --- | --- | --- | --- | --- | --- | --- |
|  | Common Commitments |  |  |  |  |  |
|  | Customer Service |  |  |  |  |  |
| 1 [20.13] 1 a [22.4] | All public service organisations over the course of this Agreement will be required to commit publicly to service standards for their customers. Performance will be evaluated against these standards and the results published in annual reports or another appropriate format. Improvements in customer service will be a particular focus of the partnership structures going forward | The Office will publish its first Customer Charter | By end November 2004 | Y | The Office Charter, along with the Charters for the AGO and OPC were placed on the Office website in March 2005. The Charters have been printed in booklet format, in Irish and English and copies were circulated to clients and customers in May, 2005. |  |
|  |  | The Office will report on performance achieved against service standards set out in Customer Charter | 2003 Annual Report will be published in early October. It is envisaged that the 2004 Annual Report will be submitted to Government in November 2005. |  |  | Annual Report for 2004 incorporating progress achieved against service standards being prepared with a view to publication by end October 2005 |
|  | All Departments and Offices will publish a charter of service standards and report on performance against these standards in their annual report. | The Office will publish a revised Customer Action Plan for the period 2005 – 2007 |  | Y | Work on revised Customer Action Plan being progressed with a view to publication by end October, 2005. | Priority given to preparation and publication of Customer Charter. |
|  |  | The Office will undertake a follow-up customer survey with a view to gauging feedback from customers in relation to the delivery of services. | Survey to commence in March, 2005 | Y | Request for Tender document is being prepared and will be issued in early October with a view to the survey being undertaken in December. | Priority given to preparation and publication of Office Charter |
|  |  | The Office will prepare a scheme to implement the provisions of the Official Languages Act | In line with direction from Minister for Community, Rural & Gaeltacht Affairs | N/A | A number of legal documents frequently used in the Office have been translated into Irish. A study on the capacity of the Office to transact business through Irish has been carried out in anticipation of the introduction of the scheme. A draft Report of the study is with MAC. | No direction received to date from the Minister for Community, Rural and Gaeltacht Affairs. |
|  |  | The Office will review training needs for service support staff | By end March 2005 | Y | Training needs have been identified on 2005 Role Profile Forms. Training in team working and customer service are ongoing. Training in communications skills, time management skills, knowledge sharing has been tendered for. Health and safety, and procurement procedures training is organised as needed. |  |
|  |  | The Office will carry out an annual safety audit of premises and will establish a Health and Safety Committee in consultation with the Partnership Committee | First audit completed by end June, 2005 and H & S Committee constituted by end February, 2005 | Y | Nifast were engaged to review the office safety statements. New Safety Statements have been drafted for both buildings occupied by the Office. A Health and Safety assessment of all workstations has been completed and the Office is considering how to implement the recommendations. | . |
|  |  | Transfer of responsibility for local State Solicitors to DPP |  | N |  | There has been good progress with Local State Solicitors negotiations. Consultants have been appointed with agreement from Dept. of Finance to undertake a study of current workload of Local State Solicitors and their expense base. Substantial progress has been made with this exercise. Consultant expected to be ready with findings by early October. Meanwhile Local State Solicitors service continue to operate well. |
|  | Efficient Use of Resources |  |  |  |  |  |
| 2 [20.11] | The parties to this Agreement will co-operate fully with the modernisation and change required to ensure that maximum value is achieved from all public expenditure in terms of defined outputs and outcomes. | The expenditure review process commenced in late 2003. An outline plan was agreed at MAC and Partnership. |  | Y | Terms of Reference for three Reviews, the Administration of the Attorney General’s Scheme, the Provision of Stenographers Services and Costs Recovery were forwarded to Department of Finance. |  |
|  |  | The Office will complete an Expenditure Review for the Attorney General’s Scheme | Completed by mid-December, 2004 | Y | Due to pressure of other work this review is only just reaching completion. A final draft has been produced by the review group and the report will be completed by end September. | Final draft of Review on AG’s Scheme being revised to take account of comments of External Reviewer. |
|  |  | The Office will complete Expenditure Reviews for the Provision of Stenographer’s Services and Costs Recovery | Completed by mid-March, 2005 | N | Project teams are in place and met on week beginning 4th April 2005 to review the draft terms of reference with a view to commencing the reviews. Substantial relevant data has been collected in respect of 2000-2003 for the Review on the provision of Stenographers Services. Both these reviews are on the next MAC Agenda. Reviews to be completed by late Spring 2006. | Delays were due to pressures associated with the introduction with the FMS. |
|  |  | A new financial management system has been implemented in conjunction with the AGO, as part of a wider implementation of MIF. The new system will facilitate both cash and accrual accounting, thereby providing enhanced financial management information. | Non-ACME dependent functionality embedded by end 2004. ACME dependent functionality embedded by end April, 2005. | Y | Non-ACME (new Case and Records Management System) dependent functionality embedded since end 2004. | However, due to the rescheduling of the ACME project it is envisaged that the ACME dependent functionality will be fully embedded by October, 2005 |
|  |  | Development of interface with new Case and Records Management System (ACME) to meet wider MIF requirements | Interface to be developed and in place by end November, 2004 | Y | Interface continues to be developed. Testing of interface is taking place in the context of the pilot of the new ACME system. |  |
|  |  | The Office will, in line with Government Decision of 11 February, 2003, continue to report on progress on implementation of MIF. | Every two months | Y | Progress reports submitted to MIF Central Unit, Department of Finance, as appropriate. |  |
|  |  | A new Case and Records Management System will enhance the quantity and quality of management information and facilitate the introduction of a comprehensive costing package in line with MIF requirements. | Case and Records Management System to be piloted by mid December 2004 and fully rolled out by end April, 2005. Costing facilities to be developed and functional by end June, 2005 | Y | The piloting of the new Case and Records Management System (ACME) commenced on 11 April, 2005, Development of other areas is ongoing. A roll out plan is currently under consideration. |  |
|  |  | The Office will provide MIF Training for MAC and Section Heads | Training commenced in October, 2004 and to be completed by end February, 2005 | Y | All members of MAC and some section heads have received training. Training is now scheduled for others with the next session scheduled for early October, 2005. |  |
|  |  | The Office will develop, in conjunction with the AGO, appropriate Performance Indicators with the setting up of a Sub-Group of the MIF Working Group | Group convened and PIs to be developed in line with central deadlines | Y | Following a tendering competition the CSSO and the AGO engaged consultants on 11 March, 2005 to identify performance indicators by July, 2005 taking account of the performance indicators included in the Statement of Strategy and Business Plans. The Performance Indicators developed. are now being refined. They will be considered further in the context of preparation of the Office’s Statement of Strategy 2006 – 2008 currently being prepared for submission to the Attorney General by 6 December, 2005. |  |
|  |  | The Office is implementing a Plan arising from the Report on the Accountability of Secretaries General and Accounting Officers. This has included a review of internal financial procedures in the Office, an enhanced internal audit function, installation of a Financial Management System, initiation of implementation of MIF and identification of potential risks. | January, 2005 | Y | The Office has addressed all of the recommendations arising from the Mullarkey Report. The Review on internal procedures in the Office was concluded and recommendations approved by the Audit Committee are being progressed. The asset tracker software was installed in the FMS in January, 2005 and a workshop for users was held on 15 February, 2005. Testing of the migration of fixed asset data into the new system has commenced. Internal financial procedures have been revised following the introduction of the FMS. |  |
|  |  | Business Plans are being revised to take account of the Department of Finance Guidelines on Risk Management and appropriate RM systems will be put in place. | Business Plans revised by end January, 2005 | Y | Joint CSSO/AGO risk management exercise undertaken and risk register being prepared for submission to MAC by end September 2005. |  |
|  |  | Promote payment by EFT as part of development of new FMS | Facility fully implemented for clients by end 2004 | N |  | The facility has been developed and is currently undergoing testing and is hoped to to go fully live in October, 2005. |
|  |  | Payment of Counsels’ Fees: A Group has been established to write guidelines on the levels of fees to be sanctioned in personal injury and torts. |  | Y | Guidelines are in place |  |
|  | Better Regulation |  |  |  |  |  |
| 3 [20.16] 4 [20.17] | The Government is committed to publishing a National Policy Statement on Better Regulation in 2003. A model of Regulatory Impact Analysis (RIA) will be introduced on a pilot basis in a number of Government Departments during 2003. In the light of the pilot phase, a model of RIA appropriate to the Irish context will be introduced. | The Office is not directly involved in this initiative. However the Office will continue to support the Attorney General in this matter, specifically by continuing to designate an Assistant Chief State Solicitor with responsibility to liaise between the Office of the Chief State Solicitor and the Office of the Attorney General. In addition, the Office will have an input into the consultative process being undertaken by the Law Reform Commission in relation to the modernisation of Irish Land and Conveyancing Law. Also, the Office will continue to participate in the Department of Justice, Equality & Law Reform’s committee to review the area of litigation costs. | From November, 2004 onwards | Y | The resources of the Office continue to remain available to support the work of the Attorney General. The Office is participating in the review of litigation costs sponsored by the Department of Justice, Equality and Law Reform and has provided a Principal Solicitor for this purpose. |  |
| 5 [20.18] | Well-drafted, easily understood and accessible regulation can reduce the difficulties and costs of compliance for both businesses and citizens. Building on progress in recent years and utilising the provisions of the Statute Law (Restatement) Act, a structured programme targeted on areas where the benefits to business and the citizen are likely to be greatest will be pursued to achieve these improvements in regulations. | See above |  | Y |  |  |
|  | Stable Industrial Relations |  |  |  |  |  |
| 6 [19.3, 19.6 and 20.5] | The parties are committed to maintaining a well-managed industrial relations environment to minimise disputes affecting the level of service to the public In this regard the agreement provides that: (i)No cost increasing claims for improvements in pay or conditions of employment will be made or processed during the course of the Agreement. (ii)Precludes strikes or other forms of industrial action on any matter covered by the Agreement. | The Partnership approach will continue to be used to foster good industrial relations. Regular meetings are held with local union branch representatives. | From November, 2004 onwards | Y | The Partnership approach continues to work successfully in the CSSO. Unions have been regularly consulted and briefed on matters of mutual interest in the period under review. Accommodation issues have been problematic for the Office. Interim Accommodation issues are being resolved through the use of full consultation with the Unions and non-Union staff. The Office has put in place a communications structure for non-Union staff and other Groups. |  |
|  | Performance Management Systems |  |  |  |  |  |
| 7 [20.7] | Where these are not already in place, the parties agree that appropriate performance management systems will be introduced so that developed performance management systems will be fully operating in each sector of the public service by 1st January, 2005 | The PMDS has been in place for all staff since November 2001. A review of the system was undertaken in 2003 following which recommendations for development and amendment have been implemented. Each year the Office will choose appropriate core competencies and implement plans for their development. | From November, 2004 onwards | Y | The Office has agreed the following core competencies for 2006: Effective Knowledge Management/Knowledge Sharing Managing and Developing People Communications Customer Service In addition arrangements are in place to include the integration of probation and increments into the 2006 scheme on a trial basis. |  |
|  |  | Following the devolution of training budgets to Division Heads monthly reports on training expenditure are provided by the Training Officer. The Office will consider the implementation of a Personal Development and a Management Programme for all staff. | Programme to be fully implemented by end 2005 | Y Y | Division Heads in the Office were been advised in February, 2005 as regards their training budget allocation for 2005. 18 Tenders have been received and evaluation is ongoing. A contract will be awarded for the roll out of a Personal Development and a Management Programme by October. |  |
|  |  | The Office will continue to develop a more structured approach to the monitoring, assessment and development of staff during probation. | From November, 2004 onwards | Y | The PMDS is utilised in this regard. Probation procedures are in place. Section Heads in consultation with Division Heads review the work of new entrants on an ongoing basis and Division Heads formally meet new entrants 3 months after assignment to discuss work issues (over and above on-going reviews under PMDS with Section Heads). See progress achieved under paras 25 [20.20] and 25a [22.20] |  |
|  | Modernisation and Flexibility |  |  |  |  |  |
| 8 [20.6] | The parties are committed to increased flexibility to ensure that public services are delivered in a manner which more closely reflects the needs of its customers. | Flexibility continues to be a feature of the Office, with regular re-organisation of staff, responsibilities and sections in response to changing demands from clients. The Office continues to review the organisational arrangements to align them with client needs. The Office will continue to achieve flexibility in the recruitment of staff in emerging skills areas such as records management and accounting technicians. |  | Y | Significant flexibility continues to be demonstrated in areas such as the implementation of IT projects in the Office. The Office has made new organisational arrangements to manage client needs arising out of child abuse litigation. Resources in the Asylum section have been strengthened. The Office has created a fully staffed Records and Registry Section. Also, a significant number of staff from this Office were involved in data migration, reviewing the fileplan, workflows, screen shots and writing user acceptance testing scripts for the ACME Project. Records Management Officer recruited by January 2005. The Office, in conjunction with the AGO recruited a Records Manager (without impact on overall staffing numbers) in February, 2005 in the context of the implementation of the new Case and Records Management System. |  |
|  |  | In the context of the effects that decentralisation will have on staffing in the administrative side of the Office, existing staff will document practices, procedures and precedents and training will be given to other staff to enable them to effect the duties involved |  | Y | The Office will be remaining in Dublin. However, staff members interested in decentralising have been identified. An evaluation of the risk based on those likely to transfer to ‘Early Mover’ Departments/Offices has been made. The impact of decentralisation on the delivery of the services of the Office will be predominantly on the administrative side and the impact on professional and technical staff will be minor. The documentation of practices and procedures is taking place particularly in the context of the File and Document Plan for the ACME project and supported by the appointment of a Know-how Officer. |  |
|  |  | The Office continues to consider the possibility of outsourcing specific legal functions which hitherto are carried out in the Office. Any such examination will be based on a broad cost benefit analysis basis. | From November, 2004 onwards | Y | The panel of external Solicitors created in 2004 continues to be used under the guidance of the Office to provide key services to Departments. A discussion on the outsourcing of an existing area of work is under discussion at Partnership. |  |
|  | Team working and cross-functional working |  |  |  |  |  |
| 9 [21.5] | All of the parties will co-operate fully with initiatives in these areas and it remains open to management to implement such initiatives in accordance with the provisions of this Agreement | The specifications for management and personal development training for the Office will contain specific requirements for the development of team building and team working skills. The specifications will be linked to the initiatives already taken by the Office to screen solicitor/legal executive applicants at recruitment interview stage for team player/leader competencies and at promotional interview stages where standards for team competencies are stated and explored with candidates. Team competencies will be hardwired into the new promotional procedures for clerical and administrative staff following on from the extension of the merit based competitive selection to those grades. | From November, 2004 onwards | Y | Specifications for this component of training are in place. The Office provided a pilot training session for 24 staff in team working in February, 2005. The feedback from staff in relation to this course was very positive and it is proposed that further training sessions will be provided for staff. Team Working competency has been specified for competition for Clerical/Administration staff. Interviews have taken place utilising the team working competency as part of its assessment. | It is proposed that this training will be incorporated by the company who are successful in the tender process for Training for Senior Management & Staff. |
|  |  | The Office is committed to the continuation of Team working to deal with specific legal work for some clients and cross-functional working initiatives such as the introduction of new IT systems and policies. The Office will continue to promote the use of project management. In line with the Office’s new Knowledge Management Strategy, group meetings in the Office will continue to be developed to promote a culture of sharing knowledge and resources. These include the establishment of Legal Issues meetings, information sharing meetings for Executive and Staff Officers, the further development of section/team/Division meetings, and the promotion of communities of practice. This will continue to promote a team-working initiative and will assist in improving flexibility and mobility of staff by providing a forum for education of wider Office issues. Further development of the team concept will be kept under review. Teamwork has been specified as an element of a required competence for PMDS purposes. |  | Y | Legal Bulletins prepared jointly with the AGO are prepared and circulated on a monthly basis. Legal issues meetings, Section/Team/Division meetings and other information sharing meetings are held regularly in the Office. Also see progress achieved under para 9 [21.5] |  |
|  |  | The Office’s new Human Resources Strategy to be agreed by Partnership will in the future focus on leveraging the best advantage from the Offices mobility policy. | Mid 2005 | N/A | Elements of the Human Resources Strategy have already been developed such as PMDS, Training policies, Refund of Fees, Probation and awards of increments, staff mobility, competitive promotional procedures and atypical working arrangements. Policies have been developed by the Human Resources Sub-Group of Partnership. |  |
|  | New Technology and eGovernment |  |  |  |  |  |
| 10 [21.6 and 21.7] | It is accepted that the use of new technology may necessitate significant change in work processes in order that the benefits of technology will be maximised. There will be full co-operation with the design and implementation of eGovernment projects. | Considerable progress has been made in implementing an IT Strategy for the period 2001- 2005. The main project is a case and records management system shared between this Office and the Office and the Office of the Attorney General. | Commence implementation of Case and Records Management System (ACME) in December 2004 on a pilot basis. System to be fully implemented by end April, 2005. | Y N | Substantial work has been done on the development of the ACME system. The ACME pilot commenced on 11th April, 2005. Technical and functional issues that arose during the pilot continue to be addressed. Specifications have been agreed in respect of all areas, workflows have been reviewed between both Offices with a view to streamlining the progress of State Litigation, ensuring that reminder notifications to keep track of both internal and external correspondence are provided for, and Records Management Policies have been developed. These continue to be reviewed with a view to system and pre-UAT testing at end September, 2005. Phase 1 UAT of the roll out of the system is scheduled to commence early October, 2005. Testing of the management information reporting functionality has commenced. Specific Training for those involved in the pilot took place in early to mid-April 2005, and a programme of refresher training is being put in place. All staff will be trained on the new system before it is rolled out. |  |
|  |  | A new Financial Management System shared with the Attorney General’s Office has been implemented. | Non-ACME dependent functionality embedded by end 2004. ACME dependent functionality embedded by end April, 2005. | Y | Non-ACME dependent functionality is operational. Testing of ACME dependent functionality is almost complete. Will be fully embedded by November 2005. |  |
|  |  | The development of an interface between the new Case and Records Management System and the Financial Management System will enhance the quantity and quality of management information and facilitate the introduction of a comprehensive costing package thus ensuring that the Office meets its MIF requirements. | Enhanced Management Information reporting and costing in place by mid 2005 | Y | Interface has been developed since end January, 2005. Testing of interface is taking place in the context of the pilot of the new ACME system which commenced on 11th April, 2005. MIF is being rolled-out. |  |
|  |  | Work on the development of a new HR Management system in conjunction with the Attorney General’s Office has commenced but progress was hindered due to delays and developments at central level. | System to be Implemented by mid 2006 | N/A |  | Following a consultant’s evaluation CMOD substantially revised the roll-out of a Civil Service HRMS. Although this has resulted in delays generally it is anticipated that the Office will still meet its previously advised target of September, 2006. |
|  |  | Also, the Office in conjunction with the Attorney General’s Office has prepared a Knowledge Management Strategy 2003 – 2005. The implementation of this strategy will be supported by the development and installation of a specialist legal Know-how application which will facilitate both Offices in the capture, organisation and sharing of knowledge, experience and expertise. | Implement Legal Know-how Application from End 2005. | Y | Interim proposals for the development of a Know-how database for the CSSO have been presented to MAC for consideration. Risk Management issues have been raised and are currently under investigation. The Library and Know-how Unit has hosted four Legal Issues Meetings as part of its Know-how strategy. |  |
|  |  | The Office will ensure full compliance with the changeover from Lotus Notes to Microsoft Outlook and training as to Microsoft Outlook and full co-operation with IT training to ensure levels of IT proficiency | Training to be completed by end 2004. | Y | Training for all staff in MS Outlook has been provided |  |
|  |  | The Office is currently developing an intranet which will be shared with the Attorney General’s Office and will enhance the sharing of information between both Offices. | Intranet to be developed by mid 2005 | N/A | The Intranet infrastructure has been put in place. A group is currently developing content to load on the system. |  |
|  |  | The Office will continue to co-operate with the Courts Service in the development of its IT strategy. A member of the Office’s IT Unit and a legal staff member continue to participate on a group working on the computerisation of the Supreme Court. | From November, 2004 onwards | Y | While the Supreme Court Working Group on the computerisation is in abeyance pending further developments, the Office continues to provide 3 officers who have responsibility for co-operation with the Courts Service. Developments in the Courts Service are reported to MAC on a quarterly basis. The Office participated in a recent demonstration by the Courts Service on the software for the filing and serving of documents in court. The demonstration was sponsored by the Judges’ library. The Office participated in the Courts Service Customer Forum representing the State in litigation. |  |
|  |  | The Office’s web page (joint site with the AGO) continues to be updated and improved. The web page provides high standards of accessibility for the public and in particular people with disabilities. | Web site to be fully redeveloped by end 2004 | Y | The Office’s redesigned website has been displayed since 16 February, 2005 has been fully constructed and is up and running. The preparation of specifications for translating text into Irish has commenced in the context of displaying an Irish version of the website. The site has been designed to meet state and international requirements for Public Service accessibility. The site has been tested for accessibility by IQ Content and the National Council for the Blind of Ireland and has been declared to have a AA+ standard of accessibility compliance. |  |
|  | Atypical Working Arrangements |  |  |  |  |  |
| 11 [21.8] | The work pattern may be such in specific areas that specific work processes can be performed most effectively by part time staff. | Atypical working patterns apply to 29 staff in the Office which equates to 12.4% of the staff complement. | From November, 2004 onwards | Y | The Office continues to accommodate staff requests in this area as appropriate. |  |
|  |  | The use of part-time staff continues to be kept under review. | From November, 2004 onwards | Y | The Office continues to keep the use of part-time staff under review |  |
|  |  | A sub-committee of Partnership has produced a report on e-Working. The report findings will be reviewed following upon an assessment of the ability of the ACME and FMS systems to support e-Working. | From January, 2005 onwards | Y |  | The further consideration of both e-Working and the use of satellite working offices has been deferred pending the completion of the ACME project. The Sub-Committee is broadly in favour of the use of satellite offices. The flexibility of such offices needs to be tested in light of the operation of new technology. |
| 12 [21.9] | Situations may arise where the need to respond to temporary pressures may require the employment of temporary staff or outsourcing of work. Unions will be notified in advance of initiatives of this kind. | Unions have been consulted and have agreed to the use of contract staff to fill vacancies on a short term basis. A Professional Accountant was engaged on a two year initial contract in March 2003 to facilitate the implementation of the new Financial Management System and the MIF initiative and the Office will shortly recruit a Records Management Officer in the context of the implementation of the new ACME system. The Office will continue to recruit contract staff subject to numbers control so as to meet any increasing and urgent work demands. | From November, 2004 onwards Records Management Officer recruited by end 2004 | Y | This process continues in the Office. Records Manager recruited in February, 2005. |  |
|  |  | The Office recognises the need to find alternative approaches in dealing with major cases that cannot be handled within its resources and is developing different models for outsourcing work. | From November, 2004 onwards | Y | The Office continues to support the management of the outsourcing of legal work to OPW. | This process continues in the Office. |
|  | Attendance Patterns |  |  |  |  |  |
| 13 [21.10] | In order to provide a satisfactory level of service to the public, there is a need in certain areas for changes to the standard working day in order to provide services outside the traditional “9 to 5” pattern. The parties are committed to discussions to establish how this can best be achieved, where required. | The Office will continue to provide an out-of-normal hours service and will maintain the capability to respond to client service requirements outside of normal working hours. | From November, 2004 onwards | Y | The Office continues to monitor the on-call panel and the panel’s effectiveness. |  |
|  |  | The working trial of variable starting and finishing times for technical staff has been completed and will be evaluated and any lessons learnt may be applied to professional staff. | Working trial has been completed and will be evaluated by end 2004 | Y | MAC has agreed to make variable starting and finishing times on an extended pilot basis available to technical i.e. legal executive staff. This follows from evaluation of a short pilot which took place in early 2005. Standard flexi time arrangements apply for all Clerical/Administrative staff. |  |
|  | Redeployment of Staff |  |  |  |  |  |
| 14 [21.11] | Redeployment of staff may be necessary on occasion to respond to urgent work demands. | Redeployment of staff to meet changing demands for legal services continues to be a feature of Office administration. | Ongoing review of internal organisation | Y |  | See progress achieved under para 8 [20.6] |
|  | Management of the Introduction of Change and New Development |  |  |  |  |  |
| 15 [21.12] | In accordance with the partnership approach, unions will be informed in advance of all new significant workplace-related initiatives, the reasons for them and the proposed implementation date. Notification will be given in advance and in sufficient time to allow discussions with the union(s) concerned to take place. Such discussions will cover the nature of the changes involved, the reasons for them and any impact on staff. Subject to this, it is accepted that management have the right to implement changes in accordance with the provisions of the Agreement. | Unions will continue to be consulted in relation to workplace initiatives. The Partnership process provides a regular forum for discussion of any proposals in this area. There is regular and ongoing consultation with Partnership so as to improve the quality and implement ability of decisions. Additionally, the Partnership Committee has a communications subgroup that has recommended a communications strategy. This has been implemented. | From November, 2004 onwards | Y | This process continues to work successfully. |  |
|  | eGovernment |  |  |  |  |  |
| 16 [20.19] | The parties are committed to the further development of eGovernment on the following basis: (i) facilitating better citizen access and interaction with the public service by realising the potential of information and communication technologies (ICTs);  (ii) building collaborative knowledge-based structures focused on serving both citizens and the public service; and  (iii) facilitating continuous adaptation and improvement in service delivery by fully utilising ICTs to deliver public services seamlessly and across traditional boundaries. | Covered in the paragraphs relating to new technology See para 21.6 and 21.7. |  |  |  |  |
|  |  | The feasibility of an extranet facility between the Office and client Departments/Offices will be considered following the implementation of the new case and records management system. | To be implemented by end 2005 subject to decision to proceed. | Y |  | Client interest in an extranet facility is proving to be less than expected. The matter would more rationally be developed in the context of further developments on the e-Government initiative. Feasibility of an extranet facility will be considered towards the end of 2005 following the expected embedding of the ACME system. |
| 16 a [22.24] | The parties commit to full co-operation with the further development and implementation of eGovernment policy as outlined in ‘New Connections’, the Government’s Action Plan to realise the potential of the Information Society. | The Office will continue to co-operate with the Courts Service in the development of electronic court facilities. See para 21.6 and 21.7 | From November, 2004 onwards | Y | Please see progress achieved under paragraph 10 [21.6 and 21.7] |  |
|  | Verification of Change Mechanisms etc. |  |  |  |  |  |
| 17 [20.25] | The parties agree to the establishment of a mechanism to verify that all sectors, organisations and grades in the public service deliver outputs in line with the provisions of this Agreement. This mechanism will be established in accordance with Section 26. | The Office will adhere to any procedures put in place in accordance with Section 26. | November, 2004 onwards | Y | The Partnership Committee met on 15th September 2005, to review this Progress Report. Progress in implementing the Action Plan was also reviewed by MAC. |  |
| 18 [22.10] | Open recruitment will be introduced for appointments above existing entry levels and one-year contracts will be extended to all new recruits to the Civil Service starting on 1 January, 2004. | The Office will implement guidelines on one-year contracts for new recruits in consultation with Partnership. | Awaiting issue of guidelines from Department of Finance | N/A |  | Guidelines not yet received from the Department of Finance. |
| 19 [22.11] 20 [22.11] | In order to deal with certain skills and expertise shortages the following specific measures have been agreed: (i)Beginning with IT, HR and financial management areas, open recruitment will be introduced (ii)Any need for open recruitment will be identified and communicated to the relevant union/unions with a view to reaching agreement on the matter speedily. (iii)The trade unions are committed to co-operating with such open recruitment in circumstances where there is a need for it. (iv)In the event that the parties have difficulties on such issues, a third party adjudication mechanism will be established immediately after ratification of this Agreement. This mechanism will make a final decision on any matter referred to it within a two month period. (v)There will be a review of these arrangements within 12 months to ensure that significant progress is made. (vi) The Civil Service may recruit in any year a number of staff at the level of Higher Executive Officer, Assistant Principal and Principal Officer (and equivalent grades) equal to the number of staff in those grades who had resigned from the Civil Service in the previous year to take up positions in the private sector or elsewhere in the public sector. (vii) Where posts, which are normally filled by promotion, are filled under the terms of the above arrangements by open competition, they will be regarded as fulfilling the requirements to fill posts by interdepartmental competitions and will also count towards the fulfillment of quotas of posts to be filled by open recruitment at lower levels where appropriate. | The Office will continue to assess the skills requirements in the IT, HR and financial management areas. | From November, 2004 onwards | Y | This process is ongoing in the Office. The experience of the Office is that we are retaining staff in I.T., H.R., and Accounts and that skills continue to develop, particularly in I.T. and H.R. In the last 2 years no staff at EO level or above have left the I.T., HR or accounts areas. |  |
|  |  | The Office has appointed a Professional Accountant (on a shared basis with the Attorney General’s Office) on a two year contract. A HR manager was recruited by confined interdepartmental competition. |  | Y | The contract of the Professional Accountant was extended for a further six months to allow for the appointment to the post on a permanent basis. The Public Service Appointments organised a competition on behalf of the Offices and an appointment is expected to be made shortly. |  |
|  |  | The Office, in conjunction with the Attorney General’s Office has advertised for the position of Records Management Officer in the context of the implementation of the new Case and Records Management System. | Records Management Officer to be recruited by end 2004. | Y | Records Manager recruited in February, 2005. |  |
|  |  | The Office will Identify numbers who resigned from Civil Service in the course of 2004, at the level of HEO, AP, and PO (and equivalent grades) | By end February, 2005 | Y | Appropriate return made to Department of Finance. |  |
|  |  | The Office will continue to conduct exit interviews for staff. | From November, 2004 onwards | Y | The exit interview procedure is in place. |  |
| 21 [22.14, and 22.15] | Discussions will take place so that greater use of competitive, merit-based promotions within Departments will be introduced and progressed over the life of the Agreement. Progress in this regard must be based on competitive selection methods used in Departments demonstrating best practice in this area. Specific measurable progress is to be made within individual Departments on a progressive basis over the life of the Agreement. | As part of an agreement with IMPACT in 2001, competitive promotion was introduced for all professional and technical promotions. Existing arrangements for internal promotions for general service grades have been reviewed in consultation with the Staff Side. |  | Y | This process is ongoing in the Office. |  |
|  |  | The objective of the Office in regard to competitive merit-based promotions has been achieved. | September 2004 | Y |  |  |
| 22 [22.16] | In the case of grades that are covered by the Executive Officer dual promotion structure, the following arrangements will apply: (i) Discussions will take place with a view to concluding an agreement on extending the proportion of competitive merit-based promotions within Departments by mid-2004 and their introduction at the first opportunity thereafter; (ii) Where competitive promotion systems do not apply in Departments they will be introduced and progressed over the life of the Agreement. | 50% of promotion to EO already on a competitive basis. In addition, 100% of promotions from SO to EO and 50% of promotions from CO to SO has been agreed between Management and Unions | October, 2004 | Y | Mechanisms are in place and arrangements agreed. 1 promotion to SO has been made following an internal competition. |  |
| 23 [22.17] | (ii) The proportion of posts filled under mobility provisions of interdepartmental promotion competitions will be increased from 33.3% to 40% from the beginning of the next competitions to be held under the existing arrangements for interdepartmental promotion schemes. This proportion will be increased to 50% from the date equating to the commencement of the next subsequent competition for promotion to Principal level. In this context, provision, will be made where feasible for a scheme of regional interdepartmental competitions outside the Dublin area to be in place as early as possible; | The Office will ensure that 40% of vacancies, in grades covered by existing arrangements for interdepartmental promotion schemes, are filled from interdepartmental panels. | Ongoing since mid-2003 | Y | New panel arrangements will be implemented as vacancies are to be filled. |  |
| 24 [22.17] | In the event that problems arise in direct discussions in relation to the manner in which any of the above provisions are to be implemented, the issues involved will be processed with the aid of a facilitator, and if necessary, referred to a third party adjudication in order to assist the parties meet the objectives identified above. | The Office will, if necessary, in implementing the above provisions avail of a facilitator or third party adjudication. | From November, 2004 onwards | N/A |  |  |
|  | Training |  |  |  |  |  |
| 25 [20.20] 25 a [22.20] | The parties are committed to continued training and development for all staff The target spend on training and development in the Civil Service will be 4% of payroll by 2003. | In the Office’s strategy statement particular focus is placed on the need for a “knowledge-based” organisation. The importance of ensuring that staff has access to continuing training and development opportunities is emphasised. A specialist training officer was appointed in 2002. Training expenditure in 2003 was 2.8% of payroll. A training needs analysis has been completed and will form the basis for a detailed training and development plan. The plan will also take into account recommendations pertaining to training contained in the Knowledge Management Strategy 2003-2005. The Office is committed to the preparation of a Training and Development Strategy | From November, 2004 onwards Provision and development of training is ongoing. To be finalised by March, 2005 | Y Y Y Y | All staff in the Office are notified of training opportunities. Priority is given to needs identified in PMDS Role Profile Forms. 3 % of payroll has been made available in 2005 for training and development in the Office. An Office Training and Development Plan for 2005 has been prepared and copies will be circulated to all staff. An Office Legal Information Skills Programme for 2005/2006 is currently being prepared A Judicial Review practice and procedure manual has been prepared and has been published (January 2005) with a view to equipping a professional and technical with comprehensive material to support their training, development, competency and skills in dealing with applications for judicial review. | The Office relies heavily on the training modules provided by the Continuing professional and Development Service of the Law Society. The training events on offer are highly relevant to the needs of legal staff. In addition the Office has agreed to work with the DSBA to obtain additional legal training for solicitors and technical staff. ECHR training is ongoing in the Office. |
|  | Partnership |  |  |  |  |  |
| 26 [22.23] | The recommendations of the Review of Partnership in the Civil Service will be considered by a Sub- Group of General Council which will present proposals for the development of partnership to General Council. | The partnership process is reviewed annually at a one day seminar, the last in December 2003. The next annual review will take place in December, 2004. Part of that review will be discussion on the implications of the provisions of the Information and Consultation Directive. | December, 2004 | Y | Annual Review of Partnership took place in December, 2004. |  |
| 27 [20.9] | The parties are committed to building upon the structures that have been established, and to further embedding and refining the process across the public service, in order to deliver real improvements in performance at organizational level, involve staff in the change and modernization process and improve the working environment. | The Partnership Committee meets monthly and a wide range of topics come up for discussion and decision. | From November, 2004 onwards | Y | The Partnership Committee continues to meet each month. |  |
|  |  | A Human Resources Strategy will be drafted and implemented. | Implemented by June, 2005 | Y | See progress achieved under paragraph 9 [21.5] |  |
|  | Equality |  |  |  |  |  |
| 28 [22.25] | The parties agree to continue to work to promote equality of opportunity for all Civil Service staff in accordance with these policies | The Office will promote existing Diversity and Gender Equality Policies | From November, 2004 onwards | Y | The Office meets its targets with respect to gender equality and has now reached its target of 3% for disability. |  |
|  |  | The Office has already achieved the Government target of 33% of AP posts filled by women - 49% of AP level posts in the Office are filled by women. |  | Y |  |  |
| 28 a [22.27] | The Department of Finance is currently drawing up proposals with a view to developing action plans to ensure that the Government’s policy, of a 3% employment target for people with a disability, is implemented as effectively as possible. Particular consideration will be given to improving monitoring arrangements. | The Office’s commitment to the principles of equality is set out in the Customer Action Plan. In the course of refurbishing our main Office building, facilities for wheelchair users were installed. |  | Y |  |  |
| 28 b [20.21] | The public service will continue to build on the significant progress which has been made in regard to policies on equality and diversity in order to promote equal opportunity in all aspects of civil and public service employment. | Training on equality issues will be provided for all staff | June 2005 | N/A |  |  |
|  |  | The Office exceeds the gender balance targets already set by the Civil Service. Currently 49% of AP level and 54% of PO level posts are filled by women. The situation will be kept under review. | From November, 2004 onwards | Y | The target continues to be met. |  |
|  |  | All applications for internal competitions are monitored for gender split, age etc. | From November, 2004 onwards | Y | All data is preserved for analysis. |  |
|  |  | Report on these issues in annual report. | Include in annual report for 2003 | Y | The relevant information is submitted to the Annual Report Editorial Board to be included in the Annual Report which are, in turn, published on the Office’s web-site. |  |
|  |  | Apply Civil Service policy on harassment, sexual harassment and bullying. | From November, 2004 onwards | Y | Ongoing |  |
|  |  | Provide awareness training for all staff and ensure particularly that all managers are fully informed on principles and best practice. |  | Y | MAC members have attended workshops in Diversity & Equality. Trainer has been selected to deliver training to all staff. |  |