|  | Commitment | Specific Action | Date | Achieved Yes – Y No - N | If not yet achieved or did not meet commitment date please provide further details |
| --- | --- | --- | --- | --- | --- |
|  | Common Commitments |  |  |  |  |
|  | Customer Service |  |  |  |  |
| 1 [20.13] 1 a [22.4] | All public service organisations over the course of this Agreement will be required to commit publicly to service standards for their customers. Performance will be evaluated against these standards and the results published in annual reports or another appropriate format. Improvements in customer service will be a particular focus of the partnership structures going forward. All Departments and Offices will publish a charter of service standards and report on performance against these standards in their annual report. | A Customer Action Plan was issued in mid-2002. That plan sets down objectives for service standards to client Departments/Offices in areas such as meetings and liaison with clients, documentation, response times, consistency of advice, skills development, equality, web site development and Court hearings. Action to achieve the planned standards is ongoing particularly in the areas of IT developments, staff recruitment, training and knowledge management. Report performance against standards set in Customer Action Plan | New Case and Records Management System to be in place by mid- 2004 Assignment of certain staff to new specialist tasks by October, 2003. Report on progress will be included in Annual Report for 2003 |  |  |
|  | Efficient Use of Resources |  |  |  |  |
| 2 [20.11] | The parties to this Agreement will co-operate fully with the modernisation and change required to ensure that maximum value is achieved from all public expenditure in terms of defined outputs and outcomes. | The expenditure review process will commence late 2003. An outline plan has been agreed at MAC and Partnership. A new financial management system will be developed, in conjunction with the AGO, as part of a wider implementation of a MIF The Office will, in line with Government Decision of 11 February, 2003, report on progress on implementation of MIF. A new Case and Records Management System (tenders currently being assessed) will enhance the quantity and quality of management information and facilitate the introduction of a comprehensive costing package in line with MIF requirements. The Office is preparing an Implementation Plan arising from the Report on the Accountability of Secretaries General and Accounting Officers. Promote payment by EFT as part of development of new FMS The Office has approved a Knowledge Management Strategy 2003-2005 in conjunction with the AGO. | Commence one review by end 2003 Implement by September 2004 Every two months Case and Records Management System to be in place by mid-2004. Costing facilities to be developed late 2004 and 2005 Ongoing from September 2004 Ongoing |  |  |
|  | Better Regulation |  |  |  |  |
| 3 [20.16] 4 [20.17] | The Government is committed to publishing a National Policy Statement on Better Regulation in 2003. A model of Regulatory Impact Analysis (RIA) will be introduced on a pilot basis in a number of Government Departments during 2003. In the light of the pilot phase, a model of RIA appropriate to the Irish context will be introduced. | These provisions are not relevant to CSSO |  |  |  |
| 5 [20.18] | Well-drafted, easily understood and accessible regulation can reduce the difficulties and costs of compliance for both businesses and citizens. Building on progress in recent years and utilising the provisions of the Statute Law (Restatement) Act, a structured programme targeted on areas where the benefits to business and the citizen are likely to be greatest will be pursued to achieve these improvements in regulations. | This provision is not relevant to CSSO |  |  |  |
|  | Stable Industrial Relations |  |  |  |  |
| 6 [19.3, 19.6 and 20.5] | The parties are committed to maintaining a well-managed industrial relations environment to minimise disputes affecting the level of service to the public In this regard the agreement provides that: (i)No cost increasing claims for improvements in pay or conditions of employment will be made or processed during the course of the Agreement. (ii)Precludes strikes or other forms of industrial action on any matter covered by the Agreement. | The Partnership approach is used to foster good industrial relations. Regular meetings are held with local union branch representatives. Any staff side proposals to be considered in the context of the commitment to have no cost increasing claims. | Ongoing Ongoing |  |  |
|  | Management Systems |  |  |  |  |
| 7 [20.7] | Where these are not already in place, the parties agree that appropriate performance management systems will be introduced so that developed performance management systems will be fully operating in each sector of the public service by 1st January, 2005 | The PMDS has been in place for all staff since November 2001. A review of the system is being undertaken following which proposals for development and amendment will be formulated. Each year the Office will chose appropriate core competencies and implement plans for their development. Information about expenditure on training identified throught PMDS will be provided Plans to roll-out upward feedback are under discussion at a sub-committee of Partnership. Continue development of more structured approach to the monitoring, assessment and development of staff during probation. | Review to be completed by November 2003 Ongoing Include in progress reports Agree a timetable for introduction of upward feedback by November 2003. Ongoing |  |  |
|  | Modernisation and Flexibility |  |  |  |  |
| 8 [20.6] | The parties are committed to increased flexibility to ensure that public services are delivered in a manner which more closely reflects the needs of its customers. In accordance with this: | Flexibility is already a feature of the Office, with regular re-organisation of staff, responsibilities and sections in response to changing demands. The Office will review the organisational arrangements to align them with client needs. Achieve flexibility in the recruitment of staff in emerging skills areas such as records management and accounting technicians, within existing authorised numbers. | Ongoing End 2003 March 2004 |  |  |
|  | Team working and cross-functional working |  |  |  |  |
| 9 [21.5] | All of the parties will co-operate fully with initiatives in these areas and it remains open to management to implement such initiatives in accordance with the provisions of this Agreement. | Where practical, work teams have been established to deal with specific legal work for some clients. Further development of the team concept will be kept under review. Teamwork has been specified as a required competence for PMDS purposes. Initiatives outlined in the Knowledge Management Strategy 2003-2005 which promote team working and knowledge sharing across different office functions will be implemented. These include the establishment of Legal Issues meetings, information sharing meetings for Executive and Staff Officers, the further development of section/team/Division meetings, and the promotion of communities of practice. | Consider feasibility of further team working by mid 2004 Ongoing |  |  |
|  | New Technology and eGovernment |  |  |  |  |
| 10 [21.6 and 21.7] | It is accepted that the use of new technology may necessitate significant change in work processes in order that the benefits of technology will be maximised. There will be full co-operation with the design and implementation of eGovernment projects. | Considerable progress has been made in implementing an IT Strategy for the period 2001- 2005. The main project is a case and records management system shared between this Office and the Office and the Office of the Attorney General. A Financial Management System is also being developed. Work on the introduction of a Management Information Framework and a new HR Management system has started. The introduction of a Legal Know-how application and intranet is under consideration. All these projects will be carried out on a shared basis with the Office of the Attorney General. The Office will continue to co-operate with the Courts Service in the development of its IT strategy. A member of the Office’s IT Unit and a legal staff member currently participate on a group working on the computerisation of the Supreme Court. The Office’s web page ( a joint site with the AGO) will be updated and improved. | Commence implementation of case and records system by November 2003. Issue RFT by July 2003. Finalise RFT for HR management system by August 2003. Ongoing Mid-2004 |  |  |
|  | Atypical Working Arrangements |  |  |  |  |
| 11 [21.8] | The work pattern may be such in specific areas that specific work processes can be performed most effectively by part time staff. | Atypical working patterns apply to 26 staff [12%]. The use of part-time staff is kept under review. A sum-committee of Partnership has produced a report on E-working. The report findings will be reviewed. | Ongoing Mid-2004 |  |  |
| 12 [21.9] | Situations may arise where the need to respond to temporary pressures may require the employment of temporary staff or outsourcing of work. Unions will be notified in advance of initiatives of this kind. | Unions have been consulted and agreed to the use of contract staff to fill vacancies on a short term basis. The Office recognises the need to find alternative approaches in dealing with major cases that cannot be handled within its resources and is developing different models for outsourcing such work. | Mid 2004 |  |  |
|  | Attendance Patterns |  |  |  |  |
| 13 [21.10] | In order to provide a satisfactory level of service to the public, there is a need in certain areas for changes to the standard working day in order to provide services outside the traditional “9 to 5” pattern. The parties are committed to discussions to establish how this can best be achieved, where required. | The Office does not have many direct dealings with members of the public. Maintain a capability to respond to client service requirements outside of normal working hours. The possibility of variable starting and finishing times for professional and technical staff is being considered at Partnership. | End 2003 |  |  |
|  | Redeployment of Staff |  |  |  |  |
| 14 [21.11] | Redeployment of staff may be necessary on occasion to respond to urgent work demands. | Redeployment of staff to meet changing demands for legal services is already a feature of Office administration. | Ongoing review of internal organisation |  |  |
|  | Management of the Introduction of Change and New Development |  |  |  |  |
| 15 [21.12] | In accordance with the partnership approach, unions will be informed in advance of all new significant workplace-related initiatives, the reasons for them and the proposed implementation date. Notification will be given in advance and in sufficient time to allow discussions with the union(s) concerned to take place, Such discussions will cover the nature of the changes involved, the reasons for them and any impact on staff. Subject to this, it is accepted that management have the right to implement changes in accordance with the provisions of the Agreement. | Unions will continue to be consulted in relation to workplace initiatives. The Partnership process provides a regular forum for discussion of any proposals in this area. Additionally, the Partnership Committee has a communications subgroup that has recommended a communications strategy. This has been implemented. | Ongoing |  |  |
|  | eGovernment |  |  |  |  |
| 16 [20.19] 16 a [22.24] | The parties are committed to the further development of eGovernment on the following basis: (i) facilitating better citizen access and interaction with the public service by realising the potential of information and communication technologies (ICTs);  (ii) building collaborative knowledge-based structures focused on serving both citizens and the public service; and  (iii) facilitating continuous adaptation and improvement in service delivery by fully utilising ICTs to deliver public services seamlessly and across traditional boundaries. The parties commit to full co-operation with the further development and implementation of eGovernment policy as outlined in ‘New Connections’, the Government’s Action Plan to realise the potential of the Information Society. | Covered in the paragraphs relating to new technology. The feasibility of an extranet facility between the Office and client Departments/Offices will be considered following the implementation of the new case and records management system. Ongoing co-operation with the Courts Service in the development of electronic court facilities. The Office will review opportunities to contribute to the furtherance of eGovernment following implementation of current IT plans. | 2005 |  |  |
| 17 [20.25] | The parties agree to the establishment of a mechanism to verify that all sectors, organisations and grades in the public service deliver outputs in line with the provisions of this Agreement. This mechanism will be established in accordance with Section 26. | The Office will adhere to any procedures put in place in accordance with Section 26. |  |  |  |
| 18 [22.10] | Open recruitment will be introduced for appointments above existing entry levels and one-year contracts will be extended to all new recruits to the Civil Service starting on 1 January, 2004. | The Office will implement guidelines on one-year contracts for new recruits. | Dec 2003 |  |  |
| 19 [22.11] | In order to deal with certain skills and expertise shortages the following specific measures have been agreed: (i)Beginning with IT, HR and financial management areas, open recruitment will be introduced (ii)Any need for open recruitment will be identified and communicated to the relevant union/unions with a view to reaching agreement on the matter speedily. (iii)The trade unions are committed to co-operating with such open recruitment in circumstances where there is a need for it. (iv)In the event that the parties have difficulties on such issues, a third party adjudication mechanism will be established immediately after ratification of this Agreement. This mechanism will make a final decision on any matter referred to it within a two month period. (v)There will be a review of these arrangements within 12 months to ensure that significant progress is made. | Assess the skills requirements in the IT, HR and financial management areas. The Office has recently appointed a Professional Accountant (on a shared basis with the Attorney General’s Office) on a two year contract. A HR manager was recruited by confined interdepartmental competition in July 2002. | October 2004 |  |  |
| 20 [22.11] | (vi) The Civil Service may recruit in any year a number of staff at the level of Higher Executive Officer, Assistant Principal and Principal Officer (and equivalent grades) equal to the number of staff in those grades who had resigned from the Civil Service in the previous year to take up positions in the private sector or elsewhere in the public sector. (vii) Where posts, which are normally filled by promotion, are filled under the terms of the above arrangements by open competition, they will be regarded as fulfilling the requirements to fill posts by interdepartmental competitions and will also count towards the fulfillment of quotas of posts to be filled by open recruitment at lower levels where appropriate. | Identify numbers who resigned from Civil Service in the course of 2002, at the level of HEO, AP, and PO (and equivalent grades) Conduct exit interviews for staff. Some interviews have already been conducted. Identify numbers who resigned in course of 2003 from Civil Service at the level of HEO, EO and AP (and equivalent grades). | August 2003 Formalise the conduct of exit interviews by September 2003 February 2004 |  |  |
| 21 [22.14, and 22.15] | Discussions will take place so that greater use of competitive, merit-based promotions within Departments will be introduced and progressed over the life of the Agreement. Progress in this regard must be based on competitive selection methods used in Departments demonstrating best practice in this area. Specific measurable progress is to be made within individual Departments on a progressive basis over the life of the Agreement. | As part of an agreement with IMPACT in 2001, competitive promotion was introduced for all professional and technical promotions. Existing arrangements for internal promotions for general service grades will be reviewed in consultation with the Staff Side. Review practice in relation to competitive promotions. | October 2003 September 2004 |  |  |
| 22 [22.16] | In the case of grades that are covered by the Executive Officer dual promotion structure, the following arrangements will apply: (i) Discussions will take place with a view to concluding an agreement on extending the proportion of competitive merit-based promotions within Departments by mid-2004 and their introduction at the first opportunity thereafter; (ii) Where competitive promotion systems do not apply in Departments they will be introduced and progressed over the life of the Agreement. | 50% of promotion to EO already on a competitive basis. Discussions with union on extending percentage of competitive promotions to be initiated. | Mid-2004 |  |  |
| 23 [22.17] | (ii) The proportion of posts filled under mobility provisions of interdepartmental promotion competitions will be increased from 33.3% to 40% from the beginning of the next competitions to be held under the existing arrangements for interdepartmental promotion schemes. This proportion will be increased to 50% from the date equating to the commencement of the next subsequent competition for promotion to Principal level. In this context, provision, will be made where feasible for a scheme of regional interdepartmental competitions outside the Dublin area to be in place as early as possible; | The Office will ensure that 40% of vacancies, in grades covered by existing arrangements for interdepartmental promotion schemes, are filled from interdepartmental panels. | From mid-2003 |  |  |
| 24 [22.17] | In the event that problems arise in direct discussions in relation to the manner in which any of the above provisions are to be implemented, the issues involved will be processed with the aid of a facilitator, and if necessary, referred to a third party adjudication in order to assist the parties meet the objectives identified above. | The Office will, if necessary, in implementing the above provisions avail of a facilitator or third party adjudication. | Ongoing |  |  |
|  | Training |  |  |  |  |
| 25 [20.20] 25 a [22.20] | The parties are committed to continued training and development for all staff The target spend on training and development in the Civil Service will be 4% of payroll by 2003. | In the Office’s strategy statement particular focus is placed on the need for a “knowledge-based” organisation. The importance of ensuring that staff have access to continuing training and development opportunities is emphasised. A specialist training officer was appointed in 2002. Training expenditure in 2002 was 3.2% of payroll. A training needs analysis is near completion and will form the basis for a detailed training and development plan. The plan will also take into account recommendations pertaining to training contained in the Knowledge Management Strategy 2003-2005. | Provision and development of training is ongoing. |  |  |
|  | Partnership |  |  |  |  |
| 26 [22.23] 27 [20.9] | The recommendations of the Review of Partnership in the Civil Service will be considered by a Sub- Group of General Council which will present proposals for the development of partnership to General Council. The parties are committed to building upon the structures that have been established, and to further embedding and refining the process across the public service, in order to deliver real improvements in performance at organizational level, involve staff in the change and modernization process and improve the working environment. | The partnership process is reviewed annually at a one day seminar, the last in December 2002. The Partnership Committee meets monthly and a wide range of topics come up for discussion and decision. A Human Resources Strategy will be drafted and implemented. | Ongoing May 2004 |  |  |
|  | Equality |  |  |  |  |
| 28 [22.25] | The parties agree to continue to work to promote equality of opportunity for all Civil Service staff in accordance with these policies. | The Office will promote existing Diversity and Gender Equality Policies The Office has already achieved the Government target of 33% of AP posts filled by women - 59% of AP level posts in the Office are filled by women. | Ongoing |  |  |
| 28 a [22.27] 28 b [20.21] | The Department of Finance is currently drawing up proposals with a view to developing action plans to ensure that the Government’s policy, of a 3% employment target for people with a disability, is implemented as effectively as possible. Particular consideration will be given to improving monitoring arrangements. The public service will continue to build on the significant progress which has been made in regard to policies on equality and diversity in order to promote equal opportunity in all aspects of civil and public service employment. | The Office’s commitment to the principles of equality is set out in the Customer Action Plan. In the course of refurbishing our main Office building, facilities for wheelchair users were installed. Training on equality issues will be provided for all staff The Office exceeds the gender balance targets already set by the Civil Service. Currently 59% of AP level and 33% of PO level posts are filled by women. The situation will be kept under review. All applications for internal competitions are monitored for gender split, age etc. Report on these issues in annual report. Apply Civil Service policy on harassment, sexual harassment and bullying. Provide awareness training for all staff and ensure particularly that all managers are fully informed on principles and best practice. | June 2005 Ongoing Ongoing Include in annual report for 2003 Ongoing March 2004 |  |  |