Phase 3 of the Performance Verification Process under Towards 2016 Attorney General’s Office, Merrion Street (including the Law Reform Commission)

Progress Report for period March 2007 to December 2007

1.	Modernisation and Flexibility

Highlights for period March 2007 to December 2007 and achievement of Performance Indicators

  - Full co-operation and flexibility maintained and demonstrated by staff in the Office and the Commission in the context of the implementation of all projects including commitment to the adoption of new processes, procedures and systems functionality.

  - Continued intensification of training programme in respect of the Case and Records Management System and Financial Management System.

  - Regular formal and informal review meetings with clients to gauge feedback in respect of service delivery issues.  Any issues raised have been addressed.

  - Data error problem in eISB rectified.  Continued progress achieved in improving usability and accessibility in the electronic Irish Statute Book (eISB) and continued maintenance and updating of the eISB.

  - Statute Law Revision Act 2007 enacted involving repeal of over 3,225 obsolete statutes and retaining 1,364 specifically listed in the first schedule to the 2007 Act.

  - Continued contribution to the Better Regulation Initiative specifically in the context of proposals for preparing by the Commission future Restatements and the Chronological Tables to the Statutes.

  - Law Reform Commission’s Third Programme for Law Reform 2008 – 2015 prepared.

  - Annual Report for 2006 published within 6 months.

  - Meeting of Client and Customer Panel for Advisory and Administrative areas.

  - Official Language Scheme in place.

  - Equality and disability targets met.

- Modernisation and Flexibility

Summary of progress on Action Plan

| Specific Initiatives/Commitments and corresponding specific Actions (Priority) | Action Ns | Target Date for completing Action | Progress Achieved | Performance Indicators |
| --- | --- | --- | --- | --- |
| Modernisation and Flexibility Specific Initiatives/Commitments and corresponding specific actions- 1. The Office and the Law Reform Commission will co-operate with the introduction of all modernisation and flexibility initiatives. Specific Actions include: All staff in the Office and the Commission will co-operate so as to ensure that all IT and non-IT related projects are completed on time and fill in for absent colleagues on leave etc. Such flexibility will be enhanced. (1) Such co-operation and flexibility will be demonstrated in the context of Full approval of the Office’s Partnership Committee and staff in the Commission in this regard, Participation of nominated staff representatives of legal and non-legal sides in the Office and the Commission in the work of Project Teams and other Project Governance Working Groups as appropriate. Agreement of such nominated staff to participate in the work of Project Teams and other Project Governance Working Groups, having regard to the work associated with their respective role and position in the Office and Commission | 1 | Lifetime of Pay Agreement September, 2006 onwards | IT Projects 6 meetings of IT Steering Committee, the over-arching Committee for all IT Projects and representative of the AGO and CSSO, to oversee the implementation of the IT Plan. ACME Project Weekly meetings of the ACME Business Users Group. Weekly meetings of ACME Project Team to discuss specific project deliverables and timelines. Fortnightly meetings of joint AGO/CSSO Project Status Group involving staff representation to oversee the implementation of the Project Plan. Fortnightly meetings of ACME/FMS Interface Group to discuss issues relating to the integration of both systems. Monthly reports to local MAC and Partnership Committee, bi-monthly reports to Main MAC, regular reports to Audit Committee, AGO/CSSO Project Status Group and to joint AGO/CSSO IT Steering Committee by Project Manager on progress towards implementation of Project Plan. FMS/MIF Project 5 meetings of joint AGO/CSSO Project Board involving staff representation to oversee bedding-in phase of system and implementation of new modules of system and roll out of MIF. Monthly reports to local MAC and Partnership Committee, bimonthly reports to Main MAC, regular reports to Audit Committee, to MIF Project Board and to IT Steering Committee by Project Manager on progress towards implementation of Project Plan. Value for Money Reviews 2 Meetings of VFM Steering Committee of Review on the Administration of the Attorney General’s Scheme. Final Report awaiting considered by Director General and Chief State Solicitor. Report on VFM Review of LRC finalised for laying before both Houses of the Oireachtas in mid-December, 2007. Meetings of the VFM Steering Committee and regular meetings of the drafting group on the Maintenance of the electronic Irish Statute Book. Draft Report being revised to take account of comments of the Director General and the Chief Parliamentary Counsel prior to submission for external evaluation and to stakeholders for views. During the reporting period participation by staff in above projects was satisfactory, the attendance was good and issues raised were attended to within agreed timelines. | All IT and non-IT related projects implemented in accordance with agreed timescales. Post-implementation reviews of projects undertaken within agreed timelines and project implementation monitored by appropriate overarching Committee, local and Main MAC (Joint AGO/CSSO MAC) and Audit Committee.. Any outstanding issues identified and resolved within agreed timelines. |
| All staff in the Office will commit to adopting the new procedures, both business process and system functionality, arising from the implementation of all new IT systems within the Office. (1) Such commitment will be demonstrated in the context of Full approval of the Office’s Partnership Committee in this regard Attendance by staff at relevant training courses and adoption of new processes and systems so as to enhance the delivery of core business services. | 2 | September, 2006 onwards | Intensification of programme of user training for ACME and FMS systems continued during the reporting phase. ACME system rolled-out across all areas in AGO & CSSO by end-August, 2007. Active continued support provided by Helpdesk staff to users of ACME and FMS. Regular monitoring by appropriate Project Governance Committees, local and Main MACs, Partnership Committees and IT Steering Committee of projects with regard to approval of expenditure, specific issues and timelines for implementation. Management training being provided to all staff at management level in the Office commencing on 10 December, 2007. Staff in the Office continued to receive much general training. Further development of a more integrated training and development programme for all training requirements (see progress achieved under Action 3 below). On target to meet timelines for relevant training. Benefits of new IT systems to the delivery of core business services being realised in the context of enhanced management information to support better decision making and more efficient use of resources. | Appropriate, just-in-time, on-going training including walk around training provided to all staff on new processes and system functionality within agreed timelines. Appropriate Helpdesk support provided to all staff. Regular monitoring by appropriate Project Governance Committee(s) and local and Main MACs. |
| Continued priority will be given to the provision of appropriate training in the context of the implementation of all IT and non-IT related projects, training identified under PMDS, management training and training in respect IT skills such as ECDL, etc., as appropriate, to all staff in the Office. Specific actions include: (1) |  | September, 2006 onwards Annual Training and Development requirements identified in context of new PMDS Role Profile Forms and delivery of training commenced from January, 2007. Management training RFT issued by end October, 2006, preferred trainer engaged by end January, 2007 and formally engaged by end February, 2007 with all modules of training delivered by December, 2007. | Continued implementation of in-house general IT training programme and all training requirements identified in role profile forms provided on an ongoing basis during reporting period. Draft Terms of Reference for VFM Review of Training and Development prepared. Management training programme commencing on 10 December, 2007. | Ongoing development of a structured and integrated approach to training and development which identifies specific requirements for all positions and grades within the Office. Annual review of specific training course requirements for all positions and grades undertaken. VFM Review of Training and Development function completed by end April, 2008. Recommendations identified implemented within agreed timelines. Management training requirements for 100% of staff in management positions developed and training delivered by end 2007. |
| Filling of post of Training and Development Officer for the Office (2) | 3 | End March, 2007 Engagement of specialist IT Trainer by end January, 2007 | Training and Development Officer engaged by end-May, 2007 and integrated training and development programme for all training requirements progressed during reporting period. Specialist IT trainer in place and intensive training on ACME provided during reporting period. | New Training and Development Officer in place by end March, 2007. Evaluations of courses attended completed by all attendees within agreed timelines and benefits identified. Introduce by mid 2008 database to capture staff evaluations of training courses attended. |
| Development of programme for the delivery of IT skills training such as ECDL, etc., for all staff in the Office. (2) | 4 | Delivery of IT skills training such as ECDL, etc., to staff to commence by end March, 2007. | Development of programme of IT skills training progressed during the reporting period. A programme to deliver more general IT training commenced on 15 October, 2007. User Manual documentation finalised by IT specialist trainer and ACME Business User Group setting out practices, procedures etc. for use of ACME system. Priority continues to be given to training of staff involved in roll-out of ACME and FMS. This training also enhances the general IT skills of staff. | Ensure that 100% of staff have received relevant IT skills training by end 2007. |
| Delivery of training in respect of new PMDS system to all staff in the Office (1) | 5 | New PMDS system training to all staff completed by end October, 2006. | Training on new PMDS system delivered to all existing staff. Training provided to new entrants within 1 – 2 months of arrival. Role Profile Forms under new PMDS in place. Interim Reviews for 2007 completed in almost all cases by end-October, 2007. Annual Reviews for 2007 and new Role Profile Forms for 2008 to be in place by 25 January, 2008. | Training programme for new PMDS system developed and delivered to all staff. |
| 1.4 The Office will continue to meet the target of setting aside 4% of payroll for staff training and development. (2) | 6 | September, 2006 onwards | €160,169 representing 2.01% of payroll allocation incurred on training and development expenditure to date in 2007. €334,000 representing 3.05% of payroll allocated for training and development in 2008 Estimates. Note - The figures quoted above relate solely to direct expenditure on training and development. The figures do not include the salary of the T&D Officer or the costs of travel and subsistence related to attendance at training events. Additionally, ACME training takes place on-site using a specially recruited trainer (cost shared with the CSSO) which helps reduce the costs involved. Priority during the reporting period was on the continued provision of ACME and FMS training. Other training identified in the context of Role Profile Forms has been provided on an ongoing basis. With the engagement of the specialist IT trainer and Training and Development Officer there has been an increased emphasis on the implementation of an integrated training and development programme for all training requirements for staff. | Target of 4% achieved annually. |
| 1.5 The Office will continue to document practices, procedures and precedents as appropriate and provide of appropriate training so as to minimize impact of decentralisation. (3) | 7 | September, 2006 onwards | All Administrative Business Units documentation of practices, procedures precedents reviewed and amended as appropriate. Appropriate training is provided to staff as required. | Documentation of all practices, procedures and precedents achieved and appropriate training provided on an ongoing basis. |
| The Office including the CSSO will publish Annual Reports within a six-month period of the end of the relevant year setting our developments and progress achieved on the implementation of commitments set out in the Statement of Strategy, Client and Customer Charters and Client Service Guide/Customer Action Plan. (2) | 8 | Annual Report 2005 published end October, 2006 Annual Report 2006 published end June, 2007 Annual Report 2007 published end June, 2008 | Published Annual Report 2005 in both languages issued to all client Departments and placed on website by mid-April, 2007. Annual Report 2006 submitted to Government in May, 2007 and laid before the Houses of the Oireachtas and English version placed on Office website and copies made available at Office Reception area by mid-June, 2007. Published Annual Report 2006 (printed, pdf and CD-ROM formats) in both languages issued to all client Departments and placed on website by late-November/early December, 2007. | Annual Reports published within six months of the end of the relevant year reporting upon developments and progress achieved on the implementation of the Statement of Strategy, Client Service Guide/Customer Action Plan and Client and Customer Charters. |
| All staff in the Office will comply with obligations set out in the Client and Customer Charters and Client Service Guide 2005 – 2007. (1) Such compliance will be demonstrated in the context of Compliance with key client service commitments and standards set out in the Office’s QCS publications in the areas of communications with clients, responsiveness to requests from clients, the accuracy and quality of outputs, service delivery to clients and the provision of an ethical and confidential service. (1) | 9 | September, 2006 onwards Staff climate/attitudinal survey conducted by end September, 2007. | Holding of regular formal and informal review meetings by each AC Group with client Departments during reporting phase to discuss service delivery issues. Specific review meetings include: The bimonthly extradition/European Arrest Warrant meetings with client Departments, Garda Síochána and CSSO continue. Issues raised, both in relation to individual cases, categories of cases, management of the area, communications between stakeholders, approaches and strategies to be communicated to panel of counsel, and liaison with requesting States and the Courts Service, are dealt with on an ongoing basis. Review meetings on bimonthly basis with Office of the Director of Public Prosecutions and CSSO regarding constitutional cases in criminal law area, arising out of the Sullivan Report continued during the reporting period. Attendance of Attorney General and OPC representatives at meetings of the Government Legislation Committee and regular meetings between OPC staff and clients. Regular formal and informal review meetings on Administration side held with clients e.g. D/Finance in context of Estimates and requests for additional resources, OPW etc. Points raised at review meetings discussed and addressed within agreed timelines. | Compliance with Guide and Charter gauged through feedback from clients in the context of regular meetings with clients, meetings of the Client and Customer Panel and survey of customers and clients. Staff climate/attitudinal survey completed and compared with previous survey results. Regular formal review meetings held by each AC legal Group with client Departments to discuss service delivery issues.. Any issues raised assessed and addressed within agreed timelines. Engagement in central Review of Customer Charter process |
| Engagement by Office in central initiative to review Customer Charter process. (1) | 10 | Submission of completed Customer Charter Checklist to Fitzpatrick Associates by end January, 2007. | Achieved. | Relevant changes made to service standards as appropriate following completion of review. |
| The Office will convene biannual meetings of the Client and Customer Panel. (2) | 11 | Panel convened by end February, 2007 | Action Plan arising out of first meeting of Client and Customer Panel implemented. External facilitator engaged and meeting of Client and Customer Panel representative of Advisory and Administrative sides held by end September, 2007. Report of meeting of Panel being considered. Issues raised informed the questionnaire that will issue to all clients in the context of the follow-up client survey. | Meetings of Client and Customer Panel convened biannually and feedback gauged. Action Plan put in place to address all issues identified and service delivery channels improved as appropriate. |
| The Office will undertake a further survey of clients. (3) | 12 | Comprehensive electronic based survey undertaken by end June, 2007 | External facilitator engaged and comprehensive questionnaire to issue to all clients in early January, 2008. Follow-up electronic survey completed by end-January, 2008. | Survey undertaken, feedback assessed and service delivery channels improved as appropriate. Client satisfaction ratings compared with prior survey across key parameters of responsiveness, timeliness, professionalism, communications, quality of outputs, consistency, courtesy, etc. |
| 1.10 The Office will publish a new Client Service Guide for the period 2008 – 2010 (4) | 13 | New Guide finalised by end 2007 | Feedback gauged from clients in the context of the follow-up survey will inform the development of new Guide. | New Client Service Guide 2008 – 2010 in place. |
| 1.11 The Office will publish new Client and Customer Charters (4) | 14 | New Client and Customer Charters finalised by mid 2008 | Feedback gauged from clients in the context of the follow-up survey will inform the development of new Charters. | New Client and Customer Charters in place. |
| 1.12 The AGO/CSSO will prepare a draft Scheme to implement the provisions of the Official Languages Act 2003. (2) | 15 | Submission of Revised Draft Scheme to Department by end February, 2007. Scheme agreed with Department and published in both Irish and English languages by end March, 2007. First report to local and Main MACs by end June, 2007 and biannually thereafter. | Scheme finalised and agreed with Department with commencement date of 20 June, 2007. Irish and English version of Scheme published by end-July, 2007. Action Plan to monitor the implement of the Scheme finalised by end-July, 2007. The first report to MAC on the implementation of the Scheme in the AGO and CSSO will be submitted at end-January, 2008. | Draft Scheme approved by Minister for Community, Rural and Gaeltacht Affairs and implemented over period of Scheme. Biannual reports by Irish Language Equality Officers delivered to local and Main MACs on progress towards implementation of commitments set out in Scheme. |
| 1.13 The Office will continue to meet Government targets in relation to the employment of women in posts above AP level and also people with disabilities. (2) | 16 | September, 2006 onwards | The Office continues to exceed the Government targets in relation to employment of women. Currently the proportion of staff at or above Assistant Principal Officer level who are female is 43%, while the proportion of female staff at or above Principal Officer level is 46%. The methods of calculating the proportion of staff with disabilities has been changed from previous years and revised by the Department of Finance. Consequently, earlier this year the Office undertook a census using the revised procedures. Based on a self-declaration process the proportion of staff with disabilities is 3%. The Office exceeds the employment target for women. | Targets set in Government decisions achieved and exceeded. |
| 1.14 The Office will continue to commit to the e-Government agenda, particularly e-Cabinet and e-Legislation. The Office will maintain close contact with other stakeholders including the Houses of the Oireachtas and Government Departments. (2) | 17 | September, 2006 onwards | 2 meetings held with representatives of the Houses of the Oireachtas in relation to collaboration on production of Acts of the Oireachtas. | Regular consultation with stakeholders maintained as appropriate. |
| 1.15 The Office will continue to improve access to legislation through: Maintaining the Electronic Irish Statute Book (pending the consideration of the outcome of the VFM Review. The Office will review how we will deal with the eISB in the future and will approach CMOD and consult with outside interests as appropriate). (1) | 18 | Acts up to end 2005, SIs up to No. 350 of 2005 and Chronological Tables to end 2004 published August, 2006 | Completion of project by external Legal Publishing Company in October, 2007 to provide a solution to the “section data error” problem and directly amend the electronic text of the Act or Statutory Instrument. Updated corrected data set published on eISB website. Continued review of usability and accessibility of eISB website following design update in March, 2006. PDF version of electronic Statutory Instruments were added to the eISB home page. These SIs were procured through the electronic Statutory Instruments system (eSIS). By December, 2007 SIs in the number range 1 – 750 were available. 2005 Chronological Tables and 2006 Acts being incorporated on eISB webpage – to be available in December, 2007. | Continued maintenance of Electronic Irish Statute Book (eISB) on eISB website. |
| Undertaking a consultation process through an electronic web-based survey of users of the eISB to guage user feedback. (1) | 19 | Survey completed by end December, 2006 | Draft Report on the VFM Review of Maintenance of eISB submitted to the Director General and Chief Parliamentary Counsel in October, 2007 and their observations being reviewed prior to issue to external evaluator and stakeholders. Good progress has been made towards finalising the VFM Report which includes recommendations for future strategy. | Responses analysed and results used to inform finalisation of VFM Review |
| The Office will continue to advise Government on a policy to be adopted as regards pre-1922 legislation through Undertaking consultation process with stakeholders (1) | 20 | Report submitted to Government March 2007 Consultation process completed by mid November, 2006 | Achieved Consultation process concluded satisfactorily. | Reports to Government submitted December, 2006, and March, 2007. Comprehensive consultation process undertaken and submissions received to inform drafting of Statute Law Revision Bill 2007. |
| Publication of Statute Law Revision Bill 2007 (This Bill will repeal all remaining pre-1922 legislation for the period 1066 to 1922 – over 3,000 Statutes) (1) | 21 | Bill announced by Taoiseach on 9 January, 2007 | Statute Law Revision Act 2007 enacted in May, 2007 repealing 3,225 obsolete statutes and retaining 1,364 specifically listed in the first schedule to the 2007 Act. Sanction approved for further phases with a reconstituted Pre-1922 Project Team with one Team Leader and 5 Research Assistants, called the Statute Law Revision Project. Work commenced in September 2007 on the next phase of statute law revision which deals with “Local and Personal” and “Private” Acts pre 1922. It is envisaged that these Acts will be dealt with in a Statute Law Revision Bill in 2009/2010. |  |
| 1.16 The Office will continue to contribute to the Better Regulation Initiative and particularly proposals in respect of improving the accessibility and coherence of Irish Statute Law through (1) Co-operation with the Law Reform Commission in relation to proposals for the Commission to prepare future Restatements arising out of the Statute Law (Restatement) Act 2002 (2) | 22 | September, 2006 onwards September, 2006 onwards | Work on the Restatement project started in March 2007 with the preparation by the Commission of a Consultation Paper, which was published in July 2007. It discussed the issues arising in the preparation and production of restatements and included three versions of a restated Freedom of Information Act 1997. A project manager was appointed in August and work is ongoing on the preparation of a report to be published in the first quarter of 2008. Tenders have been received for a customised authoring tool for Restatement and the Chronological Tables and contracts are due to be signed in December. | Proposals for hand-over of functions to the Law Reform Commission completed in a timely manner. |
| Continue to prepare the Chronological Tables to the Statutes and Statutory Instruments (2) | 23 | September, 2006 onwards | Since staffing this new function in July 2007 with a project manager and two legal researchers, the Commission has undertaken an intensive review of the operation of the Chronological Tables including meetings with stakeholders and reviewing international practice with a view to determining best practice methods for the Chronological Tables. As part of this review process, the Commission has been reviewing the nomenclature associated with the Chronological Tables. Building on the review of the existing Chronological Tables, the Commission intends to publish a Consultation Paper on the Chronological Tables of the Statutes in the first half of 2008 which will set out for consultation the Commission’s provisional views on a best practice model for the Tables. The Consultation Paper will deal with matters such as the sourcing of legislative materials (in particular statutory instruments), content, methodology for compilation, quality assurance and presentational and publication formats. It will also examine technological issues. | Future editions of Chronological Tables to the Statutes and Statutory Instruments finalised within agreed timelines and placed on eISB |
| Participation by the Office of the Parliamentary Counsel in any consultation process in relation to changes in layout and presentation of Bills that may be made by the Houses of the Oireachtas. (2) | 24 | September, 2006 onwards | See under Action 17 above. | Participation in consultation process and agreement of any proposed changes in layout and presentation of Bills in a timely manner. |
| Upon initiation by relevant Departments undertake further consolidation and revision/reform of law as appropriate arising out of the publication of Reducing Red Tape an Action Plan for Regulatory Reform in Ireland (1999), Regulatory Reform in Ireland (OECD, 2001) and Towards Better Regulation (2002) and the Law Reform Commission’s Report on Statutory Drafting and Interpretation: Plain Language and the Law. Specific initiatives include: (2) Participation and co-operation with relevant Department to complete consolidation of Company Law legislation. (2) | 25 | Company law legislation consolidation completed by end 2008 | Medical Practitioners Act 2007, enacted in May, 2007. It was a major reforming Bill repealing earlier legislation on the matter. Drafting commenced on this Bill in early December, 2007. | Further consolidation and revision/reform of law completed within agreed timeframes. Participation with relevant Department in consolidation of company law legislation and consolidation completed by end 2008. |
| Participation and co-operation with relevant Department to complete consolidation of Banking and Financial Services legislation. (2) | 26 | Banking and Financial services legislation consolidation completed by end 2009. | The Office is awaiting instruction from the Department on this project. | Participation with relevant Department in consolidation of banking and financial services legislation and consolidation completed by end 2009. |
| 1.17 The Commission will provide a flexible and efficient work environment to enable it to keep the law under review and to make recommendations to Government. (2) | 27 | Lifetime of Pay Agreement | As set out in the Commission’s Business Plan for 2007 - 5 Reports were published - 5 Consultation papers were published Additionally a seminar paper on the Third Programme of Law Reform was published. | Ongoing publication of Consultation Papers and Reports achieved in accordance with agreed timelines. |
| 1.18 The Commission will publish Draft Bills within the Commission’s Reports to enable a speedy legislative response to the Commission’s recommendations. (2) | 28 | Lifetime of Pay Agreement | Draft Bills were included with the publication of all 5 Reports in 2007. | Ongoing publication of Draft Bills within Reports achieved in accordance with agreed timelines. |
| 1.19 The Commission will consult widely in formulating its Third Programme of Law Reform. (2) | 29 | Lifetime of Pay Agreement | The Third Programme of Law Reform has been drafted and was submitted to the Government for approval on 20 November, 2007. The Government in turn referred the Programme to the Joint Oireachtas Committee on Justice, Equality, Defence and Women’s Rights for consideration. | The Formulation and agreement of Third Programme of Law Reform achieved. |
| 1.20 The Office will participate in the process of formulating the Commission’s Third Programme of Law Reform. (3) | 30 | Early 2008 | Consultative Committee convened on 25 September, 2007. Third Programme submitted to Government on 20 November, 2007. | Support and advice provided by the Office to the Commission and Third Programme of Law Reform approved by Government and published. |

2.	Stable Industrial Relations

Highlights for period March 2007 to December 2007 and achievement of Performance Indicators

  - Continued fostering of good industrial relations through the Partnership process and meeting with union and staff representatives as required.

  - Comprehensive review of the Partnership process completed with the adoption of 10 agreed changes to ensure that the Partnership process remains effective and useful in the future.

  - Formal communication channels agreed with newly formed Administrative and legal Units within the Commission.

  - Stable Industrial Relations maintained.

  - Stable Industrial Relations

Summary of Progress on Action Plan

| Specific Initiatives/Commitments and corresponding specific Actions (Priority) | Action Ns | Target Date for completing Action | Progress Achieved | Performance Indicators |
| --- | --- | --- | --- | --- |
| Stable Industrial Relations Specific Initiatives/Commitments and corresponding specific actions 1. The Office and the LRC will co-operate on the maintenance of stable industrial relations and absence of industrial action. (1) Specific Actions include: Continued use of partnership approach in the Office to foster good industrial relations. (1) | 31 | Lifetime of Pay Agreement September, 2006 onwards | 8 ordinary meetings of the Partnership Committee held during the reporting phase to discuss the progress of issues and initiatives. 2 meetings of the Monitoring Sub-Group of Partnership held to review drafts of the Third Progress Report under Towards 2016.. Attendance and participation of members of Partnership is satisfactory and contributes greatly to the maintenance of good industrial relations with the Office. | Monthly meetings of Partnership Committee and regular meetings of Sub-Groups dealing with specific issues held to discuss and progress issues and initiatives. |
| The holding of regular meetings in the AGO between management, staff and Unions as appropriate to discuss any issues of concern not appropriate for discussion at meetings of the Partnership Committee. (3) | 32 | September, 2006 onwards | During the reporting period neither side i.e. Union nor Management had cause to seek a meeting as issues of general interest were discussed in the Partnership forum. However, approximately 8 meetings were held between Union representatives and the HR Manager and/or Head of Administration to discuss issues specific to an individual or limited numbers of staff. | Meetings held promptly to discuss any issues of concern and stable industrial relations maintained. |
| 1.3 The Office will review the Partnership process (3) | 33 | Formal review of Partnership commenced and will be completed by end March, 2007. Subsequent review completed by end 2008. | The Committee held an off-site meeting of members on 26 June, 2007 and discussed the operation of the Partnership process in the Office. The meeting was facilitated by a facilitator from the NCPP. Following workshops and discussions the members agreed to adopt 10 specific changes to ensure that the Partnership process remains effective and useful in the future. | Formal review of Partnership process conducted annually and any agreed changes to process implemented within agreed timelines. |
| 1.4 The Commission will work in partnership with all staff to bring about the changes required for the organisation to work efficiently. (2) | 34 | Lifetime of Pay Agreement | New staff handbook currently being compiled in conjunction with both legal and administrative staff. Training Plan in place. | Implementation of elements of Commission’s Human Resources Strategy achieved within agreed timelines. |
| 1.5 The Commission will continue to develop measures to enhance communications and employee relations. (3) | 35 | Lifetime of Pay Agreement | Formal communications channels agreed with newly formed Administrative and Legal Units within the Commission. | Implementation of elements of Commission’s Human Resources Strategy achieved within agreed timelines. |

3.	Teamworking and Cross Functional Working

Highlights for period March 2007 to December 2007 and achievement of Performance Indicators

- Continued use of team working and cross-functional working to implement all projects, practices and procedures.

- Significant progress made on reviewing the recommendations of the Knowledge Management Strategy 2003 – 2005 with a view to moving the knowledge management agenda forward in both Offices.

- Project Management template adopted for all projects.

- Phase 1 of eJournals project rolled out.

- Commission Publication template rolled out.

3.	Teamworking and Cross Functional Working

Summary of progress on Action Plan

| Specific Initiatives/Commitments and corresponding specific Actions (Priority) | Action Ns | Target Date for completing Action | Progress Achieved | Performance Indicators |
| --- | --- | --- | --- | --- |
| 1. The Office and the Law Reform Commission will commit to the continuation of team working and cross-functional working. Specific Actions include: (1) |  | Lifetime of Pay Agreement | See under for progress achieved. |  |
| This area has been an Office competency under PMDS for a number of years and the Office will continue to adhere to this principle in the context of the implementation of IT systems, projects, practices and procedures. (1) | 36 | September, 2006 onwards | During the reporting period regular reporting by cross-Office and cross-functional Working Groups and Project Teams to meetings of local and Main MACs, other Project Governance Working Groups and Partnership on the progress and implementation of IT and other projects. The reports are comprehensive and are discussed at the relevant meetings. Staff throughout the Office actively participate in cross-functional Groups. | Regular progress reports on projects and initiatives monitored by relevant Committee and local and Main MACs. |
| The Office will continue to promote and adhere to recognized project management principles in the implementation of new IT systems and projects generally. (2) | 37 | September, 2006 onwards Project Management Plan template developed by end April, 2007 | During the reporting period regular progress reports on projects considered at meetings of local and Main MACs, other Project Governance Working Groups and Partnership on the progress and implementation of projects. These are submitted pursuant to Project Management Plan principles. Project Management Plan template adopted for utilisation within the Office for projects. | Project Managers assigned to all major projects, project plans prepared and project governance procedures put in place to implement and oversee as appropriate. Project Management training delivered to relevant staff within agreed timelines. Project Management Plan template utilised in all projects and greater efficiency, cost effectiveness and reporting mechanisms achieved. Regular progress reports to relevant Committee and local and Main MACs. Post-implementation reviews including review of system functionality and user-friendliness in respect of IT systems, conducted within agreed timelines and any issues highlighted assessed and addressed as appropriate. |
| The Office will continue to participate in cross-Departmental initiatives in the context of the delivery of services and the wider Public Service Modernisation Programme. (2) | 38 | September, 2006 onwards | Attendance at Change Management Network, meetings of QCS Officers Network and QCS Research Sub-Group and other centrally organised meetings, conferences, seminars etc on issues relating to the Modernisation Programme and subsequent reporting to Partnership. | Participation in cross-Departmental initiatives as they arise and regular reports made by participants to relevant Committee, local and Main MACs, as appropriate. |
| In line with the Office’s Knowledge Management Strategy, group and other meetings in the Office in conjunction with the CSSO will continue to embed the principles of the Knowledge Management Strategy including the promotion of systems and strategies to promote group working and sharing of legal expertise within both Offices. Among the initiatives to be developed include Legal Issues meetings, Legal Research and Bulletins, examination of user requirements for searchability within ACME system and these initiatives will be developed in accordance with the business needs of the Office and will form the basis for the promotion of sharing legal expertise within both Offices. (2) | 39 | September, 2006 onwards | Advisory and Parliamentary Counsel continued to share knowledge on topical issues of interest during this period through the medium of legal issues meetings. Legal colleagues from the CSSO were invited to AGO legal issues meetings and AGO staff also attended CSSO legal issues meetings. Five issues of both the Legal and ECHR Bulletins were published during this period. These bulletins are a joint AGO/CSSO initiative. These current awareness bulletins are made available to staff on the AGO intranet pages. Workshops were held in regard to full text searching of files and documents contained within each file. Full text searching allows users of ACME to perform complex Boolean type searches for documents. This allows for the use of separators and modifiers in searching for documents allowing for constructs of complex search arguments to be put in place thus narrowing the return of results in searching. This is accomplished through Fuzzy Logic searching. Follow up one-to-one training was also provided to users who requested same and has facilitated those users most interested in “searching” functions within ACME to benefit most for benefit most from same. Workshops are end-user driven and are tailored to the needs of particular groupings or problems. Real active files and problems are addressed allowing for maximisation of time and implementation of fully worked solutions. | Knowledge Management principles applied to share explicit learning and technical and innate knowledge, expertise and know-how. Examine user requirements for searchability within ACME system and provide appropriate training within agreed timelines. Ongoing Legal issues meetings held regularly and attended by legal staff in both Offices to share knowledge on specific legal issues. |
| 1.5 The Office and the CSSO will review Know-how procedures and select and implement a shared know-how database. (4) | 40 | Development of system to commence by end December, 2007 | Progress on the future development of a shared know-how application as per a Recommendation of the Knowledge Management Strategy was made during the reporting period. An overview paper on current know-how solutions in the legal arena was presented to the IT Steering Committee in July. The paper recommended the formation of a know-how sub-group to progress the implementation of a know-how application. The sub-group has met 4 times since its formation in September. A priority issue for the sub-group during this period was the implementation of a solution for the marking and sending of documents for profiling on the know-how application. The sub group will make a recommendation on this to the IT Steering Committee on 11 December, 2007. | Joint-Office Committee established to review and recommend requirements for Know-how database. Know-how database development commenced and implemented within agreed timelines. |
| 1.6 The AGO and CSSO Library and Know-how Units will continue to provide library, research and Know-how services in accordance with best practice. They will continue to collaborate on joint projects and initiatives in order to provide value for money services including the development of an electronic journal project. (1) | 41 | September, 2006 onwards Phase 1 of e-Journal project rolled-out by end February, 2007. | Achieved The AGO Library & Know-how Unit launched Phase 1 of the e-journals project on the 2 April, 2007. Briefly, the e-journals project provides users in the offices with: • Electronic access to a range of journals in the AGO library and the CSSO and DPP libraries from the desktop • Full text searching of these journals • Full text, abstracts and table of contents of journals Four demonstrations and training sessions on using the e-journals interface were provided to staff in the Office. | Phase 1 of e-Journal project developed and rolled-out within agreed timelines. |
| 1.7 The Office will continue to operate a staff mobility policy. (3) | 42 | September, 2006 onwards | Mobility reviewed in the context of filling newly-sanctioned posts in the Office. Reorganisation of Advisory Groups with effect from 6 December, 2007. Due to natural mobility, Decentralisation and a re-organisation of work, administrative staff have had opportunities to move and undertake new duties. The sanction of additional staff resulted in a number of new positions and promotional outlets. There has been significant movement as a result and further mobility needs will be considered as the opportunities arise. | Staff moved within Groups and Business Units so as to attain more experience and achieve more efficient use of resources. Policy regularly monitored and reviewed by Partnership Committee and MAC. |
| 1.8 The Commission will further develop its policy of having legal and administrative staff work together in delivering the outputs of its work. (3) | 43 | Lifetime of Pay Agreement Publication template re-developed by end April, 2007. | Revised Publication template has been rolled out to legal staff and is in use. IT system is currently being upgraded to cater for the new templates and training has been given to all staff A conference was hosted by the Commission to discuss the principles underpinning the Third Programme of Law Reform. | Publication Template developed by legal and administrative staff and applied in the context of the publication of Reports, Consultative Papers and other published outputs. Seminars and Conferences jointly developed as appropriate by legal and administrative staff and hosted within agreed timelines. |

4.	New Technology and eGovernment

Highlights for period March 2007 to December 2007 and achievement of Performance Indicators

- Continued full co-operation demonstrated by staff in the Office and the Commission in the context of the implementation of all IT projects and related new processes, procedures and functionality.

- Further embedding of ACME and MIF.

- Redesigned Intranet gone live.

- ACME system in use in all areas of Office with appropriate training provided.

- Functionality of FMS allows for EFT/IFT/ROS payments and enhanced management reports.

- Resource Allocation and Business Planning project completed in context of 2007 Annual Output Statement.

- New Technology and eGovernment

Summary of Progress on Action Plan

| Specific Initiatives/Commitments and corresponding specific Actions (Priority) | Action Ns | Target Date for completing Action | Progress Achieved | Performance Indicators |
| --- | --- | --- | --- | --- |
| The Office and the Law Reform Commission will co-operate with the introduction and utilisation of new technology and eGovernment. (1) Specific Actions include: In conjunction with the CSSO, continued implementation of new Case and Records Management System (ACME), (1) Human Resources Management System (PeopleSoft) (2) and Management Information Framework and further embedding of Agresso Financial Management System (1) and Knowledge Management Strategy (3). These systems, Application and Strategy will further enable the Office to:- | 44 | Lifetime of Pay Agreement September, 2006 onwards ACME system fully rolled-out in AGO by end April, 2007 | ACME ACME fully rolled-out to all legal users for new all new files by end April 2007. Training was provided to all users of the system with revision training and enhanced training being provided where appropriate. Areas included in the roll out were: Judicial Review (& Planning) Garda Compensations Extraditions, EAW & TOSP Civil Bill Summons Accordingly, from May 2007 all new legal files for the AGO and CSSO were created on ACME. Administration application also rolled out. | ACME System Full Implementation of Case and Records System (ACME) achieved and system in use in AGO by April, 2007. Protocols on new work practices arising from new system agreed and implemented within agreed timelines. Appropriate level of technical input to support and further develop the system provided. Just-in-time training to support roll-out and on-going operation of system provided. Peer review of system completed by end 2007. |
| Review and improve business processes Capture, organise and share knowledge, experience and expertise Provide enhanced financial and non-financial management information and costing reports to facilitate a greater efficiency in the use of resources Provide enhanced and improved high quality services to clients Enhance VFM. Maintain single electronic legal files between the AGO and CSSO |  | In the context of closure of the project ACME Business Users Group re-established and recommenced work in January, 2007 | ACME Business Units Group meets weekly reporting to Project Status Group fortnightly. | ACME Business Users Group re-established, functionality and business process issues and protocols developed to support new work practices addressed within agreed timelines. Post-implementation review of system undertaken within agreed timelines and any issues highlighted assessed and addressed as appropriate within agreed timelines. |
|  | 45 | HRMS go-live in AGO on 5 December, 2006 | HRMS Achieved. | HRMS System implemented in AGO and CSSO by end 2006 in line with central deadlines. |
|  | 46 | Agresso FMS fully functional by end 2006 System upgrade implemented by end October, 2006 Invoice Manager end November, 2006 EFT fully implemented in AGO by end November, 2006. MIF fully implemented by early 2007. | Agresso FMS/MIF EFT/IFT/ROS fully functional since Q3, 2007. The Offices (Merrion Street and CSSO) continue to progress the implementation of the Management Information Framework; In the Merrion Street Office. Invoice Manager refresher training delivered in November, 2007. Comprehensive use of expenditure v budget estimate functionality with FMS Budgeting module Work on fixed asset register completed, Testing now completed on Asset Tracker Module go live date end 2007 Annual Output Statement issued in March 2007. A detailed RAB Model was submitted to the MIF Project Board. Work on development of management statistics within ACME being progressed. The implementation of FMS allows the capture of accruals and commitment information for the administrative subheads. The completion of ACME integration will similarly facilitate the capture of General Law and Counsel Fees accruals information. | Agresso FMS/MIF MIF implemented and utilisation of full functionality in AGO and CSSO achieved by early 2007. Performance indicators in use in Management Reporting in AGO and CSSO by end 2006. Improved Management Reports developed in AGO and CSSO by end 2006 and reviewed monthly by local MACs and bimonthly by Main MAC thereafter. Improved performance and day-to-day decision making achieved by end 2006. Detailed commitments and accruals information available by April, 2007. Costing Reports developed in AGO and CSSO by end 2006, and reviewed monthly by local MACs and bimonthly by Main MAC thereafter. Resource Allocation and Business Planning project completed by end February, 2007 with initial Output Statement available by end March, 2007. |
|  | 47 | Review of Knowledge Management Strategy commenced by end June, 2007. | A Knowledge Management Committee consisting of staff representatives of both the AGO and CSSO was formed in July to progress the review of the Knowledge Management Strategy. The Committee met three times since its formation. The Committee circulated a comprehensive questionnaire to AGO/CSSO staff on the recommendations of the KM Strategy 2003-2005. The aim of the questionnaire was to gather feedback from staff which will assist the Committee in drafting any new Knowledge Management Strategy for the Office. A report on the results of the questionnaire was presented to the KM Committee on 22 November, 2007. | Strategy reviewed and recommendations implemented within agreed timelines. |
| The Office will continue to develop an interface between the new Case and Records Management System and the Agresso FMS so as to enhance the quality and quantity of management information and facilitate the introduction of a comprehensive costing framework. (2) | 48 | Interface rolled-out on pilot basis by end April, 2007. Fully rolled-out by end October, 2007. | The interface has been developed to allow automatic transfer of information between ACME & FMS systems. This should result in a “closed system” whereby systems communicate seamlessly. The interface is operational on the live system for new cases created in the CSSO upon case creation from June 2007. Transactional Data is subject to redevelopment, following which UAT will take place. UAT is planned for with the scripts have been prepared with a pilot group nominated to complete testing in January, 2008. A costing framework providing bimonthly statistical reports is currently being developed for the provision of non financial information. | Interface between ACME and FMS developed and operational on a pilot basis by end April, 2007. Interface fully rolled-out by end October, 2007. Enhanced financial and non-financial management information and costing reports utilised and reviewed by local and Main MACs to achieve better decision making and enhanced use of resources |
| 1.3 All staff in the Office will continue to commit themselves to adopting the new procedures arising from the implementation of new IT systems, Applications and Strategies within the Office, in particular, full compliance with training obligations and other aspects which fall out of the implementation of the Case and Records Management System, HRMS, Agresso FMS, Management Information Framework, e-Cabinet etc., and full co-operation with IT training to ensure levels of IT proficiency. (1) | 49 | September, 2006 onwards | See progress achieved under action 2 above. | Systems and new procedures implemented and operational within agreed timeframes and training delivered within agreed timeframes. Regular review of new procedures and progress reported to appropriate Committee, and meetings of local and Main MACs. |
| 1.4 The Office will continue to review and develop its intranet and bilingual website so as to provide up-to-date services information on the Office and enhanced services to both internal and external clients and customers including people with disabilities. (3) | 50 | September, 2006 onwards | An Office Internet/Intranet Review Group had its first meeting on 10 October, 2007 and agreed three main objectives: 1) Review on an ongoing basis of each Business Unit’s content on the Internet and Intranet, 2) Agree a process for each Business Unit to sign-off both new and amendments to existing content and 3) Agree a process for submitting new and amended content to the IT Unit for placing on the Internet and Intranet as appropriate. The Office Intranet site was redesigned to allow better access to the large amount of documentation now available. This redesign went live on 5 December, 2007. | Intranet and website development in AGO and CSSO reviewed monthly by local MACs and biannually by Main MAC. |
| 1.5 The Office will update its IT Strategy. (4) | 51 | Mid 2008 | During the reporting period work has progressed and is well advanced on drawing up an Invitation to Tender for external assistance for a new IT Strategy. | New IT Strategy finalised by mid 2008. |
| 1.6 The Commission will complete the next stage of the e-Conveyancing project which involves making a recommendation to Government as to the appropriate e-Conveyancing model for Ireland. (3) | 52 | End 2008 | The Commission prepared an Invitation to Tender on the eConveyancing road map. | e-Conveyancing Report finalised and published. |
| 1.7 The Commission will identify and implement an IT policy for the Restatement project. (2) | 53 | End 2007 | Requirements analysis has been completed by the Commission and tendering process is in place to identify a suitable vendor to provide a solution for the authoring tool needed for both the Chronological Tables and Restatement projects. | Policy finalised and implemented by agreed deadline. |

5.	Service Delivery Options (including outsourcing)

Highlights for period March 2007 to December 2007 and achievement of Performance Indicators

- Continued consultation with Unions in relation to the engagement of temporary and contract staff.

5.	Service Delivery Options (including outsourcing)

Summary of Progress on Action Plan

| Specific Initiatives/Commitments and corresponding specific Actions (Priority) | Action Ns | Target Date for completing Action | Progress Achieved | Performance Indicators |
| --- | --- | --- | --- | --- |
| 1. The Office and the Law Reform Commission will commit to the continuation of the employment of temporary, part-time or contract staff, contracting out of work to the private sector or outsourcing or transferring it to other public service bodies or a combination thereof, as appropriate, so as to ensure that services are delivered more effectively or efficiently, or both, including the following: 1.1 The Office will continue to consult as appropriate with Unions in relation to the engagement of temporary, part-time or contract workers. (1) | 54 | Lifetime of Pay Agreement September, 2006 onwards | There was consultation with relevant Unions about the continued engagement of temporary staff and a Contract Drafter. Consultation takes place regularly and Unions are kept informed on plans in this respect. | Consultation as appropriate with Unions and any issues resolved satisfactorily. |
| 1.2 The Commission will investigate and assess other law reform research delivery options both national and international and utilise all available channels, to ensure the most effective delivery of law reform research services, including shared research services where appropriate with Government Departments and Agencies. (3) | 55 | Lifetime of Pay Agreement | The Commission hosted a meeting of all law reform bodies in Ireland and UK in July of this year. | Ongoing communication with stakeholders maintained. |

6.	Shared Services

Highlights for period March 2007 to December 2007 and achievement of Performance Indicators

- Continued contribution to effective public service by assisting in the co-ordination of the legal services of the State.

- Continued provision of legal services to Government in the implementation of litigation policies and in the handling of cross-Departmental issues.

- Continued management of the integration of legal services with the CSSO.

- Continued attendance at and participation in many inter-Departmental Working Groups, Committees and Commission by legal staff.

- Continued implementation and expansion of secondment of Advisory Counsel project.

- Review of Advisory Counsel secondment project completed.

6.	Shared Services

Summary of Progress on Action Plan

| Specific Initiatives/Commitments and corresponding specific Actions (Priority) | Action Ns | Target Date for completing Action | Progress Achieved | Performance Indicators |
| --- | --- | --- | --- | --- |
| 1. The Office and the Law Reform Commission will commit to the introduction of shared services as appropriate with related Offices/organisations so as to give rise to efficiencies or cost savings. Specific initiatives will include: 1.1 The Office will continue to contribute to effective public service by assisting in the co-ordination of the legal services of the State through Continued co-operation and co-ordination with legal advisers in Government Departments (1) | 56 | Lifetime of Pay Agreement September, 2006 onwards September, 2006 onwards | Regular co-operation and co-ordination with legal advisors in Government Departments during the reporting period on many important issues. This regular formal and informal co-operation and co-ordination with legal advisers in Government Departments has and will continue to contribute to effective public service by assisting in the co-ordination of the legal services of the State. | Co-ordination with legal advisers in Government Departments demonstrated and 6 monthly review meetings held. |
| Development of Protocol for the secondment of Advisory Counsel to Government Departments (1). | 57 | End August, 2006 First Advisory Counsel trained and seconded by early October, 2006 Reviews completed end June, 2007 and 2008 | Significant progress made during the reporting period on recruiting, training and seconding Advisory Counsel to participating Departments. By October, 2007, 7 additional Advisory Counsel were recruited and are undergoing training. The next secondments are scheduled to take place in April, 2008. Further recruitment of Advisory Counsel to be seconded to participating Departments will be made by end-March, 2008. During the reporting period general and specific training tailored to the needs of the particular Department that they were seconded to was provided to each secondee. Ongoing advice and support was provided to each secondee. This important initiative assists in the co-ordination of the legal services of the State. 4 further Departments have indicated their desire to accept Advisory Counsel and another Department has requested a second Advisory Counsel. The Office has commenced the process to recruit and train the required staff. | Protocol developed and implemented. Annual reviews of secondment of Advisory Counsel arrangements completed by end June, 2007 and 2008. |
| 1.2 The Office will continue to provide legal services to Government in the implementation of litigation policies and in the handling of cross-cutting issues through Continuation of system to facilitate and co-ordinate the approach to domestic and European Court of Justice litigation (1) | 58 | September, 2006 onwards Annual review completed by end September, 2006, 2007 and 2008. | Continued direction of legal strategy by Advisory Counsel as appropriate to ensure ongoing effective management of domestic and European Court of Justice litigation. This has involved regular review meetings with CSSO and Departmental officials during the reporting period. | Annual reviews of system to facilitate and co-ordinate the approach to domestic and ECJ litigation completed by end September, 2006, 2007 and 2008. |
| Continued participation in interdepartmental working groups and committees in the handling of the legal aspects of cross-cutting issues including the implementation of cross-cutting policies where they arise. (1) | 59 | September, 2006 onwards | During the reporting period regular attendance at and participation in many interdepartmental Working Groups, Committees and Commissions by Advisory Counsel demonstrated through delivery of advice on legal aspects of cross-cutting issues.Cross-Departmental issues are also addressed in the context of bimonthly meetings of the joint AGO/CSSO MAC and Legal MAC. The circulation of the four-monthly Memorandum and Report on Sensitive and Constitutional Cases to relevant Departments, prior to its submission to Government provided an opportunity for Departments to review these important cases and submit observations for inclusion in the Report to Government. | Participation demonstrated through attendance and delivery of legal advice as appropriate. Participation in the rollout of the ACME system; Development of protocols and workflows for the proper use and application of the ACME system. |
| 1.3 The Office will continue to manage the integration of legal services with the CSSO. (1) | 60 | Lifetime of Pay Agreement | Regular meetings with the CSSO and other stakeholders as appropriate to discuss important cross-Office issues in the areas of extradition and asylum. |  |
| 1.4 The Commission will pursue joint initiatives with the Department of Justice, Equality and Law Reform on Land Law and e-Conveyancing and with the Courts Service on the Courts Acts. (1) | 61 | Lifetime of Pay Agreement | The Commission published a Consultation Paper on Reform of the Courts Acts. The Commission prepared an Invitation to Tender on the eConveyancing road map. | Ongoing joint initiatives progressed within agreed timelines. |

7.	Attendance Patterns and Management

Highlights for period March 2007 to December 2007 and achievement of Performance Indicators

- Continued commitment to the introduction of flexible attendance patterns to enhance the delivery of services to clients.

- e-working pilot scheme reviewed and establishment of Sub-Group of Partnership to consider the future operation of the scheme.

- Continued out-of-hours service provided.

- E-working pilot scheme reviewed.

7.	Attendance Patterns and Management

Summary of process on Action Plan

| Specific Initiatives/Commitments and corresponding specific Actions (Priority) | Action Ns | Target Date for completing Action | Progress Achieved | Performance Indicators |
| --- | --- | --- | --- | --- |
| The Office and the Law Reform Commission will commit to the introduction of flexible attendance patterns as appropriate so as to facilitate the work of the Office and the Commission and provide improved services to clients. The Office, however does not have many direct dealings with the public and this is, therefore, not a significant issue. (1) Specific initiatives include: Any proposed changes to attendance patterns will continue to be implemented through Partnership. (3) | 62 | Lifetime of Pay Agreement September, 2006 onwards | Changes in attendance patterns in a particular area of the Office was effected through consultation with relevant staff. | Proposed changes discussed and agreed as appropriate through the Partnership process at monthly meetings of Partnership Committee. |
| The Office and the Commission will continue to operate systems whereby certain staff are available where necessary out-of-core hours. (2) | 63 | September, 2006 onwards | The Office and the Commission continued to operate informal and formal systems whereby certain staff, both legal and non-legal were available where necessary to work out-of-core hours. | Out-of-core hours service provided and satisfaction gauged through client feedback. |
| 1.3 Atypical working arrangements will continue to be a feature in the Office. Staff can avail of initiatives such as job-sharing, term time, parental leave and special leave and the Office will continue to look favourably on such applications subject to the overall needs of the Office (2) | 64 | September, 2006 onwards | Atypical working arrangements continued to be implemented during the reporting period and all requests for atypical working arrangements were accommodated. | Applications for atypical working initiatives assessed in a positive manner and staff facilitated as appropriate. |
| The Office will continue to promote and operate a pilot e-Working Scheme as appropriate. (2) | 65 | E-Working Pilot Scheme reviewed by end February, 2007. | In September, 2007 the local MAC considered a report on the e-working pilot scheme following a comprehensive review of the scheme. The Partnership Committee also considered the report and agreed to establish a Sub-Group of Partnership with a view to looking at options for the future operation of the scheme. | E-Working Pilot Scheme reviewed and a formal decision as to the efficiency of system and its future to be taken. |

8.	Redeployment of Staff

Highlights for Period March 2007 to December 2007 and achievement of Performance Indicators

- Redeployment of staff in particular areas agreed in consultation with relevant staff.

- Staff released to decentralising Departments.

8.	Redeployment of Staff

Summary of Progress on Action Plan

| Specific Initiatives/Commitments and corresponding specific Actions (Priority) | Action Ns | Target Date for completing Action | Progress Achieved | Performance Indicators |
| --- | --- | --- | --- | --- |
| 1. The Office and the Law Reform Commission will commit to the redeployment of staff as appropriate within the same location but also within agreed defined areas or defined distances to respond to urgent work demands. Specific initiatives include: Any proposed changes to redeploy staff will be implemented through Partnership (3) | 66 | Lifetime of Pay Agreement September, 2006 onwards | There were no significant redeployments of staff necessary during the reporting period. Where redeployment arose in the Office it was done in consultation with relevant staff. | Proposed changes to redeploy staff discussed and agreed through the Partnership process at monthly meetings of Partnership Committee. |
| 1.2 The Office and the Commission will agree to enter discussions to draft arrangements to facilitate lateral mobility between the Civil Service and other sectors of the public service. (4) | 67 | September, 2006 onwards | During the period the AGO assisted LRC staff who wished to move within the Civil Service. | Agreement demonstrated through engagement in discussions as appropriate and finalisation of arrangements. |
| The Office will support the Decentralisation Programme through the timely release of staff on the basis that suitable replacement staff are readily available. (2) | 68 | September, 2006 onwards | During the reporting period the Office released 3 staff members to requesting Departments/Offices. However, the Office continues to experience difficulties due to the inability of either the requesting Department or the PAS to provide replacements. | Staff released to requesting Departments in a timely manner. |

9.	Management of the Introduction of Change and New Developments

Highlights for Period March 2007 to December 2007 and achievement of Performance Indicators

- Continued commitment to the introduction of any new changes and developments through the Partnership process and consultation as necessary between management and unions.

- Commission Strategy and Business Plan reviewed.

9.	Management of the Introduction of Change and New Developments

Summary of Progress on Action Plan

| Specific Initiatives/Commitments and corresponding specific Actions (Priority) | Action Ns | Target Date for completing Action | Progress Achieved | Performance Indicators |
| --- | --- | --- | --- | --- |
| 1. In accordance with the provisions set out in paragraph 28.13 of Towards 2016 the Office and the Law Reform Commission will commit to the effective and efficient management of the introduction of Change and new developments as appropriate. (1) Specific initiatives include: 1.1 The Office and the Commission will continue to discuss any changes and new developments as appropriate with Unions and staff and in the case of the Office through Partnership. (2) | 69 | Lifetime of Pay Agreement September, 2006 onwards | During the reporting period the Office continued to use the Partnership Committee as the main forum to discuss any changes and new developments with staff. Other fora where changes and new developments were discussed were at meetings between Management and Unions and regular Advisory Counsel General Issues meetings. In the Commission a formal meeting between the legal research staff and the administrative staff (including new Unit staff) took place to brief all on new change management initiatives. | Monthly meetings of Partnership Committee and biannual meetings between management and Unions held to discuss any proposed changes and new developments. |
| The Office and the Commission will continue to make extensive use of the intranet and e-mail system to keep staff informed of any changes and new developments. (2) 1.3 The Commission will implement its Business and Strategy Statement 2006 – 2008. (1) | 70 71 | September, 2006 onwards September, 2006 onwards | During the reporting period the regular Reports to MAC, Main MAC and Partnership Committee on any changes and new developments were made available to all staff mainly via the Intranet and the feedback has been very positive. Strategy and Business Plan 3rd quarter review was recently completed | Monthly and bimonthly reports to local and Main MAC respectively and monthly reports to Partnership in respect of changes and new developments reported upon. Reports on any changes and new developments reported to staff via e-mail and intranet in a timely manner. Business and Strategy Statement implemented and reported upon in Annual Report. |

10.	Commitment to Modernisation and Change

Highlights for Period March 2007 to December 2007 and achievement of Performance Indicators

- Projects to benchmark performance at organisational level with similar organisations in other jurisdictions commenced in respect of the AGO Advisory/CSSO legal sides and the OPC.

- Competitions held to recruit additional Advisory Counsel, Parliamentary Counsel and legal researchers.

- Value for Money Policy Reviews in respect of the Attorney General’s Scheme, the Law Reform Commission and the Maintenance of the eISB finalised.

- Corporate and Risk Registers reviewed in the context of the Offices’ Risk Management Strategy.

- Business Plans reviewed to take account of risk management.

- Implementation of recommendations of Sullivan Report including 3 Reports submitted to Government in March, July and December, 2007 on sensitive litigation.

- 10.	Commitment to Modernisation and Change

Summary of Progress on Action Plan

| Specific Initiatives/Commitments and corresponding specific Actions (Priority) | Action Ns | Target Date for completing Action | Progress Achieved | Performance Indicators |
| --- | --- | --- | --- | --- |
| 1. The Office and the Commission are committed to co-operating with this phase of modernization and change. 1.1 The Office and the Commission are fully committed to the integration of PMDS with HR processes in accordance with the full terms of the agreement set out in General Council Report 1452. (1) Specific actions include: The Office’s Partnership Sub-Group will recommend the necessary implementation steps of the new revised PMDS system (1) Provision of appropriate training and familiarization with the new revised model to all staff. (1) Implementation of the new revised model in its first year at end of PMDS cycle for 2006. (1) | 72 73 74 | Lifetime of Pay Agreement September, 2006 onwards Sub-Group already in place End 2006 End 2006 | Achieved Achieved Achieved | HR policies adhered to Partnership agree Action Plan for new PMDS system. Training for new system delivered to all staff. New PMDS system implemented. |
| 1.2 Implement the human resource procedures which follow from the Civil Service Regulation Act 2005. (1) Specific Actions will include: Provide training and familiarization to all staff on the implementation of the HR aspects of the new model to include the assessment cycle, rating scale, Increments, promotions, Higher Scale posts, Probation and Upward Feedback. (1) Review of the Commission of promotional possibilities for staff in the light of reorganisation. (2) | 75 76 | September, 2006 onwards End December, 2006 End 2006 | Achieved D/Finance review was undertaken and the agreed sequences of promotion were communicated to staff. | Training/familiarisation delivered to all staff and feedback from staff gauged and assessed. Review undertaken and communicated to and agreed with staff |
| 1.3 Co-operate with use of modern tools for measuring performance. (1) Specific Actions will include: Implementation of appropriate Performance Indicators highlighted in the context of the Office’s MIF Performance Indicators Project, as set out in the Statement of Strategy 2006 - 2008 and in the context of PMDS and individual role profile forms so as to measure performance at individual, team and organizational level. (1) Follow-up by the Commission of assessment procedures for staff (1) | 77 78 | September, 2006 onwards September, 2006 onwards September, 2006 onwards | See separate report in relation to benchmarking performance at organisational level with similar organisations in other jurisdictions. Performance of individuals monitored via PMDS, of Units/Groups via Business Plans and of Office via Annual Output Statement and Annual Report. Training Plan in Commission is on target as laid out in its Strategy and Business Plans | Performance at individual, team and organisational level measured and reported upon as appropriate. Implementation of an appropriate training plan for each member of staff within agreed timelines. |
| 1.4 The Office will put in place an Action Plan in respect of its existing HR Strategy. (2) | 79 | End October, 2006 | The Office will review the progress of the existing HR Strategy in conjunction with its development of its Strategy for 2008-2010 | Action Plan in place by end October, 2006 and reviewed six-monthly and annually by local and Main MACs respectively. |
| 1.5 The Office will advertise competitions for the recruitment of new legal Advisory and Legal Research staff. (1) | 80 | Competitions advertised by end February, 2007 | During 2007 the Office, in conjunction with PAS recruited 7 Advisory Counsel Grade III. A further competition for Advisory Counsel Grade III was advertised in October and a competition for Assistant Parliamentary Counsel Grade II was advertised in September. Shortlisting and written tests have already taken place for both of these competitions. The interviews for the APC II positions will take place on 10/11 December and the ACIII interviews on 15 – 17 January, 2008. It is anticipated that the resulting new recruits will arrive in the first quarter of 2008. Six Legal Researchers were engaged following a PAS competition in early-March, 2007. | Staff recruited and trained within agreed timelines. |
| 1.6 The Office will develop a new HR Strategy 2008 – 2010 in full consultation with staff. (3) | 81 | End 2007 | Work will shortly begin on the development of a Human Resources Strategy to cover the period 2008-2010. It is anticipated that the Strategy will be delivered to MAC and the Partnership Committee by April 2008. | New HR Strategy 2008-1010 developed, agreed and put in place by end 2007. |
| 1.7 The Office will complete its VFM Reviews on the Administration of the Attorney General’s Scheme (jointly with CSSO), the Law Reform Commission, the Maintenance of the Electronic Irish Statute Book, Training and Development and the Library and Know-how Unit. (2) | 82 | Attorney General’s Scheme end March, 2007 Law Reform Commission end February, 2007 Maintenance of eISB end September, 2007 Training and Development end December, 2007. Library and Know-how Unit by end 2008. | Attorney General’s Scheme VFM Review Report finalised, reviewed externally and currently being considered by the Director General and Chief State Solicitor. LRC VFM Review Report finalised with a view to publication in mid-December, 2007. Maintenance of eISB Draft Report being revised to take account of comments of the Director General and Chief Parliamentary Counsel prior to submission for external evaluation and to stakeholders for views. | VFM Reviews finalised within agreed timeframes. Recommendations fully implemented, reviewed on an on-going basis and reported upon to local MACs (quarterly) and Main MAC (biannually). |
| 1.8 The Office and the CSSO will ensure that the recommendations of the Mullarkey Report on accountability of Secretaries General and Accounting Officers will continue to be implemented. (1) In particular, the Offices will: | 83 | September, 2006 onwards | During the reporting period the Office continued to keep under review internal financial controls aspects of which were also reviewed in the context of specific internal audits. |  |
| Review annually internal financial procedures in both Offices. Reviews will be verified by the Audit Committee. (2) | 84 | End 2006, 2007, 2008 | See above | Reviews undertaken annually and reviewed and verified by Audit Committee. |
| The Offices will undertake Annual Internal Audit Programmes agreed by the Audit Committee. (2) | 85 | 2006, 2007, 2008 | Audit programme is progressing notwithstanding 2 changes in the holder of the post of internal auditor and it is anticipated that practically all the audits listed will be completed on target for 2007. However the need to train the new auditor may lead to a delay in completing the two outstanding final audits in the programme. | Audits undertaken and recommendations implemented within agreed timeframes. |
| The Offices will make an Annual Report to the Audit Committee on the implementation of audit recommendations. (3) | 86 | End February 2007 (Report for 2006), end February 2008 (Report for 2007) | The Report for 2006 was delivered in February 2007. The Report for 2007 is on schedule for delivery in February 2008. | Annual Reports completed and reviewed and approved by Audit Committee. |
| The Office and the CSSO will review its Risk Management Strategy including a Risk Management Policy, a Corporate Risk Register and Risk Registers for each Group/Division/Section/Business Unit. (1) | 87 | Mid-February, 2007 | In accordance with requirements set out in the Office’s risk management policy Group and Business Unit Heads reviewed by end July, 2007 the Risk Register for their respective areas and submitted an assurance statement in this regard to the Secretary to MAC. The process will be repeated in January, 2008. Also MAC members who have been assigned ownership of risk(s) in the corporate risk register reviewed these risks by end November, 2007 and submitted a written report to MAC as appropriate. | Risk Management Strategy including Risk Management Policy, Corporate Register and individual Registers reviewed biannually. Provision of feedback to MAC and Attorney General on areas of significant risk; Embedding of the Office’s Risk Management Strategies including Policies and Registers; External Review of risk assessment procedures at regular intervals; Provision of 8 weekly work management reports (Advisory side only); Agree and adhere to Office policies, protocols and workflows; |
| 1.9 The Offices will minimise penalty interest payments under the Prompt Payment of Accounts legislation. (1) | 88 | September, 2006 onwards | No prompt payment interest was incurred to date in 2007 | Adherence to financial procedures by all relevant staff to avoid penalty interest payments Quarterly reports by Professional Accountant to local and Main MACs on adherence to procedures. |
| 1.10 The Offices will prepare new Business Plans for each Group/Division/Section/Business Unit taking account of the Statement of Strategy 2006 – 2008. (1) | 89 | New Business Plans completed by end February, 2007. | Business Plans for each Group and Business Unit taking account of risk management prepared and reviewed. | Business Plans reviewed bimonthly by relevant Groups/Units and biannually by Main MAC. |
| Recommendations of the Report of the Review of the Office of the Attorney General (Sullivan Report, June, 2006) 1.10 The Office will fully implement the recommendations of the Review of the Office of the Attorney General in accordance with timelines set out in the Action Plan for implementation of the recommendations of the Report. (1) | 90 |  | All 19 recommendations have been fully or substantially implemented and are monitored and reviewed regularly by the Director General, Deputy Director General and at meetings of the local MAC and Legal MAC and by a Review Committee representative of both Offices. |  |
| 1.10.1 The Office should arrange that its risk assessment procedures are reviewed by an external party at regular intervals. (1) | 91 |  | The initial report of the three person panel of external experts was received by the Office in July 2007. | Panel of external experts established by end June, 2006. Appropriate documentation provided to panel to familiarise them with internal procedures and protocols of the Office. Panel to meet biannually and make recommendations to Director General as appropriate. Panel to revert to the Attorney General as appropriate. |
| 1.10.2 Continue to ensure as a matter of priority that all staff are fully aware of the formal risk assessment process in place. (1) | 92 | Process agreed and placed on Intranet on 28 July, 2006. End November, 2006. | Recommendation fully implemented. During the reporting period in terms of regular monitoring and review of this recommendation all Unit Business Plans, Role Profile Forms, and relevant Key Performance Indicators therein prepared by Groups/Units in the Office and individual job holders were prepared and reviewed as appropriate so as to ensure that they contain reference to risk assessment procedures within the Office and compliance with Protocols and Policies applied by the Office. In addition to existing training all new staff through the Induction process were made fully aware of the above mentioned procedures. | Interim process for implementing AG procedures agreed and placed on Intranet by end July, 2006. Business plans arising from new Statement of Strategy incorporating risk assessment for sensitive files agreed. |
| 1.10.3 For each risk identified, seek, in consultation with the relevant line Department, to develop an appropriate containment strategy. (1) | 93 | End October, 2006. Status Reports reviewed in AGO and CSSO for completeness | Recommendation fully implemented. During the reporting period in terms of monitoring and review 3 Memoranda for Government were forwarded in March, July and December, 2007 by the Office listing sensitive cases by reference to the issues involved, implications and status. Before this list was finally attached to the respective Memorandum for Government it was circulated to each Department for its comments. The process by which each Department was made aware of sensitive cases, the implications and issues involved is the process by which this Office enables the relevant line Department to develop an appropriate containment strategy in respect of such cases. Each Advisory Counsel Group held regular review meetings with relevant Departments in core legal areas to review work through put and discuss significant cases. At these meetings discussion took place as to how best to handle and treat significant cases. Also during the reporting period Departments who requested the Office’s views in the context of the development of their new Statements of Strategy were provided with observations where appropriate. In turn the Office invited all Departments and relevant Offices to provide observations for consideration in the context of the development of the Office’s new Strategy Statement. | All relevant Departments briefed as appropriate so as to ensure they develop appropriate containment strategy. Status Reports reviewed to ensure all notification steps to Departments have been taken. |
| 1.10.4 The risk assessment policy and register (currently at an advanced stage) should be finalised and implemented as a priority and should be expressly addressed in the forthcoming Business Plans.(1) | 94 | Mid-February, 2007 | Recommendation fully implemented. During the reporting period Group and Business Unit Plans were reviewed and amended as appropriate to address risk issues relevant to the Group or Unit. All Advisory Counsel Group Business Plans make reference to sensitive case procedures and compliance therewith. | Risk assessment policy and risk registers finalised. Address risk assessment policy in individual business plans. |
| 1.10.5 Apart from the Advisory Counsel I’s co-ordinating and allocation role, an experienced Advisory Counsel II from each group should be assigned a specific responsibility for risk assessment on an ongoing basis as cases are processed through the group. It should, however, be stressed that this augments, but in no sense dilutes the fileholder’s responsibility for processing each case including the submission of important and/or sensitive issues to the Attorney General. (1) | 95 | End October, 2006. End October, 2006. First review completed end January, 2007. | A second audit by nominated ACIIs will take place by end end-January, 2008. Procedures have been put in place to ensure that in future audits will be undertaken 3 times per year. | Suitable protocols/briefing for designated reviewers of compliance with sensitive file procedures. In accordance with agreed protocol ACIIs complete reviews of compliance with sensitive file procedures. |
| 1.10.6 In view of the particular risks attaching to the professional structure, a special debriefing should occur whenever a new co-ordinator is assigned to a group. This should be given by the outgoing Advisory Counsel I and the ‘risk’ Advisory Counsel II post referred to at 1.10.5 above. (1) | 96 | Protocols in place by end August, 2006. | Recommendation fully implemented. | Protocols to ensure effective handover of responsibility to new Group Manager devised and agreed. |
| 1.10.7 The Office should consider establishing a “legal MAC” which the Attorney General would attend – this would focus on current legal issues in the Office, and be informed by (a) the weekly meetings (of groups and of Advisory Counsel Is) and (b) the existing Legal Issues meeting. (1) | 97 | First Legal MAC held on 11 October, 2006. Second Legal MAC held 15 November, 2006. Third Legal MAC held 26 January, 2007. | Recommendation fully implemented. During the reporting period a fourth Legal MAC was held. Procedures have been put in place to ensure that the CSSO receive ACI meeting reports on a regular basis. Also, the agenda for Legal MAC meetings addresses certain legal themes of high relevance and immediacy/or urgency for the meeting. | Bimonthly attendance of Attorney General at Legal MAC meetings. Format and frequency of Legal MAC meetings agreed. |
| 1.10.8 Both the group meetings (chaired weekly by the group co-ordinator) and the Advisory Counsel I meetings (chaired by the Director General) should generate structured reports on the volume, content and status of cases on hands, with particular reference to important and sensitive cases. These reports should be forwarded promptly to the Attorney General and the MAC. (1) | 98 | End August, 2006. | Recommendation fully implemented. | Format for reporting of sensitive cases by ACIs/DG to ACI meetings and MAC and Legal MAC meetings as appropriate agreed. Develop appropriate reports in new Case and Records Management System (ACME). |
| 1.10.9 Mentoring should be implemented as part of the induction procedures for new Advisory Counsel, together with a general checklist of milestones for litigation cases. (1) | 99 | End October, 2006 | Recommendation fully implemented. | Appropriate procedures for mentoring formulated and agreed at MAC and Partnership. |
| 1.10.10 In the immediate term, an office procedure for the standard and consistent recording of risk assessments on sensitive files should be implemented. (1) | 100 | End August, 2006 | Recommendation fully implemented. During the reporting period further development work was completed within the ACME system in relation to management reporting for such sensitive cases. | Verification document template agreed and procedure implemented. |
| 1.10.11The Office Intranet should hold a central collection of all documentation relating to protocols and work practices with regular reminders of content and updates. (1) | 101 | End August, 2006. Working Group made appropriate recommendations on necessary changes by end September, 2006. Reminders issued by end September, 2006. | Recommendation fully implemented. During the reporting period a new Internet/Intranet Review Group was established (see progress reported under action 50 above). The Review Group recommended that information as to sensitivity procedures as held by the Intranet should be examined for user friendliness and accessibility. | Working Group established to review current intranet documentation w.r.t. protocols and work practices. Reminder issued to ACs each 2 months to review latest position on proposals recommended by Working Group and procedures. Working Group on collating documentation on reporting of sensitive or important cases to review reporting documentation prepared within the Office to harmonise and simplify reporting. |
| 1.10.12 The development of Management Information Systems within ACME should be expedited. Pending this, management information reports from the Lotus Notes system should be developed using third party tools. (1) | 102 | End October, 2006 Interim templates developed and rolled-out by end October, 2006. | Development work within ACME on Management Information Reports in relation to sensitive cases was completed. The system generated the Third Report to Government on such cases which was submitted to the Government in December, 2007. | Appropriate management reports developed within ACME and timescales for UAT, pilot and roll-out agreed. Interim templates on new procedures within Lotus Notes system developed and rolled-out to ACs. |
| 1.10.13 ACME should be enhanced to support the Government “Early Warning System” by the production of regular reports for management. (1) | 103 | Mid-October, 2006 | As reported above development work as to management reporting was completed. It is now possible to generate instant reports of the status of all sensitive files at any time following completion of this work. Arising from such reports it will be possible to integrate the reports with the process of notifying the Department of Taoiseach through the “Early Warning” system. | “Early Warning System” Report developed within ACME to replicate manual Report. |
| 1.10.14 The functionality within ACME should be enhanced to include a case-level risk register for sensitive or high-profile cases. This register should have reviews built into the workflow at relevant points in the lifecycle. The ACME system should alert a case handler to assess the risks identified at the opening of a case and at suitable checkpoints during its lifecycle. (1) | 104 | End February, 2007 | A system of alerts to appear within a job holders “to do” list as to review of sensitive files has been developed in ACME. And was rolled out in early-November, 2007. | Case-level risk register developed for sensitive or high profile cases and roll-out by end February, 2007. Alert system developed within “To Do” List within ACME system and roll-out by end February, 2007. |
| 1.10.15 The system of secondment of Legal Advisers, at Advisory Counsel III level, to line Departments should continue to be promoted in consultation with relevant Departments. (1) | 105 | End August, 2006. Initial secondments effected early October, 2006. | Recruitment of seven more ACIIIs was completed and all entered the Office as of October 2007. Five will receive training through to April 2008 and will be seconded to other Departments at that point. Further recruitment of additional ACIIIs for secondement will be completed by early 2008. | Protocols and timescales agreed for commencement of secondments with relevant Departments and initial secondments effected by early October, 2006. |
| 1.10.16 Having regard to the interdependence and importance of communication between the following Offices in serious litigation cases, the Director General should convene a conference to discuss how relevant material including notifications, trial dates and notice of judgment can be most promptly communicated, on receipt by any of the Offices to the other Offices. (1) These Offices are: CSSO, Courts Service, DPP, Chief Prosecution Solicitor’s Office, and Department of Justice, Equality and Law Reform. | 106 | Conference held on 6 October, 2006. End October, 2006. | Recommendation fully implemented. | Format and agenda agreed for conference and conference held by early October, 2006.. Feedback from conference delegates gauged and channels and systems of communication agreed/amended as appropriate. Follow-up meetings held as appropriate |
| 1.10.17 The review supports the proposed re-assignment of the prosecution of fisheries cases to the DPP (who examines all cognate functions). (1) | 107 | Mid-November, 2006. | Recommendation being finalised in the context of discussions between the Director General and the Director of Public Prosecutions. An issue of additional resources in the DPPO is under consideration by the D/Finance. | Mechanisms and timelines for re-assignment of fisheries cases agreed by DG and DPP by end October, 2006. Agreement between DPP and D/Finance on level of additional resources achieved before re-assignment effected. |
| 1.10.18 Equally, it supports the proposed transfer of the Attorney General’s scheme to the Department of Justice, Equality and Law Reform, under whose aegis the civil and criminal legal aid schemes are administered. (1) | 108 | End October, 2006. | Recommendation fully implemented. The administration of the Attorney General’s Scheme transferred to the Department of Justice, Equality & Law Reform with effect from end-February, 2007. | Agreement between DG, CSS and Sec. Gen on mechanisms for transfer of AG’s Scheme achieved. Resolution of prompt payments issue with Attorney General agreed before transfer effected. |
| 1.10.19 The Director General should keep the implementation and operation of the new measures under review – the first such review to be completed within six months. (1) | 109 | End July, 2006. Review Working Groups established by end July, 2006. First Report produced on 4 September, 2006. 4 February, 2007. | During the reporting period the Review Committee set up to review the implementation of the Action Plan met in October, 2007 and finalised a report that issued to the Director General. | Progress assessed and reported upon in Action Plan. Working Group (Review Working Group) with cross-Office representation established to monitor progress under the Action Plan. Monthly Reports produced by Review Group. Review Group reports biannually to Director General. |
| 1.10.20 The implementation of the Attorney General’s procedures (as set out in the appendix to the Review Report) not otherwise set out in this Action Plan. (1) | 110 | End August, 2006. End October, 2006. First Report to be delivered by end October, 2006. Meetings held on 3 July and 13 September, 2006. Reports and lists of above meetings sent to Department on 26 September, 2006. First Memorandum to be submitted by end October, 2006. Second memorandum by end February, 2007. Master list developed by end January, 2007. Review Working Group established by end July, 2006. End August, 2006. (See 1.10.5 above) | All of the Attorney General’s procedures have been implemented. However, with the consent of the Attorney General, certain modifications have been made for the purposes of streamlining such procedures and to ensure there is no duplication of task and to facilitate job holders. A further review of these protocols was completed for the purposes of a report to the new Attorney General so as to ensure that such amended protocols and procedures are approved going forward. | Formal protocols formulated and approved to ensure that all pleadings and submissions in constitution and sensitive matters are approved by the AG, confirmed by the DG in consultation with the CSS and notified as appropriate to relevant Departments and Sec. Gen. to the Government. Progress reviewed on resumption of Legal Term. Bimonthly Report on protocols delivered to Sec. Gen. to the Government. Meetings arranged with DPP’s Office to discuss constitutional challenges and list of such challenges forwarded to Department of Justice, Equality & Law Reform. Department of the Taoiseach provided with report of meetings and list of such cases. Four monthly Memorandum for the information of the Government prepared on important litigation handled by the AGO, CSSO, DPPO and CPS Draft Memorandum circulated to Departments for observations. Development of master list of sensitive and constitutional cases completed Protocol in relation to file verification agreed and reported as appropriate. Protocol for provision of spot checks on compliance with the approval and notification directions agreed. |
|  |  | First Memorandum to be submitted by end October, 2006. Second Memorandum by end February, 2007. Master list developed by end January, 2007. Review Working Group established by end July, 2006. End August, 2006. (See 1.10.5 above) | First Report for 2007 submitted to Government in March, 2007, Second Report for 2007 submitted to Government in July, 2007. Third Report for 2007 submitted to Government in early December, 2007. | Four monthly Memorandum for the information of the Government prepared on important litigation handled by the AGO, CSSO, DPPO and CPS Draft Memorandum circulated to Departments for observations. Development of master list of sensitive and constitutional cases completed Protocol in relation to file verification agreed and reported as appropriate. Protocol for provision of spot checks on compliance with the approval and notification directions agreed. |

11.	Service Channels and Shared Services (see also commitments under 6)

Highlights for Period March 2007 to December 2007 and achievement of Performance Indicators

- Office of Director of Public Prosecutions have agreed in principle to transfer of Fisheries Prosecutions.

- Commission’s Third Programme for Law Reform to be published on 17 December, 2007.

  - Service Channels and Shared Services (see also commitments under 6)

Summary of Progress on Action Plan

| Specific Initiatives/Commitments and corresponding specific Actions (Priority) | Action Ns | Target Date for completing Action | Progress Achieved | Performance Indicators |
| --- | --- | --- | --- | --- |
| 1. The Office and the Commission are committed to the introduction and utilisation as appropriate of available channels to enhance service delivery, including shared services. (1) Specific Initiatives will include: The Office will review and identify all activities/services to ascertain which should be managed by other competent authorities. (3) | 111 | September, 2006 onwards | Discussions progressed with Office of Director of Public Prosecutions on transfer of fisheries prosecutions. | Activities/services reviewed annually to ascertain which, if any, should be managed by other authorities; Division of responsibilities agreed and transfer arrangements with competent authorities made; Guidelines, protocols and transfer arrangements finalised as appropriate. |
| 1.2 The Commission will consult widely in the formulation of the Third Programme of Law Reform to ensure the input of various Government Departments and Agencies in addition to interest Groups and the general public (3) | 112 | Early 2008 | The Commission held 3 seminars in March, April and July, 2007 to which Government Departments and agencies were invited. Submissions were received on the Third Programme of Law Reform which was then submitted to the Government who referred it to the Joint Oireachtas Committee on Justice, Equality, Defence and Women’s Rights. | Third Programme of Law Reform that reflects a wide consultation process published. |

12.	Competitive Merit Bases Promotions

Highlights for Period March 2007 to December 2007 and achievement of Performance Indicators

  - 8 promotional competitions held in Office and all internal promotions in Office and recruitment in Commission filled through competitions.

- Competitive Merit Bases Promotions

Summary of Progress on Action Plan

| Specific Initiatives/Commitments and corresponding specific Actions (Priority) | Action Ns | Target Date for completing Action | Progress Achieved | Performance Indicators |
| --- | --- | --- | --- | --- |
| 1. The Office will continue in conjunction with the Partnership Committee and Unions the already agreed policy under Sustaining Progress of competitive merit based promotions for all positions within the Office. (1) | 113 | September, 2006 onwards. All promotions currently made on basis of merit-based competitions | During the reporting period all promotions in the Office have been as a result of a competitive merit-based interviews. These were based on 8 internal promotional competitions, each of which was run according to Guidelines agreed by the Office’s Partnership Committee and based on the Guidelines issued by the Public Appointments Service. | All promotions made on basis of merit based competitions. |
| 2. In the recruitment of any additional staff (as part of its restructuring exercise) the Commission will fill a number of posts through merit-based processes. (1) | 114 | September, 2006 onwards | A number of staff were recently recruited by the Commission through competitive-based competitions. | A number of additional staff recruited will be via merit-based processes. |

# Comments

3 issues have been published and 2 more will be by the end of December