SUSTAINING PROGRESS

CHIEF STATE SOLICITOR’S OFFICE THIRD PROGRESS REPORT ON

IMPLEMENTATION OF ACTION PLAN COVERING

PERIOD FROM 17 APRIL, 2004 TO 17 SEPTEMBER, 2004

17 September 2004

Note: Progress achieved since second report (together with related specific action) is shown in bold text.

|  | COMMITMENT | SPECIFIC ACTION | DATE | ACHIEVED YES – Y NO - N | IF NOT YET ACHIEVED OR DID NOT MEET COMMITMENT DATE PLEASE PROVIDE FURTHER DETAILS |
| --- | --- | --- | --- | --- | --- |
|  | Common Commitments |  |  |  |  |
|  | CUSTOMER SERVICE |
|  | All public service organisations over the course of this Agreement will be required to commit publicly to service standards for their customers. Performance will be evaluated against these standards and the results published in annual reports or another appropriate format. Improvements in customer service will be a particular focus of the partnership structures going forward. | A Customer Action Plan was issued in mid-2002. That plan sets down objectives for service standards to client Departments / Offices in areas such as meetings and liaison with clients, documentation, response times, consistency of advice, skills development, equality, web site development and Court hearings. |  | Y Following on from a customer survey conducted by the Office a Customer Service Charter has been prepared and adopted. A guide for Government Departments and Offices on how to deal with discovery of documents in legal proceedings has been published and circulated as an aid to civil servants. A module on customer service has been included on the induction course for new staff members. |  |
|  |  | Customer Action Plan Commitments include: Provision of Specialist Service Six specialist legal staff at principal solicitor grade have been appointed. Outcomes are: Dedicated management of property law services for key clients such as Departments of Defence and Communication, Marine and Natural Resources. Re-organisation of resources available to manage and defend court proceedings and Inquiry business in the area of child abuse with particular reference to current High Court litigation, Ryan Commission and Redress Board matters. Dedicated specialist management of Justice and Crime portfolio with particular attention to extradition caseload. Also specialist attention to the commencement and operation of the new European arrest warrant procedure. Strengthening of specialist lawyer input to judicial review cases taken against the Government, Department and State Offices. Strengthening of specialist lawyer input into Constitutional and Commercial litigation cases taken against the State. |  | Y Y Y Y Y Y |  |
|  |  | Commercial Contracts The Chief State Solicitor’s Office has assigned a Solicitor specifically to deal with commercial contract work for Government Departments and Offices. The dedicated unit to deal with work arising from the Commission to inquire into Child Abuse (The Ryan Commission) as described in the last report has expanded due to increased work. A dedicated unit has been established to handle the indemnification of Religious Institutions in childhood abuse litigation. This will comprise three contract Solicitors and a Clerical officer. Teams have been specifically formed to deal with Institutional Child Abuse and Day School Abuse Litigation. |  | Y Y Y Y |  |
|  |  | Communications Strategy, as a Customer Action Issue New logo, corporate design adopted and is due for roll out by October 2003 New web site to be constructed by February, 2004 Work response times to be built in to the workflow controls being prepared for the Case and Records Management System by July 2004. | October 2003 February 2004 | New logo and corporate design adopted by end 2003. Redesigned stationery delivered and full roll out was expected by May 2004. Following discussions with the AGO, it was decided at the joint AGO/CSSO MAC that both offices should share one website. A joint AGO/CSSO group has been set up to design a new layout for the website. This group has also been tasked with ensuring that the new design complies fully with the requirements for disabled access to the information and also that there is a fully functional Irish version. This group has met a number of times and the new design is at an advanced stage. The original CSSO group has generated a large amount of content for publication. It is intended to publish this information on the new website when it is launched. Y Workflows have been signed off in relation to the ACME project | This has been introduced on a phased basis and the full introduction will take place on launch of ACME (Case and Records Management System). |
|  |  | Use of ‘plain language’ as a Customer Action Issue The CSSO is committed to a change-over to ‘plain language’ in all its documentation. This commitment is expressed within the Customer Action Plan. A wide ranging discussion on the need for ‘plain English’ has been initiated within the Office through Partnership and has involved meeting s between senior management and all staff. Further specific action: Use of plain language to be specified for the review of all Office documentation forming part of the case and record management work-flows. Requirement for use of plain English to be included in induction model Use of plain English to be included in Training Plan. Time frame: Immediately. |  | Y Working groups involved in the preparation of precedents for automated workflows for the new Case and Records Management System are emphasising the use of plain language. A Committee set up in January 2004 has determined the format of letters being issued by the Office and are now working on an office manual outlining letter formats, use of plain language, response times as set out in the Office’s Customer Action Plan. All induction courses now deal with the use of appropriate language with a minimum of ‘legalese’ in all Office communications. Y Y |  |
|  |  | Local State Solicitor Service. The Office is currently negotiating terms for the transfer of the local State Solicitor service from the responsibility of the Attorney General to the DPP. A formal Offer to be made to State Solicitors Association mid October, 2003. Conclude negotiations. | October, 2003 End November, 2003 | Offer made in October 2003. State Solicitors Association has expressed dissatisfaction with offer. Negotiations (with a Dept of Finance involvement) are continuing; a meeting was held at end of March, with further negotiations due. Y N | Following agreement with the Department of Finance, the CSSO issued an enhanced offer to the State Solicitor’s Association. Clarification on the offer was sought and given to the Association during August 2004. The Association is currently considering this offer and an outcome is expected by mid-October 2004. |
|  | All Departments and Offices will publish a charter of service standards and report on performance against these standards in their annual report. The Office will publish its First Charter of Service Standards | The work on the writing of a charter of service standards will commence after the completion of the current round of business plans – and not later than early December 2003. To be finalised by February 2004. Client Meetings: Regular client meetings now take place, e.g., OPW Conveyancing and Property cases, State Claims Agency, Childhood Abuse, Public Law, Asylum cases Extradition case reviews Social Welfare Ministerial prosecutions In the case of the Office of Public Works meetings take place at team leader level and are being augmented by lower level meetings to effectively track progress on files at the operational level. A new working group (comprising Head of Property Management, a Team Leader from Property Management, IT support and Team Leader from CSSO) has been formed to develop a system for on-going and effective tracking of files from inception to completion both in OPW and CSSO. The development of milestones is underway both as regards the day to day management of workload and the overall long term management of files. The Office will report on performance achieved against the standards in its respective Annual Reports for 2003 and 2004. |  | Y Y Y The Annual Report for 2002 has been published. The Annual Report for 2003 for the Office is being prepared for finalisation in October, 2004. |  |
|  | EFFICIENT USE OF RESOURCES |
| 2. [20.11] | The parties to this Agreement will co-operate fully with the modernisation and change required to ensure that maximum value is achieved from all public expenditure in terms of defined outputs and outcomes. | Expenditure Reviews: The expenditure review process will commence late 2003 and will be carried out in the following areas. The Attorney General’s Scheme – This is the legal aid scheme funded by the Attorney General’s Office and by which legal fees are paid to applicants in bail cases and criminal judicial review cases. Payments to stenographers – The services of stenographers are being used in a greater number of State cases and are expensive. Review will focus on VFM and opportunities to save costs. Cost Recovery – this review will focus on cost and efficiency issues in the recovery of legal expenses awarded to the State in successful litigation. | November 2003 Spring 2004 Summer 2004 | The process commenced as planned in late 2003 with the selection of project team members from a list of volunteers. In January, appropriate training was provided. Terms of reference have been drafted for the review of the Attorney General’s Scheme and Payments to Stenographers and work is about to commence on the projects. A consultant has been engaged to advise staff involved in relation to the conduct of the reviews. The consultant has already provided the training for team members. He advised on the drafting of the terms of reference and will advise on the collection and analysis of data, on the formulation of findings and recommendations and on the preparation of reports. | The CSSO has engaged an outside consultant to assist this process. Terms of Reference have been agreed and work has commenced on gathering and compiling data. The progress has been slow due to the involvement of key staff in the development and roll out of the FMS |
|  |  | Accountability of Secretaries General and Accounting Officers. The Office Implementation Plan was approved by MAC, Partnership and the Audit Committee. Promote payment by EFT as part of development of new FMS |  | Y Y EFT facility included in FMS during development. Selection of a Commercial Bank after tender process and approval from Department of Finance has taken place. |  |
|  |  | Internal Audit and Risk Assessment. This Office is committed to putting in place a risk assessment policy relevant to each section of the Office. The Internal Audit committee has recommended that a Mobile Phone policy be prepared and introduced to the Office. This draft policy is due for competition by October 2003 and for submission to Partnership and MAC by November 2003. The Audit Committee received presentations from IT Project Managers on Case and Records Management System, e-Legislation, Financial Management System and Human Resources System on 27 February 2003. The Committee will meet Project Managers again before the end of 2004. The first step towards devolution of budgets within the Office will be taken from January 2004. The CSSO is preparing to undertake a review of its internal financial procedures and this review will be complete by February 2004 . | August 2004 Jan 2004 | Y The Audit Committee met on 9th August 2004 to review the Office’s risk management arrangements. Since the last report, the risk assessment exercise has resulted in the development of the following: Staff Mobility policy Scanning of Files policy Policy in relation to file access Establishment of an ‘on-call’ system for solicitor’s and legal executives for critical out of hours work Y The mobile Phone policy was presented to Partnership and the recommendations have been accepted and adopted. Y Y . Y Work is ongoing as issues are identified in the context of the implementation of FMS |  |
|  |  | Financial Management System A new financial management system will be developed and in place by July 2004 in conjunction with the AGO, as part of a wider implementation of a MIF Evaluation of tenders to be completed by end November 2003 and contract awarded. Policy approach to legal service cost methodology to be completed by end November, 2003 First tranche high level financial management (MIF) information requirements to be identified by end November, 2003. Remaining indicators with particular emphasis on costs of legal services to be available by May 2004 Requirement for financial and non-financial indicators are currently being developed across the AGO/CSSO as part of the development of the case and records management system and the FMS. Indicator of human resource type performance will be developed in connection with the HRMS. Sanction for recruitment of account technician staff to be sought / obtained from Department of Finance by February, 2004 and recruited by August, 2004. Roll out of FMS: Full roll out by July, 2004. The Office will, in line with Government Decision of 11 February, 2003, report on progress on implementation of MIF. Payment of Counsels’ Fees: A group has been established to write guidelines on the levels of fees to be sanctioned in personal injury and torts. Report expected October, 2003 | November 2003 November 2003 November 2003 to May 2004 August 2003 to February 2004 February 2004 | Y The CSSO and the AGO on 1 July, 2004 took over functions undertaken previously on their behalf by Accounts Branch, Department of Finance. An EO was assigned to this additional work in the CSSO. Y Y Policy on costing agreed in February 2004 in line with vendor’s project plan. Y A suite of Financial Management reports have been designed in relation to FMS. Testing of the reporting system is ongoing. Testing will be completed once ACME comes on stream Currently performance indicators are contained within the Statement of Strategy, the business plans for the sections and within the role profiles of individual officers. The Office is continuing to develop indicators taking in to account the information potential of the new financial system, the case and records management system and the human resource management system. The Office is developing its management information framework in conjunction with the Office of the Attorney General. N Y New system went live in both Offices on 5 July, 2004. Initially rollout was given to Finance Units and purchasing units. Gradual rollout will continue to end 2004 to all relevant Units. As FMS is being embedded in both Offices Finance Units are working closely to ensure smooth operation of new system. Y N Work is ongoing | This will require testing and continual development once ACME comes on stream Outline job specification has been prepared. This can only be finalised when the actual requirements of the costing system become clear. |
|  | BETTER REGULATION |
| 3. [20.16] 4. [20.17] | The Government is committed to publishing a National Policy Statement on Better Regulation in 2003. A model of Regulatory Impact Analysis (RIA) will be introduced on a pilot basis in a number of Government Departments during 2003. In the light of the pilot phase, a model of RIA appropriate to the Irish context will be introduced. | While the CSSO is not directly involved in servicing Better Regulation policy, the Office of the Attorney General is heavily involved. However, the CSSO will take on the following specific action, To enter into discussions with the Office of the Attorney General to consider a role for the CSSO in furthering policy on Better Regulation. To complete these discussions by mid November, 2003. To adopt a role by mid December, 2003. In addition: Senior staff in the Judicial Review Section have participated in the Law Reform Commission’s research project on practice and procedure in Judicial Review and has made submissions on reform in this area. The Office has accepted an invitation to send a representative to the Special Commission on the practical operation of the Hague Convention on the Service Abroad of Judicial and Extrajudicial Documents in Civil and Commercial Matters and the Taking of Evidence Abroad in Civil or Commercial Matters (The Hague, 28th October to 4th November, 2003). | November 2003 December 2003 2002 and ongoing | Y An Assistant Chief State Solicitor has been assigned responsibility as Liaison Solicitor and agreement reached that CSSO will participate as required in discussions with the Director of Statute Law Revision of the AG's office as regards better regulation generally and in particular legislation between 1235 and 1922 still in force. Y Y Law Reform Commission published a report in February 2004. Y |  |
| 5. [20.18] | Well-drafted, easily understood and accessible regulation can reduce the difficulties and costs of compliance for both businesses and citizens. Building on progress in recent years and utilising the provisions of the Statute Law (Restatement) Act, a structured programme targeted on areas where the benefits to business and the citizen are likely to be greatest will be pursued to achieve these improvements in regulations. |  |  |  |  |
|  | STABLE INDUSTRIAL RELATIONS |
| 6. [19.3, 19.6 and 20.5] | The parties are committed to maintaining a well-managed industrial relations environment to minimise disputes affecting the level of service to the public In this regard the agreement provides that: (i)No cost increasing claims for improvements in pay or conditions of employment will be made or processed during the course of the Agreement. (ii)Precludes strikes or other forms of industrial action on any matter covered by the Agreement. | All parties are committed to the Partnership approach to modernisation within the Office and open discussion between Office and unions. In the event that any issue cannot be resolved within Partnership or by the usual IR processes the parties will utilise the processes established under ‘Sustaining Progress’. Partnership shall continue to play a lead role in the management of change and modernisation. Any staff side proposals to be considered in the context of the commitment to have no cost increasing claims. | Monthly Yearly Monthly | Y Y Y |  |
|  | PERFORMANCE MANAGEMENT SYSTEMS |
| 7. [20.7] | Where these are not already in place, the parties agree that appropriate performance management systems will be introduced so that developed performance management systems will be fully operating in each sector of the public service by 1st January, 2005 | The PMDS has been in place for all staff since November 2001. A review of the system is being undertaken following which proposals for development and amendment will be formulated. The core competences selected for 2004 comprise Customer Service, Communications, Technical Capabilities, Managing People. Plans to roll-out upward feedback are under discussion at a sub-committee of Partnership. A climate survey is being formalised and is due for circulation by December 2003. Sub-committee of Partnership is drafting a position for the Office on the implementation of upward feedback within PMDS. This is due for completion in January 2004. Continue development of more structured approach to the monitoring, assessment and development of staff during probation. HR Section has reviewed the Probation process and has prepared a draft policy document for the guidance of the Office. | Review to be completed by November 2003 October 2003 December 2003 January 2004. | Y Y Y Climate survey completed, report issued to all staff and briefing sessions to explain the results. Focus groups have now been set up and have submitted recommendations on necessary actions to MAC. A paper on the introduction of upward feedback into PMDS in the office and a code of practice, incorporating behavioural guidelines, with a view to insuring the interest of all participants in the upward feedback process will be safeguarded, were prepared by our HR Committee and approved at our Partnership Committee meetings in July and August, 2004. Partnership has agreed to the introduction of upward feedback into this years annual review under PMDS, due to commence in December, and that just in time training will be provided to all staff in October/November 2004 to ensure all involved in the upward feedback process learn to use it effectively and in the way intended. The provision of upward feedback training has been put out to tender. MAC are currently examining over 75 recommendations made by sub-groups of Partnership in a report dated 28th May 2004 arising out of the staff attitudinal/climate survey, with a view to preparing an action plan by the end of September. The role profile and interim review phases of this year’s cycle of PMDS have taken place in the office. Y Y Probation policy prepared and agreed at Partnership. Printed in booklet format and issued to all staff. |  |
|  | MODERNISATION AND FLEXIBILITY |
| 8. [20.6] | The parties are committed to increased flexibility to ensure that public services are delivered in a manner which more closely reflects the needs of its customers. In accordance with this: | Flexibility is a feature of the Office, with regular re-organisation of staff, responsibilities and sections in response to changing demands. The Office will review the organisational arrangements to align them with client needs. Flexibility will be supported by Training Plan which is due in December 2003 Policy approach to rotation of Staff Development of Knowledge Management element of IT Strategy. Specific goal: Seek and obtain Finance sanction for a know-how officer by February 2004 and recruit by June 2004. Identification of specialist requirements of clients and aligning recruitment, training and organisation structure accordingly. The Chief State Solicitor’s Office continues to be flexible in the allocation of its staff resources to Tribunals of Inquiry. It should be noted that the Office currently provides 6 solicitors to work at the Tribunals of Inquiry which are running contemporaneously. In addition the Office has to provide 3 Solicitors as and when required to represent the Public Interest. Office involvement in the MOX arbitration versus the UK (described in the last report) is still continuing. | December 2003 March 2004 | Y Draft training plan prepared and submitted to senior management for consideration. Y Rotation policy agreed at MAC and Partnership. Job description prepared for know-how officer. Position likely to be filled internally in view of restrictions on civil service numbers. Decision will be made following recent recruitment competitions. The AGO/CSSO Library & Know-how Units continued to implement a number of Knowledge Management (KM) Strategy recommendations. Y Y Y | The policy of the Office is to align training to PMDS identified needs and to support ongoing professional legal training for legal staff (Law Society) and to provide IT training to support the new computerisation initiatives of the Office. The position of Know-how officer has been advertised internally. The selection process will be completed by end October 2004. |
|  | TEAM WORKING AND CROSS-FUNCTIONAL WORKING |
| 9. [21.5] | All of the parties will co-operate fully with initiatives in these areas and it remains open to management to implement such initiatives in accordance with the provisions of this Agreement. | Teamwork has been specified as a required competence for PMDS purposes. Examples of effective team working within the Office include: Use of teams within the Asylum Section to create a judgements and advices database (Project completed), to develop asylum law practice workflows and documentation (ongoing) and to collate relevant statutes and S.I.s. Specialist teams have been created in the Public Law Division to deal with child welfare and special education needs, tobacco litigation, taxi de-regulation (1,136 cases), challenges to the intoxilyzer and intoximeter equipment (to detect alcohol level in drink driving – 72 cases), foot and mouth compensation claims by Cooley farmers (70 cases), Donegal Garda cases (over 60 cases), adoption cases and transfer of sentences persons cases. The Conveyancing and Property Law Division of the Office is organised on a Team basis. A Principal Solicitor in the office has been nominated to a cross functional working group set up by the Minister for Justice Equality and Law Reform to examine costs arising from civil litigation. The Office has recently recruited and is currently in the process of training a Solicitor to work in-house with the Refugee Appeals Tribunal in servicing cases where Judicial Review cases are pending or threatened Evidence of ability to lead a team to be sought in promotional process. This action to be embedded into the promotional process immediately and reflected in the documentation of the recruitment process which should be commenced in March, 2004 and completed in August 2004. Team working to be manifest in working with counsel and with Attorney General’s Office. Action: Embed into outcome of review of how solicitor staff interact with staff of AGO: Time Frame: This is being considered in the current review of business plans. Inter-Office Team Work on Legal Issues exists, e.g., This Office with the Attorney General’s Office have set up a joint team to review, analysis and report by November 2003 on the process and payment of counsel fees. The Office, in conjunction with the AGO, has established a dedicated Change Management Unit to co-ordinate on behalf of both Offices the introduction of initiatives arising from the SMI and other initiatives with a change management dimension. Co-operation with third level Institutions The CSSO will hold an EU Conference on the Enlargement of the EU and the role of the Agent to the European Court of Justice. The hosting of this conference in Ireland reflects Ireland’s Presidency of the EU | Consider feasibility of further team working by mid 2004 | The need to develop team working within the work environment is an issue that features in training programmes. Y Y Y Y Y Y Y Cross-functional teams involving AGO and CSSO staff operating in Case and Records Management, Financial Management Systems, Human Resource Management System and other projects. This is particularly the case in respect of ensuring integration in Case and Records Management and Financial Management Systems currently being put in place. Y The guidelines on payment of Counsel fees were reviewed in July 2004. The guidelines are operating well and the payments process will continue to be monitored by joint AGO/CSSO. Y Y The Office co-operates with UCD and DIT to run an intern programme during the summer for students from the University of Tulsa wishing to gain experience in the practice of law in the European environment. The Office also provides limited work experience to transition year students in line with the Department of Education policy Y At an international level, a significant event reflecting Teamworking/Cross Functional working performance of the Office in the ECJ services area was the hosting by the CSSO of a meeting of the European Court of Justice Agents from the 25 EU member states. The outcome of this meeting will be the establishment of a better working relationship with member states and the strengthening of the working network between states. The event took place on the 3rd September 2004 in Dublin Castle. |  |
|  | NEW TECHNOLOGY AND eGOVERNMENT |
| 10. [21.6 and 21.7] | It is accepted that the use of new technology may necessitate significant change in work processes in order that the benefits of technology will be maximised. There will be full co-operation with the design and implementation of eGovernment projects. | The most fundamental change being undertaken by the Office, jointly with the Attorney General’s Office, is the implementation of its IT strategy (2001 – 2005). The changes contemplated in this strategy are enormous in scale and in service terms and HR terms. The constituent elements of the strategy comprise Records policy, Case and records management system Financial management system – Human resource manage system – Knowledge management system. The Office will track developments in the Courts service so as to be enabled to respond fully and immediately to the development of the IT systems servicing the courts. . A new Case and Records Management System is scheduled for full roll out by July 2004.This system will enhance the quantity and quality of management information and facilitate the introduction of a comprehensive costing package in line with MIF requirements. Work on the introduction of a Management Information Framework and a new HR Management system has started. The introduction of a Legal Know-how application and intranet is under consideration. All these projects will be carried out on a shared basis with the Office of the Attorney General. The Office will continue to co-operate with the Courts Service in the development of its IT strategy. A member of the Office’s IT Unit and a legal staff member currently participate on a group working on the computerisation of the Supreme Court. The Office will track developments in the Courts service so as to be enabled to respond fully and immediately to the development of the IT systems servicing the courts . |  | Co-operation with the Courts Service has continued and the CSSO has agreed to participate in a pilot exercise with the Courts Service where a particular case will be re-run in a pilot study to assess the new eCourt system. We are awaiting developments from the Court Service. Y A Principal Solicitor assigned to track developments in the Court Services eCourt project, reports progress to MAC bi-monthly. In addition the Office now participates in the Court Service Customer Forum representing the State in litigation. Considerable work has been done in designing the new Case and Records Management System and in planning for full implementation The new system will go live in pilot areas in December 2004 with full implementation to follow over a period of months. The go live date has been extended too allow for fuller development and testing. The new system has the capacity to effect far-reaching improvements in the level of service to customers. The project team and staff generally have almost completed the preparation of precedents and the updating records in advance of full implementation. The Office is in the process of moving its e-mail system from Lotus notes to Microsoft Outlook and training is almost complete. The Office has created a policy document which has been extensively discussed with Unions and staff and planning has commenced in the establishment of a Registry in the Office. The Registry envisages the scanning of all incoming documentation and a tender document is being drafted in respect of the purchase of scanning equipment. The office has collaborated with the AGO in the development of a fileplan. An inventory has been carried out on the stock of cases and records prior to the implementation of ACME N Y Y | Regarding HRMS following consultants’ review of the implementation of HRMS throughout the Civil Service, CMOD sought tenders for a single third-party to implement a single solution. Until the successful company is chosen the Office can not progress the matter. The closing date for receipt of tenders is 17/09/04. |
|  | ATYPICAL WORKING ARRANGEMENTS |
| 11. [21.8] | The work pattern may be such in specific areas that specific work processes can be performed most effectively by part time staff. | Atypical working patterns apply to 26 staff [12%]. The use of part-time staff is kept under review. Draft policy on providing flexible working hours in a law office will be tested in a litigation section between December 2003 and May 2004. The purpose of the test will be to consider workability within the constraints of litigation time tables. Partnership report on e-working will be re-considered once the main IT developments have been introduced and are working. This matter will be reviewed in January 2005 | Ongoing January 2005 | The Office’s view is that the typical flexi working hours arrangement modelled on the Civil Service plan will not work for solicitors working in a highly demanding litigation environment. The Office will continue to search for a model flexible working hour scheme suited to its needs. The consensus view between management and solicitor staff is that the informal arrangement for flexibility is working well and should be continued. Flexi-time operates for clerical and admin staff A pilot scheme for flexible working for technical staff is running in the State Property Division and the Legal Services Section and will be evaluated in late October 2004 |  |
| 12. [21.9] | Situations may arise where the need to respond to temporary pressures may require the employment of temporary staff or outsourcing of work. Unions will be notified in advance of initiatives of this kind. | Contract Staff: Having regard to the staffing and current phase of development of the Office the best assessment is that the principal demand for contract solicitor / legal executive employees will be for locum staff to replace established staff on breaks or extended leave. This policy has been agreed with unions and with Partnership. A panel of solicitors available for short term employment (locum style) has been put in place. Policy on Outsourcing: The business plans of the Office accept the need for outsourcing of work in the appropriate circumstances and call to ‘develop sustainable policies as regards use of external legal service providers under management of CSSO and in atypical arrangements’. Examples of policy in operation: All outdoor ‘clerking’ duties have been outsourced to a private firm and the service is regulated to the satisfaction of the Office by a service level agreement. External firms of solicitors with particular expertise have been retained by the Office on behalf of the State to act in high profile commercial development of natural resources. This has happened in at least three cases. The Office has recently undertaken to manage a panel of external solicitors for the Office of Public Works to provide the OPW with expert legal service at competitive costs. (This is over an above the work undertaken by the Office directly for the OPW). Requests for Expressions of Interest have been sought by the Office, An interview process is to commence, A panel of suitable law firms will be selected, The panel will be managed by the CSSO on behalf of the OPW. | September 2003 | Y Y Selection of suitable external legal service providers has been completed for the OPW; CSSO to have direct involvement in the outsourcing process. Y Y Y Y A panel of external solicitors for OPW has been set up. Y |  |
|  | ATTENDANCE PATTERNS |
| 13. [21.10] | In order to provide a satisfactory level of service to the public, there is a need in certain areas for changes to the standard working day in order to provide services outside the traditional “9 to 5” pattern. The parties are committed to discussions to establish how this can best be achieved, where required. | The Office has identified three main areas where out of office hours demands can frequently arise. These are: Extradition / European Arrest Warrants/Habeas Corpus and other urgent legal service areas – Satisfactory arrangements are in place but need to be augmented by an ‘on-call’ system calling on a larger number of staff. Negotiations with unions to commence by October 2003. Anticipated that agreement will be in place by end November, 2003. Documentation Demand. There is an occasional demand for late night / week end working in the Documentation Centre to copy and bind large volumes of paperwork required to support litigation. | November 2003 | Y A panel of approximately 30 Solicitors and Legal executives has been in place to deal with ‘on-call’ requirements in relation to extradition and European Arrest Warrants (EAW) and other urgent legal service areas. The staffs are rostered on a two week term and are on call 24 hours a day, including weekends for this period. The implementation has been supported by training. In addition, an out of hour’s facility exists for dealing with certain sensitive asylum matters. Y Satisfactory arrangements are in place This service is now available for late evening work and week-end work. | . |
|  | REDEPLOYMENT OF STAFF |
| 14. [21.11] | Redeployment of staff may be necessary on occasion to respond to urgent work demands. | A policy of re-deployment of staff to meet particularly heavy peaks in work operates informally. However this policy will be more clearly articulated in business plans. Action: Embed in current review of business plans. | December 2003 | Y This issue is addressed in the agreed mobility policy, mentioned above. |  |
|  | MANAGEMENT OF THE INTRODUCTION OF CHANGE AND NEW DEVELOPMENT |
| 15. [21.12] | In accordance with the partnership approach, unions will be informed in advance of all new significant workplace-related initiatives, the reasons for them and the proposed implementation date. Notification will be given in advance and in sufficient time to allow discussions with the union(s) concerned to take place. Such discussions will cover the nature of the changes involved, the reasons for them and any impact on staff. Subject to this, it is accepted that management have the right to implement changes in accordance with the provisions of the Agreement. | Unions will continue to be consulted in relation to workplace initiatives. The Partnership process provides a regular forum for discussion of any proposals in this area. A Partnership sub-committee developed a communications strategy which has been put in place. |  | All change and development proposals are submitted to the Partnership Committee which meets monthly. Items requiring detailed consideration are usually referred to sub-groups. Issues discussed in past six months include MIF, Case and Records Management System, Climate Survey, Customer Survey, Refund of Fee’s Scheme, Paid Study Leave, Management Style Document, Mobile Phone Policy, IT policy issues, Expenditure Reviews, Business Plans, PMDS and Merit Awards. |  |
|  | - eGOVERNMENT |
| 16. [20.19] 16 a [22.24] | The parties are committed to the further development of eGovernment on the following basis: (i) facilitating better citizen access and interaction with the public service by realising the potential of information and communication technologies (ICTs);  (ii) building collaborative knowledge-based structures focused on serving both citizens and the public service; and  (iii) facilitating continuous adaptation and improvement in service delivery by fully utilising ICTs to deliver public services seamlessly and across traditional boundaries. The parties commit to full co-operation with the further development and implementation of eGovernment policy as outlined in ‘New Connections’, the Government’s Action Plan to realise the potential of the Information Society. | The feasibility of an extranet facility between the Office and client Departments/Offices will be considered following the implementation of the new case and records management system. IT link on cases and instructions between CSSO and OPW to be reviewed by end October, 2003. IT link on case and instructions between CSSO and State Claims Agency to be developed. Object: Place on agenda for SCA before December, 2003. Continue co-operation with Courts service on IT and eCourts. Object: Specific responsibility to one member of staff to track, report and respond. Support the Attorney General’s Office as required in the development of e-legislation. Specifically in the interface with case and records management system and by participation on the IT Steering Committee. The Office will review opportunities to contribute to the furtherance of eGovernment following implementation of current IT plans. | 2005 End October 2003 February 2004 December 2004 July 2004 | N In order to protect the integrity of our systems, this facility is being considered as part of the CRMS Y Co-operation continuing. CSSO is participating in a pilot study involving a re-run of a completed case using the newly developed electronic system. The achievement of this is dependant on the Court Service timetable Y |  |
|  | VERIFICATION OF CHANGE MECHANISMS ETC. |  |
| 17. [20.25] | The parties agree to the establishment of a mechanism to verify that all sectors, organisations and grades in the public service deliver outputs in line with the provisions of this Agreement. This mechanism will be established in accordance with Section 26. | The Office will co-operate fully with any procedures put in place in accordance with Section 26. |  |  |  |
| 18. [22.10] | Open recruitment will be introduced for appointments above existing entry levels and one-year contracts will be extended to all new recruits to the Civil Service starting on 1 January, 2004. | The Office will implement guidelines on one-year contracts for new recruits. | Dec 2003 | Y | The Office is committed to implementing these guidelines, once available from Department of Finance |
| 19. [22.11] | In order to deal with certain skills and expertise shortages the following specific measures have been agreed: (i)Beginning with IT, HR and financial management areas, open recruitment will be introduced (ii)Any need for open recruitment will be identified and communicated to the relevant union/unions with a view to reaching agreement on the matter speedily. (iii)The trade unions are committed to co-operating with such open recruitment in circumstances where there is a need for it. (iv)In the event that the parties have difficulties on such issues, a third party adjudication mechanism will be established immediately after ratification of this Agreement. This mechanism will make a final decision on any matter referred to it within a two month period. (v)There will be a review of these arrangements within 12 months to ensure that significant progress is made. | The Office has recently appointed a Professional Accountant (on a shared basis with the Attorney General’s Office) on a two year contract. A HR manager was recruited by confined interdepartmental competition in July 2002. The assessment of the Office is that it requires two account technicians to assist in the implementation of the costing of legal service function of FMS/ MIF. (See comment above). It also requires a transfer of administrative staff from Department of Finance to cope with the delegation of payments intended to take place in. The Office has identified a skills shortage in the area of commercial contracts practice and in the overlap area of commercial conveyancing. It has developed a position which it will put to the unions It is anticipated that the role of the Know-how Officer will be to fill the skills or knowledge gaps as they are identified The appointment of a Records Manager will take place in October 2004 prior to the role out of ACME | October 2004 October 2003 | Y Agreement has been reached with the Department of Finance for the creation of one EO post to deal with additional duties and for specific assistance during the period when the actual transfer of functions is taking place. The policy of the Office is under review in the light of restriction of staff numbers and in the light of emerging skills within the Office. Y Selection process for Know How Officer is in train Y An advertisement for the post of Records Manager has been prepared for the national newspapers |  |
| 20. [22.11] | (vi) The Civil Service may recruit in any year a number of staff at the level of Higher Executive Officer, Assistant Principal and Principal Officer (and equivalent grades) equal to the number of staff in those grades who had resigned from the Civil Service in the previous year to take up positions in the private sector or elsewhere in the public sector. (vii) Where posts, which are normally filled by promotion, are filled under the terms of the above arrangements by open competition, they will be regarded as fulfilling the requirements to fill posts by interdepartmental competitions and will also count towards the fulfillment of quotas of posts to be filled by open recruitment at lower levels where appropriate. | The Human Resources Section has been tasked to do a report on the implication of this requirement for the Office. The report will identify the numbers and grades of staff involved. The report is to be ready for MAC in late November. | November 2003 | Y The Office has provided the relevant information to the Department of Finance |  |
| 21. [22.14, and 22.15] | Discussions will take place so that greater use of competitive, merit-based promotions within Departments will be introduced and progressed over the life of the Agreement. Progress in this regard must be based on competitive selection methods used in Departments demonstrating best practice in this area. Specific measurable progress is to be made within individual Departments on a progressive basis over the life of the Agreement. | As part of an agreement with IMPACT in 2001, competitive promotion was introduced for all professional and technical promotions. Promotions on the professional and technical sides will continue to be exclusively by competitive interview. Management favours a position whereby all promotions on the clerical / administrative side are filled by competition. Negotiations are being scheduled with the clerical and administrative staff unions to reach agreement whereby the Office can move to a situation whereby 50% of all promotions are filled from the inter-departmental panel (itself a competitive process) and the remaining 50% are filled by internal competition. Negotiations are expected to commence n early December, 2003 and to be completed in March, 2004. | October 2003 January 2004 | Y Negotiations with relevant unions have commenced. PSEU have agreed to 100% competition (relates to promotions to HEO and AP grades). |  |
| 22. [22.16] | In the case of grades that are covered by the Executive Officer dual promotion structure, the following arrangements will apply: (i) Discussions will take place with a view to concluding an agreement on extending the proportion of competitive merit-based promotions within Departments by mid-2004 and their introduction at the first opportunity thereafter; (ii) Where competitive promotion systems do not apply in Departments they will be introduced and progressed over the life of the Agreement. | . Discussions with union on extending percentage of competitive promotions to be initiated in early January | January 2004 | Y Discussions with PSEU finished. Agreement to have 100% competition to HEO grade. The Office’s other objectives are substantially achieved in this regard and are awaiting the resolution of outstanding negotiations on one issue |  |
| 23. [22.17] | (ii) The proportion of posts filled under mobility provisions of interdepartmental promotion competitions will be increased from 33.3% to 40% from the beginning of the next competitions to be held under the existing arrangements for interdepartmental promotion schemes. This proportion will be increased to 50% from the date equating to the commencement of the next subsequent competition for promotion to Principal level. In this context, provision, will be made where feasible for a scheme of regional interdepartmental competitions outside the Dublin area to be in place as early as possible; | The Office will ensure that 40% of vacancies, in grades covered by existing arrangements for interdepartmental promotion schemes, are filled from inter departmental panels moving to 50% in line with public policy. | From mid-2003 | Y The CSSO is committed to following promotion sequences as set out by Department of Finance. |  |
| 24. [22.17] | In the event that problems arise in direct discussions in relation to the manner in which any of the above provisions are to be implemented, the issues involved will be processed with the aid of a facilitator, and if necessary, referred to a third party adjudication in order to assist the parties meet the objectives identified above. | The Office will, if necessary, in implementing the above provisions avail of a facilitator or third party adjudication. | Ongoing | Y |  |
|  | TRAINING |
| 25. [20.20] 25a [22.20] | The parties are committed to continued training and development for all staff The target spend on training and development in the Civil Service will be 4% of payroll by 2003. | In the Office’s strategy statement particular focus is placed on the need for a “knowledge-based” organisation. The importance of ensuring that staff have access to continuing training and development opportunities is emphasised. Training expenditure in 2003 was 3.2% of payroll. A training needs analysis is near completion and is due for submission to Partnership and MAC in December 2003 and will form the basis for a detailed training and development plan. Training plan to be brought before MAC in January 2004, before Partnership in February 2004 and adopted by March, 2004. The training plan will provide for full equality training within the Office. This must be evident in the draft plan by December, 2003 The Training Unit in conjunction with the HR Section has examined and revised the Induction process in the Office. All new staff are due to receive Induction Training by the end of December 2003 Staff Training Schemes: The existing scheme for the training of legal executives as solicitors will be continued. The scheme will be reviewed by MAC in September, 2004 to monitor the performance and VFM of the scheme. The existing scheme for the training of clerical staff as legal executives will be continued. The scheme will be reviewed by MAC in September, 2004 to monitor the performance and VFM of the scheme. The Training Unit is to produce a policy on evaluation of Training and the impact of training on the Office for approval by Partnership and MAC by November 2003 With the Introduction of the new ECHR with effect from November 2003, this Office in conjunction with the AGO have initiated lectures so that staff are prepared for this new initiative and are equipped with the necessary skills to serve the requirements of our clients. This Office is committed to the release of staff for secondment to the European Court of Justice, Luxembourg, so as to gain a greater insight into how the Court and its Registry operate. A report was prepared which is being acted upon and which has resulted in the redeployment of an additional Senior State Solicitor to deal with European Litigation. A number of members of staff have been awarded the Law Society’s Diploma in European Law and diplomas in human rights law from UCD. Members of staff have been awarded master’s degrees in human rights law and in public management and several more are studying with the assistance of the Office. The Knowledge Management (KM) Strategy 2003-2005 recommended the production of a joint AGO/CSSO Office Newsletter, as one method of keeping staff informed of general office developments. . | December 2003 September 2004 September 2004 November 2003 November 2003 | A committee has been established to implement the recommendations of a consultancy assessment of the development needs in the area of knowledge management. A staff newsletter is one positive result. Staff training requirements continue to be identified from role profile forms and updates received from interim and annual reviews. The Office policy is to support specialist legal training providers such as the Law Society. The Office supports postgraduate legal and public management training. The Office has identified a significant training need to support the new computerisation initiatives. With the introduction of FMS and ACME, training requirements for end-users have been identified. An equality course design has been developed by the Training Officer with the assistance of an external consultant and delivery of training has commenced. As a result of the examination, plain language and customer service training feature in the induction courses Since its inception, two legal executive staff have benefited under the scheme. Three members of staff are currently training as law clerks and a decision has been taken to continue with the scheme. Y A policy on evaluation was presented to MAC and was accepted and adopted in September 2004 Seven lectures held in 2003 with a further seven scheduled for 2004. Three of the lectures scheduled for 2004 have taken place Two staff have been seconded for short periods to the European Court of Justice. Twenty three staff have undertaken undergraduate and post-graduate courses for the academic year 2003 – 2004. All are covered by the refund of fees scheme. Y Grapevine (a joint newsletter between the CSSO and the AGO), which also has a strong social content, has been published five times since January. The joint newsletter team is comprised of representatives from all sides of the Office and comprises of legal, library, and training, clerical and administrative staff. The content of the newsletter should reflect staffing changes, updates on IT projects, updates on Partnership and Committee activities, topics discussed by MAC and developments relating to PMDS, training and development and library activities. |  |
|  | PARTNERSHIP |
| 26. [22.23] 27. [20.9] | The recommendations of the Review of Partnership in the Civil Service will be considered by a Sub- Group of General Council which will present proposals for the development of partnership to General Council. The parties are committed to building upon the structures that have been established, and to further embedding and refining the process across the public service, in order to deliver real improvements in performance at organizational level, involve staff in the change and modernization process and improve the working environment. | Partnership to meet at least once a month and to maintain a sub committee structure to deal with key Office management and change issues. Partnership meets at least once a month. Maintains the following sub committees Flexi / E-working, Accommodation IT Policy, Business Planning, MIF HR Committee. Communication Steering Group | On-going | Y Partnership has continued detailed involvement in the development of key policies for the Office. |  |
|  | EQUALITY |
| 28. [22.25] | The parties agree to continue to work to promote equality of opportunity for all Civil Service staff in accordance with these policies. | The Office promotes existing Diversity and Gender Equality Policies There is some evidence that in the clerical/administrative grades female staff are disproportionately in the lower grades. (The evidence isn’t definitive). Partnership is anxious for a levelling and the Office agrees that this should be addressed positively through the negotiations with clerical staff on competitions. Gender balance issues for solicitors have been the subject of a study within the Office and will remain on the management agenda. Gender balance issues are to be reviewed annually. This Office will introduce a 1 day programme for senior management and Managers of staff so as to increase Management awareness of the issues relating to Equality and Diversity. |  | Y 58% of AP level posts are filled by women, a figure that is in excess of the Government target of 33% Discussion is ongoing at Partnership Y An equality course design has been developed by the Training Officer with the assistance of an external consultant. | This issue is on the agenda for discussion with the union involved. |
| 28a [22.27] 28b [20.21] | The Department of Finance is currently drawing up proposals with a view to developing action plans to ensure that the Government’s policy, of a 3% employment target for people with a disability, is implemented as effectively as possible. Particular consideration will be given to improving monitoring arrangements. The public service will continue to build on the significant progress which has been made in regard to policies on equality and diversity in order to promote equal opportunity in all aspects of civil and public service employment. | Disability Issues: The Office is short of the 3% target but the number of recruits with disabilities has increased over the past two years. The Office is willing to increase its number of staff with disabilities but suited to the work. The Office will undertake a study of its employment of staff with disabilities. This study will commence in September 2004 and will finish in February, 2005. The Office’s commitment to the principles of equality is set out in the Customer Action Plan. In the course of refurbishing our main Office building, facilities for wheelchair users were installed. Training on equality issues will be provided for all staff | June 2005 | The evidence appears to show that the Office is now marginally short of the 3% target, which is a substantial increase over past year. In relation to the proposed transfer of a Division of the Office to alternative accommodation, the OPW has been requested to have cognisance of the draft document produced by the National Disability Authority regarding accessibility. Y Ongoing |  |